# Legacy CBS → .NET 10 Migration

Estimated effort, timeline, and phasing for management review

Prepared 17 June 2026  ·  Basis: automated scan of the legacy codebase + velocity from delivered pilot screens

# Executive summary

TrustBank CBS is a large core-banking system — 1,458 web screens, ~890 report definitions, and 5,317 stored procedures. Migrating it to the new .NET 10 / C# MVC platform is estimated at roughly 10,550 person-days (~48 person-years), most likely delivered over 2.5–3 years with a team of about 20 (developers, QA, BA, PM).

The reusable foundation — application framework, authentication/session, menu and fail-closed access control, multi-database data-access layer, a library of reusable UI components, and a repeatable per-screen migration recipe — is already built and proven on six delivered screens. That work (typically 15–20% of such a programme) is excluded from the build figures below and materially de-risks delivery; the strangler-fig approach lets us cut over module-by-module rather than in a single big-bang.

This is a Rough Order of Magnitude (ROM) estimate, accurate to about ±40%. A focused 4–6 week discovery (the attached screen-by-screen inventory) would firm it to roughly ±15% and produce a committed Phase-1 budget.

| Likely effort | Indicative timeline | Team size |
| --- | --- | --- |
| ~10,550 person-days (~48 PY) | ~2.5–3 years | ~20 (incl. QA / BA / PM) |

# 1. Measured scope

Counts come from an automated scan of the legacy source (Trust.Bank.Publish and the SQL procedure set):

| Artifact | Count |
| --- | --- |
| ASPX screens (total) | 1,458 |
| — of which Reports | 399 |
| — functional (non-report) screens | 1,059 |
| Report definitions (.rdlc / .rpt) | 892 |
| Reusable user controls (.ascx) | 19 |
| Stored procedures (.sql) | 5,317 |
| VB code-behind files | 1,497 |

Largest modules by screen count: RetailBanking 667, Reports 362, HO 203, Reconciliation 74, Inventory 23, HR / Helpdesk / EmployeeDemand 21 each, Lockers 15.

# 2. Method and assumptions

Bottom-up: each functional screen is classified Simple / Medium / Complex and costed at a per-screen rate calibrated to the six screens already delivered; reports are costed separately; cross-cutting workstreams are added explicitly. Calendar = total effort ÷ (team size × 220 productive days per year).

## Key assumptions

- Foundation already built (excluded from build figures): framework, auth/session, menu + access guard, multi-provider data layer, reusable components (record / account / date pickers, search modal, notifications, opaque row tokens), the per-screen recipe, and six reference screens.

- Stored procedures are migrated with their consuming screen (master CRUD → repository pattern; heavy transactional logic → C# service); only shared “engine” procedures are a separate line.

- A blended team of developers, QA, business analysts, and project management.

- Strangler-fig coexistence → incremental, module-by-module cutover (value delivered early, no big-bang).

# 3. Effort breakdown (likely case)

| Workstream | Count | Rate (pd) | Effort (pd) |
| --- | --- | --- | --- |
| Simple screens (masters, config, lookups, inquiries) | 121 | 1.5 | 182 |
| Medium screens (search/list, multi-tab, dependent pickers) | 751 | 4.0 | 3,004 |
| Complex screens (transactions, maker-checker, calc, batch) | 187 | 10.0 | 1,870 |
| Reports (re-implement) | 399 | 2.0 | 798 |
| Reporting platform setup | — | — | 40 |
| Core engine procedures (interest, balance, day-end, GL, clearing) | 40 | 15.0 | 600 |
| Data migration + parallel-run tooling | — | — | 200 |
| Foundation remaining + cross-provider hardening | — | — | 240 |
| Build subtotal |  |  | 6,934 |
| QA + UAT (30% of build) |  |  | 2,080 |
| PM / BA / DevOps / training / docs (20% of build) |  |  | 1,387 |
| Security review + performance hardening |  |  | 150 |
| TOTAL — likely |  |  | ~10,550 pd (~48 PY) |

# 4. Estimate range

| Scenario | Drivers | pd | PY |
| --- | --- | --- | --- |
| Optimistic | Single-DB, reports rehosted, strong reuse, senior team | ~7,400 | ~34 |
| Likely | Multi-DB, reports re-implemented, normal parallel-run | ~10,550 | ~48 |
| Pessimistic | Multi-DB hardening, full report rebuild, deep parallel-run, scope growth | ~14,800 | ~67 |

# 5. Indicative timeline by team size (likely effort)

| Team (incl. QA / BA / PM) | People | Duration |
| --- | --- | --- |
| Lean | 15 | ~3.2 years |
| Balanced (recommended) | 20 | ~2.4 years |
| Accelerated | 25 | ~1.9 years |

Add ramp-up and final UAT/cutover — a realistic window is ~2.5–3 years at ~20 people.

# 6. Phased roadmap

- Phase 0 — done: foundation, reusable components, pilot screens, migration recipe.

- Phase 1 — Discovery & inventory (4–6 weeks): screen-by-screen catalogue → firm the estimate to ±15%.

- Phase 2 — Masters & config (HO, Config, Lockers, HR): quick wins, prove velocity.

- Phase 3 — Reporting platform + reports (parallel workstream).

- Phase 4 — RetailBanking transactions (the bulk), by sub-module: deposits → loans → clearing → cash → day-end.

- Phase 5 — Reconciliation, Inventory, Helpdesk, EmployeeDemand, Customer360.

- Phase 6 — Data migration, parallel run, cutover, hardening, training.

# 7. Key risks and cost drivers

- Cross-provider SQL (Oracle / PostgreSQL): raw-SQL screens are written in SQL-Server dialect; a single-database target removes ~120–150 pd and de-risks delivery.

- Reports (362 screens + 892 definitions): “rehost” vs “rebuild” swings the total by ~500–700 pd — the single biggest decision.

- 5,317 stored procedures indicate deep embedded business logic (interest, GL, day-end) — the highest-risk, highest-value engines; require senior attention and rigorous parallel-run validation.

- Banking correctness & compliance mandate reconciliation and likely regulator sign-off, which lengthens UAT.

# 8. Recommendation

Approve a 4–6 week discovery phase now. It converts this ROM into a committed plan (±15%), confirms the per-screen complexity in the attached inventory, settles the reports and database-target decisions, and produces a firm Phase-1 budget — all before any large build commitment. The proven foundation means the team can begin delivering migrated screens in Phase 2 immediately afterward.

Supporting workbook: TrustBank-Migration-Estimate.xlsx (editable assumptions, module inventory, and the full 1,458-screen list).