## Slide 1
CORE BANKING SYSTEM MODERNISATION
Legacy CBS → .NET 10 Migration
Effort, timeline and phasing — estimate for management review
~10,550 person-days ~2.5–3 years ~20 team
Prepared 17 June 2026 · Basis: automated scan of the legacy codebase + measured velocity from six delivered pilot screens

## Slide 2
EXECUTIVE SUMMARY
A large system — but the hard foundation is already built
~10,550
person-days likely (~48 person-years)
~2.5–3 yr
indicative delivery window
~20
blended team (dev / QA / BA / PM)
Phase 0
✓ done
foundation + 6 pilot screens
Scope is real: 1,458 web screens, ~890 report definitions and 5,317 stored procedures move to the new .NET 10 / C# MVC platform.
Already in place (excluded from build figures): application framework, authentication / session, menu + fail-closed access control, multi-database data layer, a library of reusable UI components, and a repeatable per-screen migration recipe — proven on six delivered screens. This foundation is typically 15–20% of such a programme and materially de-risks delivery.
Strangler-fig approach → cut over module-by-module, delivering value early with no big-bang. This is a ROM estimate (±40%); a 4–6 week discovery would firm it to ~±15%.
TrustBank CBS · Migration Estimate (ROM ±40%) · Confidential
2

## Slide 3
1 · MEASURED SCOPE
Counted from an automated scan of the legacy source
1,458
ASPX screens (total)
1,059
functional (non-report) screens
399
report screens
5,317
stored procedures
1,497
VB code-behind files
19
reusable user controls (.ascx)
Functional screens by complexity
Chart: 
| Simple | Medium | Complex | Reports
Screens | 121 | 751 | 187 | 399
Largest modules by screen count: RetailBanking 667 · Reports 362 · HO 203 · Reconciliation 74 · Inventory 23 · HR / Helpdesk / EmployeeDemand 21 each · Lockers 15
TrustBank CBS · Migration Estimate (ROM ±40%) · Confidential
3

## Slide 4
2 · EFFORT BREAKDOWN — LIKELY CASE
Bottom-up, calibrated to the six screens already delivered
Workstream | Count | Rate (pd) | Effort (pd)
Simple screens (masters, config, lookups, inquiries) | 121 | 1.5 | 182
Medium screens (search/list, multi-tab, dependent pickers) | 751 | 4.0 | 3,004
Complex screens (transactions, maker-checker, batch) | 187 | 10.0 | 1,870
Reports (re-implement) | 399 | 2.0 | 798
Reporting platform setup | — | — | 40
Core engine procedures (interest, GL, day-end, clearing) | 40 | 15.0 | 600
Data migration + parallel-run tooling | — | — | 200
Foundation remaining + cross-provider hardening | — | — | 240
Build subtotal |  |  | 6,934
QA + UAT (30% of build) |  |  | 2,080
PM / BA / DevOps / training / docs (20%) |  |  | 1,387
Security review + performance hardening |  |  | 150
TOTAL — likely (~48 person-years) |  |  | ~10,550
TrustBank CBS · Migration Estimate (ROM ±40%) · Confidential
4

## Slide 5
3 · ESTIMATE RANGE
Where the number could land — and what drives it
Chart: 
| Optimistic | Likely | Pessimistic
Person-days | 7400 | 10550 | 14800
Optimistic ~7,400 pd · ~34 PY
Single database, reports rehosted, strong reuse, senior team
Likely ~10,550 pd · ~48 PY
Multi-DB, reports re-implemented, normal parallel-run
Pessimistic ~14,800 pd · ~67 PY
Multi-DB hardening, full report rebuild, deep parallel-run, scope growth
TrustBank CBS · Migration Estimate (ROM ±40%) · Confidential
5

## Slide 6
4 · INDICATIVE TIMELINE
Calendar = likely effort ÷ (team × 220 productive days/yr)
Chart: 
| Lean — 15 | Balanced — 20 | Accelerated — 25
Years | 3.2 | 2.4 | 1.9
~2.4 years
Balanced team of ~20 (recommended)
Add ramp-up and final UAT / cutover. A realistic planning window is ~2.5–3 years at ~20 people.
More people shortens the calendar but raises coordination cost; ~20 balances throughput and onboarding.
TrustBank CBS · Migration Estimate (ROM ±40%) · Confidential
6

## Slide 7
5 · PHASED ROADMAP
Strangler-fig — module-by-module, value delivered early
0
DONE
Phase 0
Foundation
Framework, reusable components, pilot screens, recipe
1
Phase 1
Discovery
Screen-by-screen inventory → firm estimate to ±15% (4–6 wks)
2
Phase 2
Masters & config
HO, Config, Lockers, HR — quick wins, prove velocity
3
Phase 3
Reporting platform
Report engine + reports (parallel workstream)
4
Phase 4
RetailBanking txns
The bulk: deposits → loans → clearing → cash → day-end
5
Phase 5
Remaining modules
Reconciliation, Inventory, Helpdesk, Customer360
6
Phase 6
Migrate & cut over
Data migration, parallel run, cutover, hardening, training
TrustBank CBS · Migration Estimate (ROM ±40%) · Confidential
7

## Slide 8
6 · KEY RISKS & COST DRIVERS
Where the estimate swings — manage these deliberately
1
Database target
Raw-SQL screens use SQL-Server dialect. A single-DB target removes ~120–150 pd and de-risks delivery; multi-provider (Oracle / PostgreSQL) adds hardening.
2
Reports: rehost vs rebuild
362 report screens + 892 definitions. The rehost-vs-rebuild decision swings the total by ~500–700 pd — the single biggest lever.
3
5,317 stored procedures
Deep embedded logic (interest, GL, day-end). The highest-risk, highest-value engines — need senior attention and rigorous parallel-run validation.
4
Banking correctness & compliance
Reconciliation and likely regulator sign-off mandate extended UAT and parallel running before each cutover.
TrustBank CBS · Migration Estimate (ROM ±40%) · Confidential
8

## Slide 9
RECOMMENDATION
Approve a 4–6 week discovery phase now
Discovery converts this ROM into a committed plan (±15%): it confirms per-screen complexity in the attached inventory, settles the reports and database-target decisions, and produces a firm Phase-1 budget — all before any large build commitment.
Low-risk start
Proven foundation + 6 delivered screens; the team begins migrating in Phase 2 immediately after discovery.
Early value
Strangler-fig cutover, module-by-module — no big-bang, benefits realised throughout.
Decision-ready
Editable workbook + full 1,458-screen inventory accompany this deck for due diligence.
Supporting pack: TrustBank-Migration-Estimate.docx (full report) · TrustBank-Migration-Estimate.xlsx (editable assumptions + 1,458-screen inventory)