## Read Me
TrustBank CBS → .NET 10 MVC — Migration Estimate
Prepared from an automated scan of the legacy source on 2026-06-17.
STATUS: Rough Order of Magnitude (ROM), +/-40%. Firm to +/-15% after a 4-6 week discovery (screen-by-screen inventory).
MEASURED SCOPE
- Functional (non-report) screens: 1,059
- Report screens: 399 (+ 892 .rdlc/.rpt report definitions)
- Total .aspx: 1,458 Reusable controls (.ascx): 19 Stored procedures: 5,317
METHOD
- Bottom-up: each functional screen classified Simple/Medium/Complex; reports separate; rate per bucket.
- Plus workstreams: reporting platform, core engine procedures, data migration/parallel-run,
remaining foundation + cross-provider hardening, QA/UAT, security/perf, PM/BA/DevOps/training.
- Calendar = total effort / (team size x productive days per year).
ALREADY BUILT (excluded from the build numbers — a real head start)
- Framework split, auth/session, menu + fail-closed access guard, multi-provider DAL,
reusable components (record/account/date pickers, search modal, notifications, RowToken),
a repeatable per-screen migration recipe, and 6 screens delivered as reference.
HOW TO USE THIS WORKBOOK
- 'Assumptions' — edit the blue cells (rates, %s, team size, scenario multipliers); everything recalculates.
- 'Effort Estimate' — the headline numbers, scenarios, and calendar.
- 'Module Inventory' — screens + effort by module (for phasing/sequencing).
- 'Screen List' — every screen with its suggested complexity (the discovery worksheet).
KEY RISKS / SWING ITEMS
- Cross-provider SQL (Oracle/Postgres): raw-SQL screens are SQL-Server dialect; single-DB target removes ~120-150 pd.
- Reports (362 screens + 892 definitions): 'rehost' vs 'rebuild' swings the total by ~500-700 pd.
- 5,317 procedures: deep embedded logic (interest/GL/day-end) — highest risk, needs heavy parallel-run validation.
- Banking correctness/compliance lengthens UAT and may require regulator sign-off.

## Assumptions
TrustBank CBS — Migration Estimate · Assumptions & Rates
All blue cells are editable inputs. Source counts from legacy code scan, 2026-06-17.
Effort rates (person-days per screen)
Simple | 1.5
Medium | 4
Complex | 10
Report | 2
Program parameters
QA + UAT (% of build effort) | 30%
PM / BA / DevOps / training / docs (% of build) | 20%
Security review + performance hardening (pd) | 150
Core engine procs to migrate (count) | 40 | interest, balance, day-end, GL posting, clearing
Core engine proc rate (pd each) | 15
Data migration + parallel-run tooling (pd) | 200
Foundation remaining + cross-provider hardening (pd) | 240 | framework is otherwise already built
Reporting platform setup (pd) | 40
Productive days per person-year | 220
Scenario multipliers
Optimistic × | 0.7 | SQL-Server-only, reports rehosted, strong reuse
Likely × | 1
Pessimistic × | 1.4 | multi-DB, full report rebuild, deep parallel-run
Calendar — team sizes (incl. QA/BA/PM)
Team A (people) | 15
Team B (people) | 20
Team C (people) | 25

## Effort Estimate
Migration Effort Estimate
Counts are from the legacy code scan (2026-06-17); rates/parameters live on the Assumptions sheet (editable).
Workstream | Count | Rate (pd) | Effort (pd) | Notes
Simple screens (masters, config, lookups, inquiries) | 121
Medium screens (search/list, multi-tab, dependent pickers) | 751
Complex screens (transactions, maker-checker, calc, batch) | 187
Reports (re-implement) | 399
Reporting platform setup
Core engine procedures
Data migration + parallel-run tooling
Foundation remaining + cross-provider hardening
Build subtotal
QA + UAT
PM / BA / DevOps / training / docs
Security + performance hardening
TOTAL — Likely (pd)
Scenario |  | Effort (pd) | Person-years
Optimistic
Likely
Pessimistic
Calendar (Likely) | People |  | Years
Team A
Team B
Team C

## Module Inventory
Legacy Screens by Module
Auto-classified from the code scan (2026-06-17); complexity is a suggestion to confirm in discovery. Effort uses Assumptions rates.
Module | Simple | Medium | Complex | Report | Total | Est. effort (pd)
RetailBanking | 0 | 535 | 113 | 19
Reports | 0 | 0 | 0 | 362
HO | 78 | 120 | 0 | 5
Reconciliation | 0 | 0 | 74 | 0
Inventory | 0 | 19 | 0 | 4
EmployeeDemand | 0 | 21 | 0 | 0
Helpdesk | 0 | 19 | 0 | 2
Hr | 2 | 19 | 0 | 0
Lockers | 15 | 0 | 0 | 0
(root) | 12 | 0 | 0 | 1
Config | 6 | 0 | 0 | 2
Authentication | 7 | 0 | 0 | 0
external_api | 0 | 5 | 0 | 0
fp | 0 | 5 | 0 | 0
UserControls | 0 | 4 | 0 | 0
StatutoryReports | 0 | 0 | 0 | 3
Customer360 | 0 | 2 | 0 | 0
ajax | 0 | 2 | 0 | 0
CcpcClearing | 0 | 0 | 0 | 1
ServiceBranch | 1 | 0 | 0 | 0
TOTAL

## Screen List
Full Screen Inventory (1 row per .aspx)
Source: legacy Trust.Bank.Publish code scan, 2026-06-17. 'Suggested complexity' is heuristic — confirm in the discovery phase.
Module | Sub-area | Screen | Relative path | Suggested complexity | Est. pd
Authentication |  | ChooseModule.aspx | Authentication/ChooseModule.aspx | Simple
Authentication |  | MainMenu.aspx | Authentication/MainMenu.aspx | Simple
Authentication |  | external_module_handler.aspx | Authentication/external_module_handler.aspx | Simple
Authentication | qrlogin | login_qr_verify.aspx | Authentication/qrlogin/login_qr_verify.aspx | Simple
Authentication | qrlogin | login_qr_verify_handler.aspx | Authentication/qrlogin/login_qr_verify_handler.aspx | Simple
Authentication | qrlogin | qrlogin_register.aspx | Authentication/qrlogin/qrlogin_register.aspx | Simple
Authentication | qrlogin | qrlogin_register_handler.aspx | Authentication/qrlogin/qrlogin_register_handler.aspx | Simple
CcpcClearing | CCPCClearingReports | ReportSettings.aspx | CcpcClearing/CCPCClearingReports/ReportSettings.aspx | Report
Config |  | AgriReportConfig.aspx | Config/AgriReportConfig.aspx | Report
Config |  | SGFReportConfig.aspx | Config/SGFReportConfig.aspx | Report
Config |  | SGFSubMemconnUsers.aspx | Config/SGFSubMemconnUsers.aspx | Simple
Config |  | UpdateBlockedUser.aspx | Config/UpdateBlockedUser.aspx | Simple
Config |  | b_MarqueeAlert.aspx | Config/b_MarqueeAlert.aspx | Simple
Config |  | connectedUsers.aspx | Config/connectedUsers.aspx | Simple
Config |  | g_CBSShortcutsPopup.aspx | Config/g_CBSShortcutsPopup.aspx | Simple
Config |  | protectapp.aspx | Config/protectapp.aspx | Simple
Customer360 |  | Customer360View_v1.aspx | Customer360/Customer360View_v1.aspx | Medium
Customer360 |  | JointDet360.aspx | Customer360/JointDet360.aspx | Medium
(root) |  | DashBoard.aspx | DashBoard.aspx | Simple
(root) |  | EmailCheck.aspx | EmailCheck.aspx | Simple
EmployeeDemand |  | EMPMemberResignTransaction.aspx | EmployeeDemand/EMPMemberResignTransaction.aspx | Medium
EmployeeDemand |  | EMPRecoveryMaintenance.aspx | EmployeeDemand/EMPRecoveryMaintenance.aspx | Medium
EmployeeDemand |  | EMPSuretyDemandDepositAccount.aspx | EmployeeDemand/EMPSuretyDemandDepositAccount.aspx | Medium
EmployeeDemand |  | EmpDemandPostMemberWise.aspx | EmployeeDemand/EmpDemandPostMemberWise.aspx | Medium
EmployeeDemand |  | EmpExceptionalDemandAmount.aspx | EmployeeDemand/EmpExceptionalDemandAmount.aspx | Medium
EmployeeDemand |  | EmpMemDemandPostConfig.aspx | EmployeeDemand/EmpMemDemandPostConfig.aspx | Medium
EmployeeDemand |  | EmpMemberSalaryTransaction.aspx | EmployeeDemand/EmpMemberSalaryTransaction.aspx | Medium
EmployeeDemand |  | EmpSocBranch.aspx | EmployeeDemand/EmpSocBranch.aspx | Medium
EmployeeDemand |  | EmpSocCompMaster.aspx | EmployeeDemand/EmpSocCompMaster.aspx | Medium
EmployeeDemand |  | EmpSocDemandConfiguration.aspx | EmployeeDemand/EmpSocDemandConfiguration.aspx | Medium
EmployeeDemand |  | EmpSocDivision.aspx | EmployeeDemand/EmpSocDivision.aspx | Medium
EmployeeDemand |  | EmpSocMember.aspx | EmployeeDemand/EmpSocMember.aspx | Medium
EmployeeDemand |  | EmpSocRegion.aspx | EmployeeDemand/EmpSocRegion.aspx | Medium
EmployeeDemand |  | EmpSocSateliteOffice.aspx | EmployeeDemand/EmpSocSateliteOffice.aspx | Medium
EmployeeDemand |  | EmployeeDemandDetails.aspx | EmployeeDemand/EmployeeDemandDetails.aspx | Medium
EmployeeDemand |  | EmployeeDemandGeneration.aspx | EmployeeDemand/EmployeeDemandGeneration.aspx | Medium
EmployeeDemand |  | EmployeeDemandImport.aspx | EmployeeDemand/EmployeeDemandImport.aspx | Medium
EmployeeDemand |  | EmployeeDemandModify.aspx | EmployeeDemand/EmployeeDemandModify.aspx | Medium
EmployeeDemand |  | EmployeeDepartment.aspx | EmployeeDemand/EmployeeDepartment.aspx | Medium
EmployeeDemand |  | EmployeeMemberTransfer.aspx | EmployeeDemand/EmployeeMemberTransfer.aspx | Medium
EmployeeDemand |  | UpdateEmployeeDemadAmount.aspx | EmployeeDemand/UpdateEmployeeDemadAmount.aspx | Medium
HO | Admin | A_User.aspx | HO/Admin/A_User.aspx | Medium
HO | Admin | Audit.aspx | HO/Admin/Audit.aspx | Medium
HO | Admin | AuditDetails.aspx | HO/Admin/AuditDetails.aspx | Medium
HO | Admin | AuditView.aspx | HO/Admin/AuditView.aspx | Medium
HO | Admin | ChangePassword.aspx | HO/Admin/ChangePassword.aspx | Medium
HO | Admin | ForgotPassword.aspx | HO/Admin/ForgotPassword.aspx | Medium
HO | Admin | PasswordPolicyConfig.aspx | HO/Admin/PasswordPolicyConfig.aspx | Medium
HO | Admin | Pop-up.aspx | HO/Admin/Pop-up.aspx | Medium
HO | Admin | a_AutoGenerateUser.aspx | HO/Admin/a_AutoGenerateUser.aspx | Medium
HO | Admin | a_BrLoginAccessTime.aspx | HO/Admin/a_BrLoginAccessTime.aspx | Medium
HO | Admin | a_CashierLimit.aspx | HO/Admin/a_CashierLimit.aspx | Medium
HO | Admin | a_ChangePassword.aspx | HO/Admin/a_ChangePassword.aspx | Medium
HO | Admin | a_Menus.aspx | HO/Admin/a_Menus.aspx | Medium
HO | Admin | a_Module.aspx | HO/Admin/a_Module.aspx | Medium
HO | Admin | a_RemoteHostAttempt.aspx | HO/Admin/a_RemoteHostAttempt.aspx | Medium
HO | Admin | a_ResponsibilityRights.aspx | HO/Admin/a_ResponsibilityRights.aspx | Medium
HO | Admin | a_ResponsibilityUser.aspx | HO/Admin/a_ResponsibilityUser.aspx | Medium
HO | Admin | a_RoleMaster.aspx | HO/Admin/a_RoleMaster.aspx | Medium
HO | Admin | a_RoleOnMenu.aspx | HO/Admin/a_RoleOnMenu.aspx | Medium
HO | Admin | a_UserCashierRights.aspx | HO/Admin/a_UserCashierRights.aspx | Medium
HO | Admin | a_UserInModule.aspx | HO/Admin/a_UserInModule.aspx | Medium
HO | Admin | a_UserLedgerRights.aspx | HO/Admin/a_UserLedgerRights.aspx | Medium
HO | Admin | a_UserOprRights.aspx | HO/Admin/a_UserOprRights.aspx | Medium
HO | Admin | a_UserRights.aspx | HO/Admin/a_UserRights.aspx | Medium
HO | Alerts | al_AlertConfig.aspx | HO/Alerts/al_AlertConfig.aspx | Medium
HO | Alerts | al_AlertsRights.aspx | HO/Alerts/al_AlertsRights.aspx | Medium
HO | Bank | Form121.aspx | HO/Bank/Form121.aspx | Medium
HO | Bank | MemberLoanSchemeMap.aspx | HO/Bank/MemberLoanSchemeMap.aspx | Medium
HO | Bank | b_ATMRequest.aspx | HO/Bank/b_ATMRequest.aspx | Simple
HO | Bank | b_BankList.aspx | HO/Bank/b_BankList.aspx | Simple
HO | Bank | b_BranchList.aspx | HO/Bank/b_BranchList.aspx | Simple
HO | Bank | b_MergeClient.aspx | HO/Bank/b_MergeClient.aspx | Simple
HO | Bank | b_NoteItemSeq.aspx | HO/Bank/b_NoteItemSeq.aspx | Simple
HO | Bank | b_TdsSavingSchemeMapping.aspx | HO/Bank/b_TdsSavingSchemeMapping.aspx | Simple
HO | Bank | clientTDSExcemtion.aspx | HO/Bank/clientTDSExcemtion.aspx | Medium
HO | Bank | clientTDSExcemtionDetails.aspx | HO/Bank/clientTDSExcemtionDetails.aspx | Medium
HO | Bank | g_AccountHead.aspx | HO/Bank/g_AccountHead.aspx | Simple
HO | Bank | g_BranchCategory.aspx | HO/Bank/g_BranchCategory.aspx | Simple
HO | Bank | g_BranchVariablesList.aspx | HO/Bank/g_BranchVariablesList.aspx | Simple
HO | Bank | g_City.aspx | HO/Bank/g_City.aspx | Simple
HO | Bank | g_Designation.aspx | HO/Bank/g_Designation.aspx | Simple
HO | Bank | g_District.aspx | HO/Bank/g_District.aspx | Simple
HO | Bank | g_FormAccountHeadMapping.aspx | HO/Bank/g_FormAccountHeadMapping.aspx | Simple
HO | Bank | g_IFSCCode.aspx | HO/Bank/g_IFSCCode.aspx | Simple
HO | Bank | g_InventoryCategory.aspx | HO/Bank/g_InventoryCategory.aspx | Simple
HO | Bank | g_LGA.aspx | HO/Bank/g_LGA.aspx | Simple
HO | Bank | g_MICRCity.aspx | HO/Bank/g_MICRCity.aspx | Simple
HO | Bank | g_MICRRegion.aspx | HO/Bank/g_MICRRegion.aspx | Simple
HO | Bank | g_Notes.aspx | HO/Bank/g_Notes.aspx | Simple
HO | Bank | g_OrgElement.aspx | HO/Bank/g_OrgElement.aspx | Simple
HO | Bank | g_OrgElementDepartment.aspx | HO/Bank/g_OrgElementDepartment.aspx | Simple
HO | Bank | g_PostOfficeCodes.aspx | HO/Bank/g_PostOfficeCodes.aspx | Simple
HO | Bank | g_Relation.aspx | HO/Bank/g_Relation.aspx | Simple
HO | Bank | g_ReportSettings.aspx | HO/Bank/g_ReportSettings.aspx | Report
HO | Bank | g_ServiceStatus.aspx | HO/Bank/g_ServiceStatus.aspx | Simple
HO | Bank | g_State.aspx | HO/Bank/g_State.aspx | Simple
HO | Bank | g_Step.aspx | HO/Bank/g_Step.aspx | Simple
HO | Bank | g_Taluka.aspx | HO/Bank/g_Taluka.aspx | Simple
HO | Bank | g_Title.aspx | HO/Bank/g_Title.aspx | Simple
HO |  | BankVariableConfig.aspx | HO/BankVariableConfig.aspx | Medium
HO |  | BranchVariableConfig.aspx | HO/BranchVariableConfig.aspx | Medium
HO |  | DeductMinBalHeadMap.aspx | HO/DeductMinBalHeadMap.aspx | Medium
HO | ECS | EcsMandateCancelPopup.aspx | HO/ECS/EcsMandateCancelPopup.aspx | Medium
HO | ECS | x_EcsMandateNew.aspx | HO/ECS/x_EcsMandateNew.aspx | Medium
HO |  | GSTTransactionDetail.aspx | HO/GSTTransactionDetail.aspx | Medium
HO |  | GlobalClientDocAttach.aspx | HO/GlobalClientDocAttach.aspx | Medium
HO |  | GlobalClientDocAttachPopup.aspx | HO/GlobalClientDocAttachPopup.aspx | Medium
HO | Hr | g_BankDirRelative.aspx | HO/Hr/g_BankDirRelative.aspx | Simple
HO | Hr | g_BankDirectors.aspx | HO/Hr/g_BankDirectors.aspx | Simple
HO | Hr | h_EmpDeputationExt.aspx | HO/Hr/h_EmpDeputationExt.aspx | Medium
HO | Hr | h_Employee.aspx | HO/Hr/h_Employee.aspx | Medium
HO | Hr | h_EmployeeDeputation.aspx | HO/Hr/h_EmployeeDeputation.aspx | Medium
HO | Hr | h_EmployeeRelease.aspx | HO/Hr/h_EmployeeRelease.aspx | Medium
HO |  | KYCClientPopup.aspx | HO/KYCClientPopup.aspx | Medium
HO |  | KYCClientPopup_V1.aspx | HO/KYCClientPopup_V1.aspx | Medium
HO |  | KYCUpdateInfo.aspx | HO/KYCUpdateInfo.aspx | Medium
HO |  | MbankGlobalAccLimit.aspx | HO/MbankGlobalAccLimit.aspx | Medium
HO |  | PigmyContraMaping.aspx | HO/PigmyContraMaping.aspx | Medium
HO | ProjectFormulation | C_LoanDocCollection.aspx | HO/ProjectFormulation/C_LoanDocCollection.aspx | Medium
HO | ProjectFormulation | P_CreditOfficer.aspx | HO/ProjectFormulation/P_CreditOfficer.aspx | Medium
HO | ProjectFormulation | c_LoanDocRelease.aspx | HO/ProjectFormulation/c_LoanDocRelease.aspx | Medium
HO | ProjectFormulation | p_AnnexPre.aspx | HO/ProjectFormulation/p_AnnexPre.aspx | Medium
HO | ProjectFormulation | p_Applicant.aspx | HO/ProjectFormulation/p_Applicant.aspx | Medium
HO | ProjectFormulation | p_CommitteeDirectors.aspx | HO/ProjectFormulation/p_CommitteeDirectors.aspx | Medium
HO | ProjectFormulation | p_CommitteeMaster.aspx | HO/ProjectFormulation/p_CommitteeMaster.aspx | Medium
HO | ProjectFormulation | p_CommitteeMasterMemberAP.aspx | HO/ProjectFormulation/p_CommitteeMasterMemberAP.aspx | Medium
HO | ProjectFormulation | p_CommitteeMasterMemberAR.aspx | HO/ProjectFormulation/p_CommitteeMasterMemberAR.aspx | Medium
HO | ProjectFormulation | p_Document.aspx | HO/ProjectFormulation/p_Document.aspx | Medium
HO | ProjectFormulation | p_LoanCaseCommitteeRemarks.aspx | HO/ProjectFormulation/p_LoanCaseCommitteeRemarks.aspx | Medium
HO | ProjectFormulation | p_LoanCase_v1.aspx | HO/ProjectFormulation/p_LoanCase_v1.aspx | Medium
HO | ProjectFormulation | p_SchemeDetails.aspx | HO/ProjectFormulation/p_SchemeDetails.aspx | Medium
HO | ProjectFormulation | p_SchemeDetailsV1.aspx | HO/ProjectFormulation/p_SchemeDetailsV1.aspx | Medium
HO | ProjectFormulation | p_SetCommitteeApprovalLimit.aspx | HO/ProjectFormulation/p_SetCommitteeApprovalLimit.aspx | Medium
HO | Retailbanking | Aadhaar_Vault.aspx | HO/Retailbanking/Aadhaar_Vault.aspx | Medium
HO | Retailbanking | b_CashRemitLimit.aspx | HO/Retailbanking/Cash/b_CashRemitLimit.aspx | Simple
HO | Retailbanking | x_CashRemittanceOrder.aspx | HO/Retailbanking/Cash/x_CashRemittanceOrder.aspx | Medium
HO | Retailbanking | DayendCOABalTrf.aspx | HO/Retailbanking/DayendCOABalTrf.aspx | Medium
HO | Retailbanking | DepositHeadValidateMap.aspx | HO/Retailbanking/DepositHeadValidateMap.aspx | Medium
HO | Retailbanking | FinancialRatioParamRang.aspx | HO/Retailbanking/FinancialRatioParamRang.aspx | Medium
HO | Retailbanking | KYCConfig.aspx | HO/Retailbanking/KYCConfig.aspx | Medium
HO | Retailbanking | LoanCCIntRule.aspx | HO/Retailbanking/LoanCCIntRule.aspx | Medium
HO | Retailbanking | b_SatutaryReportSubmission.aspx | HO/Retailbanking/RBIAdditionalStatements/b_SatutaryReportSubmission.aspx | Report
HO | Retailbanking | rp_BankSavingPercentage.aspx | HO/Retailbanking/RBIGroup/rp_BankSavingPercentage.aspx | Medium
HO | Retailbanking | rp_GroupBorrower.aspx | HO/Retailbanking/RBIGroup/rp_GroupBorrower.aspx | Medium
HO | Retailbanking | rp_MiscValues.aspx | HO/Retailbanking/RBIGroup/rp_MiscValues.aspx | Medium
HO | Retailbanking | RiskCatCalcDetailsV2.aspx | HO/Retailbanking/RiskCat/RiskCatCalcDetailsV2.aspx | Medium
HO | Retailbanking | RiskCatCalcV2.aspx | HO/Retailbanking/RiskCat/RiskCatCalcV2.aspx | Medium
HO | Retailbanking | RiskCatConfigPopUpV2.aspx | HO/Retailbanking/RiskCat/RiskCatConfigPopUpV2.aspx | Medium
HO | Retailbanking | RiskCatConfigV2.aspx | HO/Retailbanking/RiskCat/RiskCatConfigV2.aspx | Medium
HO | Retailbanking | x_ServiceTaxCharge.aspx | HO/Retailbanking/ServiceTaxCalculation/x_ServiceTaxCharge.aspx | Medium
HO | Retailbanking | Sms_AutoDayendMob.aspx | HO/Retailbanking/Sms_AutoDayendMob.aspx | Medium
HO | Retailbanking | a_SubMemberBankUser.aspx | HO/Retailbanking/a_SubMemberBankUser.aspx | Medium
HO | Retailbanking | a_UserTranLimit.aspx | HO/Retailbanking/a_UserTranLimit.aspx | Medium
HO | Retailbanking | a_UserTranLimitSource.aspx | HO/Retailbanking/a_UserTranLimitSource.aspx | Medium
HO | Retailbanking | b_CardTypeConfig.aspx | HO/Retailbanking/b_CardTypeConfig.aspx | Simple
HO | Retailbanking | b_ChargesConfig.aspx | HO/Retailbanking/b_ChargesConfig.aspx | Simple
HO | Retailbanking | b_ChargesConfigslab.aspx | HO/Retailbanking/b_ChargesConfigslab.aspx | Simple
HO | Retailbanking | b_ChargesMaster.aspx | HO/Retailbanking/b_ChargesMaster.aspx | Simple
HO | Retailbanking | b_DailyDepositInterestChart.aspx | HO/Retailbanking/b_DailyDepositInterestChart.aspx | Simple
HO | Retailbanking | b_FinancialYear.aspx | HO/Retailbanking/b_FinancialYear.aspx | Simple
HO | Retailbanking | b_GlInterestMapping.aspx | HO/Retailbanking/b_GlInterestMapping.aspx | Simple
HO | Retailbanking | b_Holiday.aspx | HO/Retailbanking/b_Holiday.aspx | Simple
HO | Retailbanking | b_HolidayChannel.aspx | HO/Retailbanking/b_HolidayChannel.aspx | Simple
HO | Retailbanking | b_PreDisbInfoItem.aspx | HO/Retailbanking/b_PreDisbInfoItem.aspx | Simple
HO | Retailbanking | b_PreDisbQstFormat.aspx | HO/Retailbanking/b_PreDisbQstFormat.aspx | Simple
HO | Retailbanking | b_ReportGLMap.aspx | HO/Retailbanking/b_ReportGLMap.aspx | Report
HO | Retailbanking | b_RiskCatAcTypeSlab.aspx | HO/Retailbanking/b_RiskCatAcTypeSlab.aspx | Simple
HO | Retailbanking | b_RiskCatByThresHold.aspx | HO/Retailbanking/b_RiskCatByThresHold.aspx | Simple
HO | Retailbanking | b_SavingInterestChart.aspx | HO/Retailbanking/b_SavingInterestChart.aspx | Simple
HO | Retailbanking | b_SkipAutoRecHead.aspx | HO/Retailbanking/b_SkipAutoRecHead.aspx | Simple
HO | Retailbanking | c_InsCompMaster.aspx | HO/Retailbanking/c_InsCompMaster.aspx | Medium
HO | Retailbanking | c_LNCCAgstDepAddlIRSlab.aspx | HO/Retailbanking/c_LNCCAgstDepAddlIRSlab.aspx | Medium
HO | Retailbanking | c_LNCCGroupExpLimit.aspx | HO/Retailbanking/c_LNCCGroupExpLimit.aspx | Medium
HO | Retailbanking | c_LNCCRebateSlab.aspx | HO/Retailbanking/c_LNCCRebateSlab.aspx | Medium
HO | Retailbanking | c_LnCcSchemeAccountHeadMapping.aspx | HO/Retailbanking/c_LnCcSchemeAccountHeadMapping.aspx | Medium
HO | Retailbanking | c_LnSancAuthority.aspx | HO/Retailbanking/c_LnSancAuthority.aspx | Medium
HO | Retailbanking | c_LoanPreClsrIntSlab.aspx | HO/Retailbanking/c_LoanPreClsrIntSlab.aspx | Medium
HO | Retailbanking | c_LoanScheme.aspx | HO/Retailbanking/c_LoanScheme.aspx | Medium
HO | Retailbanking | c_NRLMAccHead.aspx | HO/Retailbanking/c_NRLMAccHead.aspx | Medium
HO | Retailbanking | d_DepSchExclDEAF.aspx | HO/Retailbanking/d_DepSchExclDEAF.aspx | Medium
HO | Retailbanking | d_DepositScheme.aspx | HO/Retailbanking/d_DepositScheme.aspx | Medium
HO | Retailbanking | d_DepositSchemeAccountHeadMapping.aspx | HO/Retailbanking/d_DepositSchemeAccountHeadMapping.aspx | Medium
HO | Retailbanking | d_DepositSchemeBulk.aspx | HO/Retailbanking/d_DepositSchemeBulk.aspx | Medium
HO | Retailbanking | d_TDSCategoryWiseSetting.aspx | HO/Retailbanking/d_TDSCategoryWiseSetting.aspx | Medium
HO | Retailbanking | g_AllowMinimumBelowBalSourceMapping.aspx | HO/Retailbanking/g_AllowMinimumBelowBalSourceMapping.aspx | Simple
HO | Retailbanking | g_BSTemplateDesign.aspx | HO/Retailbanking/g_BSTemplateDesign.aspx | Simple
HO | Retailbanking | g_BSTemplateMaster.aspx | HO/Retailbanking/g_BSTemplateMaster.aspx | Simple
HO | Retailbanking | g_BSTemplateReport.aspx | HO/Retailbanking/g_BSTemplateReport.aspx | Report
HO | Retailbanking | g_CTRPostalMapping.aspx | HO/Retailbanking/g_CTRPostalMapping.aspx | Simple
HO | Retailbanking | g_ECSMasterData.aspx | HO/Retailbanking/g_ECSMasterData.aspx | Simple
HO | Retailbanking | g_PLR.aspx | HO/Retailbanking/g_PLR.aspx | Simple
HO | Retailbanking | g_RdPenaltyChartSlab.aspx | HO/Retailbanking/g_RdPenaltyChartSlab.aspx | Simple
HO | Retailbanking | g_ReconciliationTransaction.aspx | HO/Retailbanking/g_ReconciliationTransaction.aspx | Simple
HO | Retailbanking | g_State_Mapping.aspx | HO/Retailbanking/g_State_Mapping.aspx | Simple
HO | Retailbanking | g_auditCommitteeMembers.aspx | HO/Retailbanking/g_auditCommitteeMembers.aspx | Simple
HO | Retailbanking | x_ChargeWaiveOffBySplCat.aspx | HO/Retailbanking/x_ChargeWaiveOffBySplCat.aspx | Medium
HO | Retailbanking | x_ChequeBookCharges.aspx | HO/Retailbanking/x_ChequeBookCharges.aspx | Medium
HO | Retailbanking | x_IncomeSTheadMapping.aspx | HO/Retailbanking/x_IncomeSTheadMapping.aspx | Medium
HO | Retailbanking | x_MICREcsAccountMapping.aspx | HO/Retailbanking/x_MICREcsAccountMapping.aspx | Medium
HO | Retailbanking | x_OdTrDescMapping.aspx | HO/Retailbanking/x_OdTrDescMapping.aspx | Medium
HO | Retailbanking | x_TBPLBSFormats.aspx | HO/Retailbanking/x_TBPLBSFormats.aspx | Medium
HO | Retailbanking | x_TdsReversal.aspx | HO/Retailbanking/x_TdsReversal.aspx | Medium
HO |  | SMSAutoConfig.aspx | HO/SMSAutoConfig.aspx | Medium
HO |  | SignaturePreview.aspx | HO/SignaturePreview.aspx | Medium
HO |  | SmsConfig.aspx | HO/SmsConfig.aspx | Medium
HO |  | SubMemSubStatus.aspx | HO/SubMemSubStatus.aspx | Medium
HO |  | Sys_AccessControl.aspx | HO/Sys_AccessControl.aspx | Medium
HO |  | Sys_MetaData.aspx | HO/Sys_MetaData.aspx | Medium
HO |  | TerroristGroupdetails.aspx | HO/TerroristGroupdetails.aspx | Medium
HO |  | TerroristGroupdetails_V1.aspx | HO/TerroristGroupdetails_V1.aspx | Medium
HO |  | VerifyAadhar.aspx | HO/VerifyAadhar.aspx | Medium
HO |  | VerifyDocuments.aspx | HO/VerifyDocuments.aspx | Medium
HO |  | VerifyPancard.aspx | HO/VerifyPancard.aspx | Medium
HO |  | a_UserOtherBranchLogin.aspx | HO/a_UserOtherBranchLogin.aspx | Medium
HO |  | b_ATMAccCatSkip.aspx | HO/b_ATMAccCatSkip.aspx | Simple
HO |  | b_AccountEmailMap.aspx | HO/b_AccountEmailMap.aspx | Simple
HO |  | b_AutoScheduleLog.aspx | HO/b_AutoScheduleLog.aspx | Simple
HO |  | b_BlackListedAcc.aspx | HO/b_BlackListedAcc.aspx | Simple
HO |  | b_CTSSubMemberBank.aspx | HO/b_CTSSubMemberBank.aspx | Simple
HO |  | b_ClientCKYCRUpdateFlagPopup.aspx | HO/b_ClientCKYCRUpdateFlagPopup.aspx | Simple
HO |  | b_ClientCKYCR_V1.aspx | HO/b_ClientCKYCR_V1.aspx | Simple
HO |  | b_ClientCKYCR_V3.aspx | HO/b_ClientCKYCR_V3.aspx | Simple
HO |  | b_ClientSTRInfo.aspx | HO/b_ClientSTRInfo.aspx | Simple
HO |  | b_ClientV1.aspx | HO/b_ClientV1.aspx | Simple
HO |  | b_GstExcludeGL.aspx | HO/b_GstExcludeGL.aspx | Simple
HO |  | b_IMPSUPILimit.aspx | HO/b_IMPSUPILimit.aspx | Simple
HO |  | b_IbtLimitMapping.aspx | HO/b_IbtLimitMapping.aspx | Simple
HO |  | b_PigmyIntCommChart.aspx | HO/b_PigmyIntCommChart.aspx | Simple
HO |  | b_PigmyInterestSlab.aspx | HO/b_PigmyInterestSlab.aspx | Simple
HO |  | b_RiskCategory.aspx | HO/b_RiskCategory.aspx | Simple
HO |  | b_clientv2.aspx | HO/b_clientv2.aspx | Simple
HO | client_image_verify | client_doc_verify.aspx | HO/client_image_verify/client_doc_verify.aspx | Medium
HO | client_image_verify | client_doc_verify_handler.aspx | HO/client_image_verify/client_doc_verify_handler.aspx | Medium
HO |  | g_BlackListedDomain.aspx | HO/g_BlackListedDomain.aspx | Simple
HO |  | g_ClientGroup.aspx | HO/g_ClientGroup.aspx | Simple
HO |  | g_ClientIncomeDet.aspx | HO/g_ClientIncomeDet.aspx | Simple
HO |  | g_CustomerOnBoarding.aspx | HO/g_CustomerOnBoarding.aspx | Simple
HO |  | g_PigmyCommisionMapping.aspx | HO/g_PigmyCommisionMapping.aspx | Simple
HO |  | sys_AutoProcessConfig.aspx | HO/sys_AutoProcessConfig.aspx | Medium
HO |  | x_GetGstData.aspx | HO/x_GetGstData.aspx | Medium
HO |  | x_GstGLBalanceReport.aspx | HO/x_GstGLBalanceReport.aspx | Report
HO |  | x_IncomeGSTTrans.aspx | HO/x_IncomeGSTTrans.aspx | Medium
HO |  | x_IncomeGSTTransV1.aspx | HO/x_IncomeGSTTransV1.aspx | Medium
Helpdesk |  | HD_TranLimitslab.aspx | Helpdesk/HD_TranLimitslab.aspx | Medium
Helpdesk |  | HelpDeskPasswordPolicyConfig.aspx | Helpdesk/HelpDeskPasswordPolicyConfig.aspx | Medium
Helpdesk |  | MapHelpDeskAccounts.aspx | Helpdesk/MapHelpDeskAccounts.aspx | Medium
Helpdesk |  | MapHelpDeskAccountsV1.aspx | Helpdesk/MapHelpDeskAccountsV1.aspx | Medium
Helpdesk |  | UserTrailLog.aspx | Helpdesk/UserTrailLog.aspx | Medium
Helpdesk |  | hd_AllRequest.aspx | Helpdesk/hd_AllRequest.aspx | Medium
Helpdesk |  | hd_AllRequestInfo.aspx | Helpdesk/hd_AllRequestInfo.aspx | Medium
Helpdesk |  | hd_ApprovalAuthority.aspx | Helpdesk/hd_ApprovalAuthority.aspx | Medium
Helpdesk |  | hd_DashBoard.aspx | Helpdesk/hd_DashBoard.aspx | Medium
Helpdesk |  | hd_DashboardDetailPopup.aspx | Helpdesk/hd_DashboardDetailPopup.aspx | Medium
Helpdesk |  | hd_DepositSchemeMap.aspx | Helpdesk/hd_DepositSchemeMap.aspx | Medium
Helpdesk |  | hd_EmailConfig.aspx | Helpdesk/hd_EmailConfig.aspx | Medium
Helpdesk |  | hd_ExcludeIBHead.aspx | Helpdesk/hd_ExcludeIBHead.aspx | Medium
Helpdesk |  | hd_FeatureConfig.aspx | Helpdesk/hd_FeatureConfig.aspx | Medium
Helpdesk |  | hd_InternetBankingReport.aspx | Helpdesk/hd_InternetBankingReport.aspx | Report
Helpdesk |  | hd_LoginText.aspx | Helpdesk/hd_LoginText.aspx | Medium
Helpdesk |  | hd_ResendMail.aspx | Helpdesk/hd_ResendMail.aspx | Medium
Helpdesk |  | hd_ResendMailV1.aspx | Helpdesk/hd_ResendMailV1.aspx | Medium
Helpdesk |  | hd_ServiceStatus.aspx | Helpdesk/hd_ServiceStatus.aspx | Medium
Helpdesk |  | hd_TransactionReport.aspx | Helpdesk/hd_TransactionReport.aspx | Report
Helpdesk |  | hd_UserRelease.aspx | Helpdesk/hd_UserRelease.aspx | Medium
Hr |  | g_Bank.aspx | Hr/g_Bank.aspx | Simple
Hr |  | g_Language.aspx | Hr/g_Language.aspx | Simple
Hr |  | h_CourseHistory.aspx | Hr/h_CourseHistory.aspx | Medium
Hr |  | h_DiscipAction.aspx | Hr/h_DiscipAction.aspx | Medium
Hr |  | h_DiscipActionHistory.aspx | Hr/h_DiscipActionHistory.aspx | Medium
Hr |  | h_EmployeeDataCard.aspx | Hr/h_EmployeeDataCard.aspx | Medium
Hr |  | h_EmployeeDataCardDetails.aspx | Hr/h_EmployeeDataCardDetails.aspx | Medium
Hr |  | h_ExprHistory.aspx | Hr/h_ExprHistory.aspx | Medium
Hr |  | h_HonAward.aspx | Hr/h_HonAward.aspx | Medium
Hr |  | h_HonAwardHistory.aspx | Hr/h_HonAwardHistory.aspx | Medium
Hr |  | h_LeaveApplication.aspx | Hr/h_LeaveApplication.aspx | Medium
Hr |  | h_LeaveApproval.aspx | Hr/h_LeaveApproval.aspx | Medium
Hr |  | h_LeaveCancellation.aspx | Hr/h_LeaveCancellation.aspx | Medium
Hr |  | h_LeaveType.aspx | Hr/h_LeaveType.aspx | Medium
Hr |  | h_PromHistory.aspx | Hr/h_PromHistory.aspx | Medium
Hr |  | h_Promotion.aspx | Hr/h_Promotion.aspx | Medium
Hr |  | h_Qualification.aspx | Hr/h_Qualification.aspx | Medium
Hr |  | h_QualificationHistory.aspx | Hr/h_QualificationHistory.aspx | Medium
Hr |  | h_Transfer.aspx | Hr/h_Transfer.aspx | Medium
Hr |  | h_TransferHistory.aspx | Hr/h_TransferHistory.aspx | Medium
Hr |  | h_TransferV1.aspx | Hr/h_TransferV1.aspx | Medium
(root) |  | InitSession.aspx | InitSession.aspx | Simple
Inventory |  | i_AssetSale.aspx | Inventory/i_AssetSale.aspx | Medium
Inventory |  | i_AssetScrap.aspx | Inventory/i_AssetScrap.aspx | Medium
Inventory |  | i_BrInvRegister.aspx | Inventory/i_BrInvRegister.aspx | Medium
Inventory |  | i_BrInvRegisterPop.aspx | Inventory/i_BrInvRegisterPop.aspx | Medium
Inventory |  | i_ConsumableDisposal.aspx | Inventory/i_ConsumableDisposal.aspx | Medium
Inventory |  | i_Depriciation.aspx | Inventory/i_Depriciation.aspx | Medium
Inventory |  | i_DepriciationCalculation.aspx | Inventory/i_DepriciationCalculation.aspx | Medium
Inventory |  | i_EstimateReport.aspx | Inventory/i_EstimateReport.aspx | Report
Inventory |  | i_HSNCode.aspx | Inventory/i_HSNCode.aspx | Medium
Inventory |  | i_InvAllocation.aspx | Inventory/i_InvAllocation.aspx | Medium
Inventory |  | i_InvRequest.aspx | Inventory/i_InvRequest.aspx | Medium
Inventory |  | i_InventoryRegister.aspx | Inventory/i_InventoryRegister.aspx | Medium
Inventory |  | i_Item.aspx | Inventory/i_Item.aspx | Medium
Inventory |  | i_ItemDetailsPopup.aspx | Inventory/i_ItemDetailsPopup.aspx | Medium
Inventory |  | i_ItemPurchase.aspx | Inventory/i_ItemPurchase.aspx | Medium
Inventory |  | i_OPeningBalance.aspx | Inventory/i_OPeningBalance.aspx | Medium
Inventory |  | i_Supplier.aspx | Inventory/i_Supplier.aspx | Medium
Inventory |  | i_SupplierPayment.aspx | Inventory/i_SupplierPayment.aspx | Medium
Inventory |  | i_SupplierPaymentPopup.aspx | Inventory/i_SupplierPaymentPopup.aspx | Medium
Inventory |  | i_SupplierPaymentReport.aspx | Inventory/i_SupplierPaymentReport.aspx | Report
Inventory |  | i_UnitOfMeasurement.aspx | Inventory/i_UnitOfMeasurement.aspx | Medium
Inventory |  | i_masterReport.aspx | Inventory/i_masterReport.aspx | Report
Inventory |  | i_transactionReport.aspx | Inventory/i_transactionReport.aspx | Report
(root) |  | KeyHelp.aspx | KeyHelp.aspx | Simple
Lockers |  | K_LockerAccChange.aspx | Lockers/K_LockerAccChange.aspx | Simple
Lockers |  | K_LockerSignature.aspx | Lockers/K_LockerSignature.aspx | Simple
Lockers |  | k_LockerAccChangeHistoryPopup.aspx | Lockers/k_LockerAccChangeHistoryPopup.aspx | Simple
Lockers |  | k_LockerAdvRental.aspx | Lockers/k_LockerAdvRental.aspx | Simple
Lockers |  | k_LockerBreak.aspx | Lockers/k_LockerBreak.aspx | Simple
Lockers |  | k_LockerIssue.aspx | Lockers/k_LockerIssue.aspx | Simple
Lockers |  | k_LockerMake.aspx | Lockers/k_LockerMake.aspx | Simple
Lockers |  | k_LockerMaster.aspx | Lockers/k_LockerMaster.aspx | Simple
Lockers |  | k_LockerOpratorSignPopup.aspx | Lockers/k_LockerOpratorSignPopup.aspx | Simple
Lockers |  | k_LockerReturn.aspx | Lockers/k_LockerReturn.aspx | Simple
Lockers |  | k_LockerType.aspx | Lockers/k_LockerType.aspx | Simple
Lockers |  | k_LockerVerifyPassPopup.aspx | Lockers/k_LockerVerifyPassPopup.aspx | Simple
Lockers |  | k_LockerVisiting.aspx | Lockers/k_LockerVisiting.aspx | Simple
Lockers |  | k_LockerWaitlist.aspx | Lockers/k_LockerWaitlist.aspx | Simple
Lockers |  | k_NomineeOperatorHisPopup.aspx | Lockers/k_NomineeOperatorHisPopup.aspx | Simple
(root) |  | Login.aspx | Login.aspx | Simple
Reconciliation |  | Re_OutPutType.aspx | Reconciliation/Re_OutPutType.aspx | Complex
Reconciliation |  | re_AccountMapping.aspx | Reconciliation/re_AccountMapping.aspx | Complex
Reconciliation |  | re_BankAccountInformation.aspx | Reconciliation/re_BankAccountInformation.aspx | Complex
Reconciliation |  | re_DeleteOLedgerImportData.aspx | Reconciliation/re_DeleteOLedgerImportData.aspx | Complex
Reconciliation |  | re_DeleteTLedgerImportData.aspx | Reconciliation/re_DeleteTLedgerImportData.aspx | Complex
Reconciliation |  | re_FWATMRecConfig.aspx | Reconciliation/re_FWATMRecConfig.aspx | Complex
Reconciliation |  | re_FWATMTerminalFormatMapping.aspx | Reconciliation/re_FWATMTerminalFormatMapping.aspx | Complex
Reconciliation |  | re_FWAccountTransactionMapping.aspx | Reconciliation/re_FWAccountTransactionMapping.aspx | Complex
Reconciliation |  | re_FWAutoReconRRNWise.aspx | Reconciliation/re_FWAutoReconRRNWise.aspx | Complex
Reconciliation |  | re_FWAutoReconRRNWisePopUp.aspx | Reconciliation/re_FWAutoReconRRNWisePopUp.aspx | Complex
Reconciliation |  | re_FWAutoReconciliation.aspx | Reconciliation/re_FWAutoReconciliation.aspx | Complex
Reconciliation |  | re_FWConfigDataFilter.aspx | Reconciliation/re_FWConfigDataFilter.aspx | Complex
Reconciliation |  | re_FWConfigTextFile.aspx | Reconciliation/re_FWConfigTextFile.aspx | Complex
Reconciliation |  | re_FWDSRFileItemList.aspx | Reconciliation/re_FWDSRFileItemList.aspx | Complex
Reconciliation |  | re_FWDeleteDSRUnpassedData.aspx | Reconciliation/re_FWDeleteDSRUnpassedData.aspx | Complex
Reconciliation |  | re_FWDeleteImportDSRFileData.aspx | Reconciliation/re_FWDeleteImportDSRFileData.aspx | Complex
Reconciliation |  | re_FWDeleteImportData.aspx | Reconciliation/re_FWDeleteImportData.aspx | Complex
Reconciliation |  | re_FWDeleteImportSettlementData.aspx | Reconciliation/re_FWDeleteImportSettlementData.aspx | Complex
Reconciliation |  | re_FWDisputeCaseCofiguration.aspx | Reconciliation/re_FWDisputeCaseCofiguration.aspx | Complex
Reconciliation |  | re_FWDisputeCaseConfiguration.aspx | Reconciliation/re_FWDisputeCaseConfiguration.aspx | Complex
Reconciliation |  | re_FWDisputeTransaction.aspx | Reconciliation/re_FWDisputeTransaction.aspx | Complex
Reconciliation |  | re_FWFileMapping.aspx | Reconciliation/re_FWFileMapping.aspx | Complex
Reconciliation |  | re_FWForceReconciliation.aspx | Reconciliation/re_FWForceReconciliation.aspx | Complex
Reconciliation |  | re_FWFormWiseEntity.aspx | Reconciliation/re_FWFormWiseEntity.aspx | Complex
Reconciliation |  | re_FWImportDSRExcelFile.aspx | Reconciliation/re_FWImportDSRExcelFile.aspx | Complex
Reconciliation |  | re_FWImportEJPoolTextFile.aspx | Reconciliation/re_FWImportEJPoolTextFile.aspx | Complex
Reconciliation |  | re_FWImportEJPoolTextFileMulti.aspx | Reconciliation/re_FWImportEJPoolTextFileMulti.aspx | Complex
Reconciliation |  | re_FWImportEntityFile.aspx | Reconciliation/re_FWImportEntityFile.aspx | Complex
Reconciliation |  | re_FWImportExcelFile.aspx | Reconciliation/re_FWImportExcelFile.aspx | Complex
Reconciliation |  | re_FWImportExcelFileMulti.aspx | Reconciliation/re_FWImportExcelFileMulti.aspx | Complex
Reconciliation |  | re_FWImportPOSExcelFile.aspx | Reconciliation/re_FWImportPOSExcelFile.aspx | Complex
Reconciliation |  | re_FWImportSwitchExcelFile.aspx | Reconciliation/re_FWImportSwitchExcelFile.aspx | Complex
Reconciliation |  | re_FWImportSwitchExcelFileMulti.aspx | Reconciliation/re_FWImportSwitchExcelFileMulti.aspx | Complex
Reconciliation |  | re_FWImportTextFile.aspx | Reconciliation/re_FWImportTextFile.aspx | Complex
Reconciliation |  | re_FWImportTextFileMulti.aspx | Reconciliation/re_FWImportTextFileMulti.aspx | Complex
Reconciliation |  | re_FWImportTrustLedger.aspx | Reconciliation/re_FWImportTrustLedger.aspx | Complex
Reconciliation |  | re_FWLoadFile.aspx | Reconciliation/re_FWLoadFile.aspx | Complex
Reconciliation |  | re_FWManualReconciliation.aspx | Reconciliation/re_FWManualReconciliation.aspx | Complex
Reconciliation |  | re_FWManualReconciliationRollBack.aspx | Reconciliation/re_FWManualReconciliationRollBack.aspx | Complex
Reconciliation |  | re_FWSettlementAccount.aspx | Reconciliation/re_FWSettlementAccount.aspx | Complex
Reconciliation |  | re_FWSettlementAccountLedger.aspx | Reconciliation/re_FWSettlementAccountLedger.aspx | Complex
Reconciliation |  | re_FWSettlementImportMulti.aspx | Reconciliation/re_FWSettlementImportMulti.aspx | Complex
Reconciliation |  | re_FWSettlementItemList.aspx | Reconciliation/re_FWSettlementItemList.aspx | Complex
Reconciliation |  | re_FWSettlementItemListConfiguration.aspx | Reconciliation/re_FWSettlementItemListConfiguration.aspx | Complex
Reconciliation |  | re_FWSettlementItemListMonthly.aspx | Reconciliation/re_FWSettlementItemListMonthly.aspx | Complex
Reconciliation |  | re_FWTransaction.aspx | Reconciliation/re_FWTransaction.aspx | Complex
Reconciliation |  | re_FWTransactionCons.aspx | Reconciliation/re_FWTransactionCons.aspx | Complex
Reconciliation |  | re_FWTransactionDSR.aspx | Reconciliation/re_FWTransactionDSR.aspx | Complex
Reconciliation |  | re_FWTransactionDSRPassing.aspx | Reconciliation/re_FWTransactionDSRPassing.aspx | Complex
Reconciliation |  | re_FWTransactionDaily.aspx | Reconciliation/re_FWTransactionDaily.aspx | Complex
Reconciliation |  | re_FWTransactionDailyPassing.aspx | Reconciliation/re_FWTransactionDailyPassing.aspx | Complex
Reconciliation |  | re_FWTransactionMonthly.aspx | Reconciliation/re_FWTransactionMonthly.aspx | Complex
Reconciliation |  | re_FWTransactionMonthlyPassing.aspx | Reconciliation/re_FWTransactionMonthlyPassing.aspx | Complex
Reconciliation |  | re_FWTransactionMonthlyPopUp.aspx | Reconciliation/re_FWTransactionMonthlyPopUp.aspx | Complex
Reconciliation |  | re_FWTransactionPassing.aspx | Reconciliation/re_FWTransactionPassing.aspx | Complex
Reconciliation |  | re_FWTransactionPopUp.aspx | Reconciliation/re_FWTransactionPopUp.aspx | Complex
Reconciliation |  | re_LedgerEntry.aspx | Reconciliation/re_LedgerEntry.aspx | Complex
Reconciliation |  | re_LedgerFileDataImport.aspx | Reconciliation/re_LedgerFileDataImport.aspx | Complex
Reconciliation |  | re_MultiReconciliation.aspx | Reconciliation/re_MultiReconciliation.aspx | Complex
Reconciliation |  | re_MultiReconciliationV1.aspx | Reconciliation/re_MultiReconciliationV1.aspx | Complex
Reconciliation |  | re_OurLedgerImport.aspx | Reconciliation/re_OurLedgerImport.aspx | Complex
Reconciliation |  | re_Owner.aspx | Reconciliation/re_Owner.aspx | Complex
Reconciliation |  | re_ProcessTypeMatchCriteria.aspx | Reconciliation/re_ProcessTypeMatchCriteria.aspx | Complex
Reconciliation |  | re_Reconciliation.aspx | Reconciliation/re_Reconciliation.aspx | Complex
Reconciliation |  | re_ReconciliationRollBack.aspx | Reconciliation/re_ReconciliationRollBack.aspx | Complex
Reconciliation |  | re_ReconciliationRollBackBatch.aspx | Reconciliation/re_ReconciliationRollBackBatch.aspx | Complex
Reconciliation |  | re_ReconciliationRollBackV1.aspx | Reconciliation/re_ReconciliationRollBackV1.aspx | Complex
Reconciliation |  | re_ReconciliationRollBackV2.aspx | Reconciliation/re_ReconciliationRollBackV2.aspx | Complex
Reconciliation |  | re_SelfReconciliation.aspx | Reconciliation/re_SelfReconciliation.aspx | Complex
Reconciliation |  | re_SelfReconciliationV1.aspx | Reconciliation/re_SelfReconciliationV1.aspx | Complex
Reconciliation |  | re_SingleReconciliationRollback.aspx | Reconciliation/re_SingleReconciliationRollback.aspx | Complex
Reconciliation |  | re_TLedgerImportDataEdit.aspx | Reconciliation/re_TLedgerImportDataEdit.aspx | Complex
Reconciliation |  | re_TextFileConfiguration.aspx | Reconciliation/re_TextFileConfiguration.aspx | Complex
Reconciliation |  | re_TheirLedgerExcelDataTransfer.aspx | Reconciliation/re_TheirLedgerExcelDataTransfer.aspx | Complex
Reports | Admin | AdminDatalogreport.aspx | Reports/Admin/AdminDatalogreport.aspx | Report
Reports | Admin | AdminReport.aspx | Reports/Admin/AdminReport.aspx | Report
Reports | Admin | BankBranchLogReport.aspx | Reports/Admin/BankBranchLogReport.aspx | Report
Reports | Admin | DepositSchemeLogReport.aspx | Reports/Admin/DepositSchemeLogReport.aspx | Report
Reports | Admin | EmpTransferLogReport.aspx | Reports/Admin/EmpTransferLogReport.aspx | Report
Reports | Admin | GLIntMappLogReport.aspx | Reports/Admin/GLIntMappLogReport.aspx | Report
Reports | Admin | LoanSchemeLogReport.aspx | Reports/Admin/LoanSchemeLogReport.aspx | Report
Reports | Admin | UserActivityLogReport.aspx | Reports/Admin/UserActivityLogReport.aspx | Report
Reports | Admin | UserLoginTypeLogReport.aspx | Reports/Admin/UserLoginTypeLogReport.aspx | Report
Reports | Admin | UserRightsLogReport.aspx | Reports/Admin/UserRightsLogReport.aspx | Report
Reports | AgriLoans | AgriDisbReport.aspx | Reports/AgriLoans/AgriDisbReport.aspx | Report
Reports | AgriLoans | InterestSubventionReport.aspx | Reports/AgriLoans/InterestSubventionReport.aspx | Report
Reports | AgriLoans | PACSTransferReport.aspx | Reports/AgriLoans/PACSTransferReport.aspx | Report
Reports | AgriLoans | PACSTransferReportDet.aspx | Reports/AgriLoans/PACSTransferReportDet.aspx | Report
Reports | CKYC | CKYCReports.aspx | Reports/CKYC/CKYCReports.aspx | Report
Reports | CKYC | kyc_ReportSettings.aspx | Reports/CKYC/kyc_ReportSettings.aspx | Report
Reports |  | CrystalViewer.aspx | Reports/CrystalViewer.aspx | Report
Reports |  | CustomizeAdHoc.aspx | Reports/CustomizeAdHoc.aspx | Report
Reports |  | CustomizeAdHocConfig.aspx | Reports/CustomizeAdHocConfig.aspx | Report
Reports | EmployeeDemand | DemandRecoveryStatementReport.aspx | Reports/EmployeeDemand/DemandRecoveryStatementReport.aspx | Report
Reports | EmployeeDemand | DemandSentReceivedStatement.aspx | Reports/EmployeeDemand/DemandSentReceivedStatement.aspx | Report
Reports | EmployeeDemand | EmployeeDemandDiffAmount.aspx | Reports/EmployeeDemand/EmployeeDemandDiffAmount.aspx | Report
Reports | EmployeeDemand | EmployeeDemandLetter.aspx | Reports/EmployeeDemand/EmployeeDemandLetter.aspx | Report
Reports | EmployeeDemand | EmployeeDemandShortTermReport.aspx | Reports/EmployeeDemand/EmployeeDemandShortTermReport.aspx | Report
Reports | EmployeeDemand | EmployeeDemandTallyReport.aspx | Reports/EmployeeDemand/EmployeeDemandTallyReport.aspx | Report
Reports | EmployeeDemand | EmplyeeDemandGeneration_NICBEL.aspx | Reports/EmployeeDemand/EmplyeeDemandGeneration_NICBEL.aspx | Report
Reports | EmployeeDemand | EmplyeeDemandModify.aspx | Reports/EmployeeDemand/EmplyeeDemandModify.aspx | Report
Reports | EmployeeDemand | LoanEligibilityCertificate.aspx | Reports/EmployeeDemand/LoanEligibilityCertificate.aspx | Report
Reports | EmployeeDemand | MemberDetailsReport.aspx | Reports/EmployeeDemand/MemberDetailsReport.aspx | Report
Reports | EmployeeDemand | MemberTransferDetails.aspx | Reports/EmployeeDemand/MemberTransferDetails.aspx | Report
Reports | EmployeeDemand | MemberWiseConsReport.aspx | Reports/EmployeeDemand/MemberWiseConsReport.aspx | Report
Reports | EmployeeDemand | MemberWiseDemandModification.aspx | Reports/EmployeeDemand/MemberWiseDemandModification.aspx | Report
Reports | EmployeeDemand | MonthlyRecoveryReport.aspx | Reports/EmployeeDemand/MonthlyRecoveryReport.aspx | Report
Reports | EmployeeDemand | RecoveryScheduleReport.aspx | Reports/EmployeeDemand/RecoveryScheduleReport.aspx | Report
Reports | Hr | ReportOptions.aspx | Reports/Hr/ReportOptions.aspx | Report
Reports | Inventory | LockerReport.aspx | Reports/Inventory/Lockers/LockerReport.aspx | Report
Reports | Lockers | BrWiseUnutilisedLockerReport.aspx | Reports/Lockers/BrWiseUnutilisedLockerReport.aspx | Report
Reports | Lockers | LockerReport.aspx | Reports/Lockers/LockerReport.aspx | Report
Reports | Lockers | LockerWaitListReport.aspx | Reports/Lockers/LockerWaitListReport.aspx | Report
Reports | Lockers | k_LockerExpiryLetter.aspx | Reports/Lockers/k_LockerExpiryLetter.aspx | Report
Reports |  | NABARDAdHoc.aspx | Reports/NABARDAdHoc.aspx | Report
Reports | PACS | x_PACSReportOptions.aspx | Reports/PACS/x_PACSReportOptions.aspx | Report
Reports | ProjectFormulation | p_LoanApplicationReport.aspx | Reports/ProjectFormulation/p_LoanApplicationReport.aspx | Report
Reports | RBI Report | AnnualInfReportForm61A.aspx | Reports/RBI Report/AnnualInfReportForm61A.aspx | Report
Reports | RBI Report | AnnualInfReportForm61A_SFT016.aspx | Reports/RBI Report/AnnualInfReportForm61A_SFT016.aspx | Report
Reports | RBI Report | AnnualInfReportForm61A_export.aspx | Reports/RBI Report/AnnualInfReportForm61A_export.aspx | Report
Reports | RBI Report | CIBIL.aspx | Reports/RBI Report/CIBIL.aspx | Report
Reports | RBI Report | CIBIL_AgencySegment.aspx | Reports/RBI Report/CIBIL_AgencySegment.aspx | Report
Reports | RBI Report | CIBIL_BusinessIndustryTypeMapping.aspx | Reports/RBI Report/CIBIL_BusinessIndustryTypeMapping.aspx | Report
Reports | RBI Report | CIBIL_CommercialRelationshipMapping.aspx | Reports/RBI Report/CIBIL_CommercialRelationshipMapping.aspx | Report
Reports | RBI Report | CIBIL_ConstitutionTypeMapping.aspx | Reports/RBI Report/CIBIL_ConstitutionTypeMapping.aspx | Report
Reports | RBI Report | CIBIL_JLGMicroFin.aspx | Reports/RBI Report/CIBIL_JLGMicroFin.aspx | Report
Reports | RBI Report | CIBIL_ProductConfiguration.aspx | Reports/RBI Report/CIBIL_ProductConfiguration.aspx | Report
Reports | RBI Report | ConsolidateReport.aspx | Reports/RBI Report/ConsolidateReport.aspx | Report
Reports | RBI Report | RBIDataFilterView.aspx | Reports/RBI Report/RBIDataFilterView.aspx | Report
Reports | RBI Report | RBIDataFilterView_export.aspx | Reports/RBI Report/RBIDataFilterView_export.aspx | Report
Reports | RBI Report | RBIReport.aspx | Reports/RBI Report/RBIReport.aspx | Report
Reports | RBI Report | RBIReportConfiguration.aspx | Reports/RBI Report/RBIReportConfiguration.aspx | Report
Reports | RBI Report | rp_CRRSLRpercentage.aspx | Reports/RBI Report/rp_CRRSLRpercentage.aspx | Report
Reports | RBI Report | rp_DatabankDiagnose.aspx | Reports/RBI Report/rp_DatabankDiagnose.aspx | Report
Reports | RBI Report | rp_DiagnosedDifferencePopUp.aspx | Reports/RBI Report/rp_DiagnosedDifferencePopUp.aspx | Report
Reports | RBI Report | rp_GroupBorrowerReport.aspx | Reports/RBI Report/rp_GroupBorrowerReport.aspx | Report
Reports | RBI Report | rp_IndustryMapping.aspx | Reports/RBI Report/rp_IndustryMapping.aspx | Report
Reports | RBI Report | rp_RBIConfiguration.aspx | Reports/RBI Report/rp_RBIConfiguration.aspx | Report
Reports | RBI Report | rp_RBIConfigurationLog.aspx | Reports/RBI Report/rp_RBIConfigurationLog.aspx | Report
Reports | RBI Report | rp_RBIOSSIntegrityData.aspx | Reports/RBI Report/rp_RBIOSSIntegrityData.aspx | Report
Reports | RBI Report | rp_RBIOSSIntegrityDataExecutor.aspx | Reports/RBI Report/rp_RBIOSSIntegrityDataExecutor.aspx | Report
Reports | RBI Report | rp_RBIUnbindedCOA.aspx | Reports/RBI Report/rp_RBIUnbindedCOA.aspx | Report
Reports | RBI Report | rp_TargetMaster.aspx | Reports/RBI Report/rp_TargetMaster.aspx | Report
Reports | RBI Report | rp_VariousRatios.aspx | Reports/RBI Report/rp_VariousRatios.aspx | Report
Reports |  | RBIIndentAdHoc_export.aspx | Reports/RBIIndentAdHoc_export.aspx | Report
Reports | Reconciliation | AgeAnalysisInterBankRec.aspx | Reports/Reconciliation/AgeAnalysisInterBankRec.aspx | Report
Reports | Reconciliation | OutPutTypeReport.aspx | Reports/Reconciliation/OutPutTypeReport.aspx | Report
Reports | Reconciliation | re_FWAllUnPassTransactionReport.aspx | Reports/Reconciliation/re_FWAllUnPassTransactionReport.aspx | Report
Reports | Reconciliation | re_FWAtmReports.aspx | Reports/Reconciliation/re_FWAtmReports.aspx | Report
Reports | Reconciliation | re_FWCbsMtiMapping.aspx | Reports/Reconciliation/re_FWCbsMtiMapping.aspx | Report
Reports | Reconciliation | re_FWDSRFileReport.aspx | Reports/Reconciliation/re_FWDSRFileReport.aspx | Report
Reports | Reconciliation | re_FWDSRSummaryReport.aspx | Reports/Reconciliation/re_FWDSRSummaryReport.aspx | Report
Reports | Reconciliation | re_FWDailyReconciliationReport.aspx | Reports/Reconciliation/re_FWDailyReconciliationReport.aspx | Report
Reports | Reconciliation | re_FWDisputeTransactionReport.aspx | Reports/Reconciliation/re_FWDisputeTransactionReport.aspx | Report
Reports | Reconciliation | re_FWFilterReconData.aspx | Reports/Reconciliation/re_FWFilterReconData.aspx | Report
Reports | Reconciliation | re_FWForceReconcileTransactionReport.aspx | Reports/Reconciliation/re_FWForceReconcileTransactionReport.aspx | Report
Reports | Reconciliation | re_FWGetSettlementCommissionReport.aspx | Reports/Reconciliation/re_FWGetSettlementCommissionReport.aspx | Report
Reports | Reconciliation | re_FWImportSettlementReport.aspx | Reports/Reconciliation/re_FWImportSettlementReport.aspx | Report
Reports | Reconciliation | re_FWLedgerReport.aspx | Reports/Reconciliation/re_FWLedgerReport.aspx | Report
Reports | Reconciliation | re_FWNPCI_CBS_EntryStatusReport.aspx | Reports/Reconciliation/re_FWNPCI_CBS_EntryStatusReport.aspx | Report
Reports | Reconciliation | re_FWNPCI_CBS_StatusReport.aspx | Reports/Reconciliation/re_FWNPCI_CBS_StatusReport.aspx | Report
Reports | Reconciliation | re_FWReconSummaryReport.aspx | Reports/Reconciliation/re_FWReconSummaryReport.aspx | Report
Reports | Reconciliation | re_FWReconcileTransactionPopUp.aspx | Reports/Reconciliation/re_FWReconcileTransactionPopUp.aspx | Report
Reports | Reconciliation | re_FWReconcileTransactionReport.aspx | Reports/Reconciliation/re_FWReconcileTransactionReport.aspx | Report
Reports | Reconciliation | re_FWReconciliationDashboard.aspx | Reports/Reconciliation/re_FWReconciliationDashboard.aspx | Report
Reports | Reconciliation | re_FWReconciliationDashboardPopUp.aspx | Reports/Reconciliation/re_FWReconciliationDashboardPopUp.aspx | Report
Reports | Reconciliation | re_FWSettlementAccountLedgerReport.aspx | Reports/Reconciliation/re_FWSettlementAccountLedgerReport.aspx | Report
Reports | Reconciliation | re_FWSettlementReport.aspx | Reports/Reconciliation/re_FWSettlementReport.aspx | Report
Reports | Reconciliation | re_FWSettlementSummaryComparisionReport.aspx | Reports/Reconciliation/re_FWSettlementSummaryComparisionReport.aspx | Report
Reports | Reconciliation | re_FWSettlementSummaryReport.aspx | Reports/Reconciliation/re_FWSettlementSummaryReport.aspx | Report
Reports | Reconciliation | re_FWTransactionDSRPassUnpassReport.aspx | Reports/Reconciliation/re_FWTransactionDSRPassUnpassReport.aspx | Report
Reports | Reconciliation | re_FWTransactionPassReport.aspx | Reports/Reconciliation/re_FWTransactionPassReport.aspx | Report
Reports | Reconciliation | re_FWTransactionPassReportDaily.aspx | Reports/Reconciliation/re_FWTransactionPassReportDaily.aspx | Report
Reports | Reconciliation | re_FWTransactionPassReportMonthly.aspx | Reports/Reconciliation/re_FWTransactionPassReportMonthly.aspx | Report
Reports | Reconciliation | re_FWTrustBankSettelmentSummaryReport.aspx | Reports/Reconciliation/re_FWTrustBankSettelmentSummaryReport.aspx | Report
Reports | Reconciliation | re_FWUnReconcileTransactionReport.aspx | Reports/Reconciliation/re_FWUnReconcileTransactionReport.aspx | Report
Reports | Reconciliation | re_FwDayBatchReport.aspx | Reports/Reconciliation/re_FwDayBatchReport.aspx | Report
Reports | Reconciliation | re_LedgerReport.aspx | Reports/Reconciliation/re_LedgerReport.aspx | Report
Reports | Reconciliation | re_OutPutTypeSummaryReport.aspx | Reports/Reconciliation/re_OutPutTypeSummaryReport.aspx | Report
Reports | Reconciliation | re_ProcessTypeReport.aspx | Reports/Reconciliation/re_ProcessTypeReport.aspx | Report
Reports | Reconciliation | re_UnRecInterBankAdjConsReport.aspx | Reports/Reconciliation/re_UnRecInterBankAdjConsReport.aspx | Report
Reports | Reconciliation | re_UnRecInterBrAdjEntrReport.aspx | Reports/Reconciliation/re_UnRecInterBrAdjEntrReport.aspx | Report
Reports |  | ReportSelector.aspx | Reports/ReportSelector.aspx | Report
Reports |  | ReportsSourceHandler.aspx | Reports/ReportsSourceHandler.aspx | Report
Reports |  | ReportsTargetHandler.aspx | Reports/ReportsTargetHandler.aspx | Report
Reports | RetailBanking | 206ABCCAReport.aspx | Reports/RetailBanking/206ABCCAReport.aspx | Report
Reports | RetailBanking | ABCDReport.aspx | Reports/RetailBanking/ABCDReport.aspx | Report
Reports | RetailBanking | AMLAccountWiseCriteria.aspx | Reports/RetailBanking/AML/AMLAccountWiseCriteria.aspx | Report
Reports | RetailBanking | AMLClientWhiteListAdd.aspx | Reports/RetailBanking/AML/AMLClientWhiteListAdd.aspx | Report
Reports | RetailBanking | AMLClientWhiteListPass.aspx | Reports/RetailBanking/AML/AMLClientWhiteListPass.aspx | Report
Reports | RetailBanking | AMLDataScheduler.aspx | Reports/RetailBanking/AML/AMLDataScheduler.aspx | Report
Reports | RetailBanking | AMLGetRiskCategoryAcc.aspx | Reports/RetailBanking/AML/AMLGetRiskCategoryAcc.aspx | Report
Reports | RetailBanking | AMLKYCDetailsPopUp.aspx | Reports/RetailBanking/AML/AMLKYCDetailsPopUp.aspx | Report
Reports | RetailBanking | AMLMonthWiseAlerts.aspx | Reports/RetailBanking/AML/AMLMonthWiseAlerts.aspx | Report
Reports | RetailBanking | AMLSettings.aspx | Reports/RetailBanking/AML/AMLSettings.aspx | Report
Reports | RetailBanking | AMLTransactionWhiteListAdd.aspx | Reports/RetailBanking/AML/AMLTransactionWhiteListAdd.aspx | Report
Reports | RetailBanking | AMLTransactionWhiteListPass.aspx | Reports/RetailBanking/AML/AMLTransactionWhiteListPass.aspx | Report
Reports | RetailBanking | AMLWhiteListRecordRemove.aspx | Reports/RetailBanking/AML/AMLWhiteListRecordRemove.aspx | Report
Reports | RetailBanking | AMLWhiteListTransactionRemove.aspx | Reports/RetailBanking/AML/AMLWhiteListTransactionRemove.aspx | Report
Reports | RetailBanking | AML_AlertReport.aspx | Reports/RetailBanking/AML/AML_AlertReport.aspx | Report
Reports | RetailBanking | AML_STRWhiteListedReport.aspx | Reports/RetailBanking/AML/AML_STRWhiteListedReport.aspx | Report
Reports | RetailBanking | AML_SuspiciousMarkingReport.aspx | Reports/RetailBanking/AML/AML_SuspiciousMarkingReport.aspx | Report
Reports | RetailBanking | AML_WhiteListMarking.aspx | Reports/RetailBanking/AML/AML_WhiteListMarking.aspx | Report
Reports | RetailBanking | AmlVerificationMarkedByUserPopUp.aspx | Reports/RetailBanking/AML/AmlVerificationMarkedByUserPopUp.aspx | Report
Reports | RetailBanking | AmlVerificationMarkedByUserPopUpWhiteList.aspx | Reports/RetailBanking/AML/AmlVerificationMarkedByUserPopUpWhiteList.aspx | Report
Reports | RetailBanking | AmlWorkingDateReports.aspx | Reports/RetailBanking/AML/AmlWorkingDateReports.aspx | Report
Reports | RetailBanking | AmlWorkingDateReportsV1.aspx | Reports/RetailBanking/AML/AmlWorkingDateReportsV1.aspx | Report
Reports | RetailBanking | AmlWorkingDateReportsV1PopUp.aspx | Reports/RetailBanking/AML/AmlWorkingDateReportsV1PopUp.aspx | Report
Reports | RetailBanking | AmlWorkingDateReportsV1_WithExcel.aspx | Reports/RetailBanking/AML/AmlWorkingDateReportsV1_WithExcel.aspx | Report
Reports | RetailBanking | AmlWorkingDateReportsV2.aspx | Reports/RetailBanking/AML/AmlWorkingDateReportsV2.aspx | Report
Reports | RetailBanking | AmlWorkingDateReportsV2PopUp.aspx | Reports/RetailBanking/AML/AmlWorkingDateReportsV2PopUp.aspx | Report
Reports | RetailBanking | AmlWorkingDateReportsV3.aspx | Reports/RetailBanking/AML/AmlWorkingDateReportsV3.aspx | Report
Reports | RetailBanking | AmlWorkingDateReportsWhiteListV1PopUp.aspx | Reports/RetailBanking/AML/AmlWorkingDateReportsWhiteListV1PopUp.aspx | Report
Reports | RetailBanking | AntiMoneyLaundering.aspx | Reports/RetailBanking/AML/AntiMoneyLaundering.aspx | Report
Reports | RetailBanking | BranchAMLMarking.aspx | Reports/RetailBanking/AML/BranchAMLMarking.aspx | Report
Reports | RetailBanking | PrincipalOfficerAMLMarking.aspx | Reports/RetailBanking/AML/PrincipalOfficerAMLMarking.aspx | Report
Reports | RetailBanking | STRAlertReport.aspx | Reports/RetailBanking/AML/STRAlertReport.aspx | Report
Reports | RetailBanking | b_ATMCardBlockReport.aspx | Reports/RetailBanking/ATM/b_ATMCardBlockReport.aspx | Report
Reports | RetailBanking | ATMAccMismatchTran.aspx | Reports/RetailBanking/ATMAccMismatchTran.aspx | Report
Reports | RetailBanking | ATMDisputeReport.aspx | Reports/RetailBanking/ATMDisputeReport.aspx | Report
Reports | RetailBanking | ATMReports.aspx | Reports/RetailBanking/ATMReports.aspx | Report
Reports | RetailBanking | AccOpenCloseRegister.aspx | Reports/RetailBanking/AccOpenCloseRegister.aspx | Report
Reports | RetailBanking | AccountLedger.aspx | Reports/RetailBanking/Account/AccountLedger.aspx | Report
Reports | RetailBanking | AccountReportSetting.aspx | Reports/RetailBanking/Account/AccountReportSetting.aspx | Report
Reports | RetailBanking | AllAccStmtbyClient.aspx | Reports/RetailBanking/Account/AllAccStmtbyClient.aspx | Report
Reports | RetailBanking | AllAcc_Export.aspx | Reports/RetailBanking/Account/AllAcc_Export.aspx | Report
Reports | RetailBanking | CCOprAccount.aspx | Reports/RetailBanking/Account/CCOprAccount.aspx | Report
Reports | RetailBanking | DeafAccountDetailReport.aspx | Reports/RetailBanking/Account/DeafAccountDetailReport.aspx | Report
Reports | RetailBanking | AccountBalancingReport.aspx | Reports/RetailBanking/AccountBalancingReport.aspx | Report
Reports | RetailBanking | AccountClosingCertificate.aspx | Reports/RetailBanking/AccountClosingCertificate.aspx | Report
Reports | RetailBanking | AccountOpenCloseSummary.aspx | Reports/RetailBanking/AccountOpenCloseSummary.aspx | Report
Reports | RetailBanking | AccountStatement.aspx | Reports/RetailBanking/AccountStatement.aspx | Report
Reports | RetailBanking | AllUnpassedReports.aspx | Reports/RetailBanking/AllUnpassedReports.aspx | Report
Reports | RetailBanking | AuditReportSetting.aspx | Reports/RetailBanking/Audit/AuditReportSetting.aspx | Report
Reports | RetailBanking | BGReportOptions.aspx | Reports/RetailBanking/BG/BGReportOptions.aspx | Report
Reports | RetailBanking | BachatGatReports.aspx | Reports/RetailBanking/BachatGat/BachatGatReports.aspx | Report
Reports | RetailBanking | BalanceCertificate.aspx | Reports/RetailBanking/BalanceCertificate.aspx | Report
Reports | RetailBanking | BalancingReportSetting.aspx | Reports/RetailBanking/Balancing/BalancingReportSetting.aspx | Report
Reports | RetailBanking | BookBalanceCertificateReport.aspx | Reports/RetailBanking/BookBalanceCertificateReport.aspx | Report
Reports | RetailBanking | BranchReconciliationSummary.aspx | Reports/RetailBanking/BranchReconciliationSummary.aspx | Report
Reports | RetailBanking | CTR.aspx | Reports/RetailBanking/CTR.aspx | Report
Reports | RetailBanking | CTR_BranchDetails.aspx | Reports/RetailBanking/CTR/CTR_BranchDetails.aspx | Report
Reports | RetailBanking | CTR_ControlFile.aspx | Reports/RetailBanking/CTR/CTR_ControlFile.aspx | Report
Reports | RetailBanking | CTR_ReportFile.aspx | Reports/RetailBanking/CTR/CTR_ReportFile.aspx | Report
Reports | RetailBanking | CTR_V1.aspx | Reports/RetailBanking/CTR_V1.aspx | Report
Reports | RetailBanking | CashLimitDetails.aspx | Reports/RetailBanking/CashLimitDetails.aspx | Report
Reports | RetailBanking | CashPosition.aspx | Reports/RetailBanking/CashPosition.aspx | Report
Reports | RetailBanking | CashRemittanceReport.aspx | Reports/RetailBanking/CashRemittanceReport.aspx | Report
Reports | RetailBanking | CashTDSReport.aspx | Reports/RetailBanking/CashTDSReport.aspx | Report
Reports | RetailBanking | ChargesRecReport.aspx | Reports/RetailBanking/ChargesRecReport.aspx | Report
Reports | RetailBanking | ChargesRecRpt.aspx | Reports/RetailBanking/ChargesRecRpt.aspx | Report
Reports | RetailBanking | ChargesReport.aspx | Reports/RetailBanking/ChargesReport.aspx | Report
Reports | RetailBanking | CentralizeOWClearingReport.aspx | Reports/RetailBanking/Clearing/CentralizeOWClearingReport.aspx | Report
Reports | RetailBanking | ClearingReportSettings.aspx | Reports/RetailBanking/Clearing/ClearingReportSettings.aspx | Report
Reports | RetailBanking | CtsOWContclrEntShift.aspx | Reports/RetailBanking/Clearing/CtsOWContclrEntShift.aspx | Report
Reports | RetailBanking | HoldChequeDet.aspx | Reports/RetailBanking/Clearing/HoldChequeDet.aspx | Report
Reports | RetailBanking | InwOutSubMemClearingReports.aspx | Reports/RetailBanking/Clearing/InwOutSubMemClearingReports.aspx | Report
Reports | RetailBanking | InwardA6Report.aspx | Reports/RetailBanking/Clearing/InwardA6Report.aspx | Report
Reports | RetailBanking | InwardReturnSummaryReport.aspx | Reports/RetailBanking/Clearing/InwardReturnSummaryReport.aspx | Report
Reports | RetailBanking | IwChequeShiftReport.aspx | Reports/RetailBanking/Clearing/IwChequeShiftReport.aspx | Report
Reports | RetailBanking | IwOwClrSummary.aspx | Reports/RetailBanking/Clearing/IwOwClrSummary.aspx | Report
Reports | RetailBanking | IwProbableReturnReport.aspx | Reports/RetailBanking/Clearing/IwProbableReturnReport.aspx | Report
Reports | RetailBanking | OwRecPayDetail.aspx | Reports/RetailBanking/Clearing/OwRecPayDetail.aspx | Report
Reports | RetailBanking | OwRegisterReport.aspx | Reports/RetailBanking/Clearing/OwRegisterReport.aspx | Report
Reports | RetailBanking | OwReturnBnSummary.aspx | Reports/RetailBanking/Clearing/OwReturnBnSummary.aspx | Report
Reports | RetailBanking | PositivePaydetailsReport.aspx | Reports/RetailBanking/Clearing/PositivePaydetailsReport.aspx | Report
Reports | RetailBanking | SubMemberPosition.aspx | Reports/RetailBanking/Clearing/SubMemberPosition.aspx | Report
Reports | RetailBanking | ClientAccountInfo.aspx | Reports/RetailBanking/ClientAccountInfo.aspx | Report
Reports | RetailBanking | ClientModLog.aspx | Reports/RetailBanking/ClientModLog.aspx | Report
Reports | RetailBanking | ClientWithTerrorist.aspx | Reports/RetailBanking/ClientWithTerrorist.aspx | Report
Reports | RetailBanking | ComparativeChartReport.aspx | Reports/RetailBanking/ComparativeChartReport.aspx | Report
Reports | RetailBanking | CounterfeitNotesReceipt.aspx | Reports/RetailBanking/CounterfeitNotesReceipt.aspx | Report
Reports | RetailBanking | CustAccInfoPrint.aspx | Reports/RetailBanking/CustAccInfoPrint.aspx | Report
Reports | RetailBanking | DCBS.aspx | Reports/RetailBanking/DCBS/DCBS.aspx | Report
Reports | RetailBanking | DCC_RBI_Report.aspx | Reports/RetailBanking/DCC_RBI_Report/DCC_RBI_Report.aspx | Report
Reports | RetailBanking | DDPOReportSettings.aspx | Reports/RetailBanking/DDPOReports/DDPOReportSettings.aspx | Report
Reports | RetailBanking | DailyReportSetting.aspx | Reports/RetailBanking/Daily Report/DailyReportSetting.aspx | Report
Reports | RetailBanking | DataComareReports.aspx | Reports/RetailBanking/DataComareReports.aspx | Report
Reports | RetailBanking | DayWiseInterestProduct.aspx | Reports/RetailBanking/DayWiseInterestProduct.aspx | Report
Reports | RetailBanking | DeathClaimReport.aspx | Reports/RetailBanking/DeathClaim/DeathClaimReport.aspx | Report
Reports | RetailBanking | DemandCollection.aspx | Reports/RetailBanking/DemandCollection.aspx | Report
Reports | RetailBanking | DemandCollectionBalanceDCCYearly.aspx | Reports/RetailBanking/DemandCollectionBalanceDCCYearly.aspx | Report
Reports | RetailBanking | DemandGenerationReport.aspx | Reports/RetailBanking/DemandGenerationReport.aspx | Report
Reports | RetailBanking | DepAdvInterestLog.aspx | Reports/RetailBanking/DepAdvInterestLog.aspx | Report
Reports | RetailBanking | DepAdvQtrAnnex.aspx | Reports/RetailBanking/DepAdvQtrAnnex.aspx | Report
Reports | RetailBanking | DepositRatePeriodWise.aspx | Reports/RetailBanking/DepositRatePeriodWise.aspx | Report
Reports | RetailBanking | DocumentExpiryReport.aspx | Reports/RetailBanking/DocumentExpiryReport.aspx | Report
Reports | RetailBanking | ECSBankToSubMemShift.aspx | Reports/RetailBanking/ECS/ECSBankToSubMemShift.aspx | Report
Reports | RetailBanking | ECSReportSettings.aspx | Reports/RetailBanking/ECS/ECSReportSettings.aspx | Report
Reports | RetailBanking | ExceptionalReport.aspx | Reports/RetailBanking/ExceptionalReport.aspx | Report
Reports | RetailBanking | ExcessCashReport.aspx | Reports/RetailBanking/ExcessCashReport.aspx | Report
Reports | RetailBanking | FDMatNotPaidsummary.aspx | Reports/RetailBanking/FDMatNotPaidsummary.aspx | Report
Reports | RetailBanking | FDRReportSettings.aspx | Reports/RetailBanking/FDR/FDRReportSettings.aspx | Report
Reports | RetailBanking | FutureFDRenewal.aspx | Reports/RetailBanking/FDR/FutureFDRenewal.aspx | Report
Reports | RetailBanking | FDRenewalReport.aspx | Reports/RetailBanking/FDRenewalReport.aspx | Report
Reports | RetailBanking | Form60.aspx | Reports/RetailBanking/Form60.aspx | Report
Reports | RetailBanking | FutureIntNotice.aspx | Reports/RetailBanking/FutureIntNotice.aspx | Report
Reports | RetailBanking | FutureIntNoticeV1.aspx | Reports/RetailBanking/FutureIntNoticeV1.aspx | Report
Reports | RetailBanking | GDCCStatements.aspx | Reports/RetailBanking/GDCCStatements.aspx | Report
Reports | RetailBanking | GeneralLedgerConsolidation.aspx | Reports/RetailBanking/GeneralLedgerConsolidation.aspx | Report
Reports | RetailBanking | GeneralLedgerReport.aspx | Reports/RetailBanking/GeneralLedgerReport.aspx | Report
Reports | RetailBanking | GoldSecurityReport.aspx | Reports/RetailBanking/GoldSecurityReport.aspx | Report
Reports | RetailBanking | HOBalance.aspx | Reports/RetailBanking/HOBalance.aspx | Report
Reports | RetailBanking | BankDirRelReport.aspx | Reports/RetailBanking/HeadOffice/BankDirRelReport.aspx | Report
Reports | RetailBanking | ChannelTranReport.aspx | Reports/RetailBanking/HeadOffice/ChannelTranReport.aspx | Report
Reports | RetailBanking | HeadofficeReportSetting.aspx | Reports/RetailBanking/HeadOffice/HeadofficeReportSetting.aspx | Report
Reports | RetailBanking | LoanSchemeChangeLog.aspx | Reports/RetailBanking/HeadOffice/LoanSchemeChangeLog.aspx | Report
Reports | RetailBanking | TBBSPLReportSetting.aspx | Reports/RetailBanking/HeadOffice/TBBSPLReportSetting.aspx | Report
Reports | RetailBanking | IBTMisTranReport.aspx | Reports/RetailBanking/IBTMisTranReport.aspx | Report
Reports | RetailBanking | IncomeGSTReport.aspx | Reports/RetailBanking/IncomeGSTReport.aspx | Report
Reports | RetailBanking | IntPaidPayRecdRecReport.aspx | Reports/RetailBanking/IntPaidPayRecdRecReport.aspx | Report
Reports | RetailBanking | IntSubventionReport.aspx | Reports/RetailBanking/IntSubventionReport.aspx | Report
Reports | RetailBanking | InterestReportSetting.aspx | Reports/RetailBanking/InterestActivities/InterestReportSetting.aspx | Report
Reports | RetailBanking | InterestCalcLogReport.aspx | Reports/RetailBanking/InterestCalcLogReport.aspx | Report
Reports | RetailBanking | InvPurSaleReport.aspx | Reports/RetailBanking/Investment/InvPurSaleReport.aspx | Report
Reports | RetailBanking | InvestmentNewReportSettings.aspx | Reports/RetailBanking/Investment/InvestmentNewReportSettings.aspx | Report
Reports | RetailBanking | InvestmentReportSettings.aspx | Reports/RetailBanking/Investment/InvestmentReportSettings.aspx | Report
Reports | RetailBanking | JLGReports.aspx | Reports/RetailBanking/JLGReports.aspx | Report
Reports | RetailBanking | JLGReports_export.aspx | Reports/RetailBanking/JLGReports_export.aspx | Report
Reports | RetailBanking | KeyFactStatement.aspx | Reports/RetailBanking/KeyFactStatement.aspx | Report
Reports | RetailBanking | KycComplianceReport.aspx | Reports/RetailBanking/KycComplianceReport.aspx | Report
Reports | RetailBanking | LNAccExceedingLTVRatioReport.aspx | Reports/RetailBanking/LNAccExceedingLTVRatioReport.aspx | Report
Reports | RetailBanking | LNCCRecoveryReport.aspx | Reports/RetailBanking/LNCCRecoveryReport.aspx | Report
Reports | RetailBanking | LNPostDatedChqReport.aspx | Reports/RetailBanking/LNPostDatedChqReport.aspx | Report
Reports | RetailBanking | LedgerViewLogReport.aspx | Reports/RetailBanking/LedgerViewLogReport.aspx | Report
Reports | RetailBanking | LegalReportSetting.aspx | Reports/RetailBanking/Legal/LegalReportSetting.aspx | Report
Reports | RetailBanking | LegalActionTakenReport.aspx | Reports/RetailBanking/LegalActionTakenReport.aspx | Report
Reports | RetailBanking | LiabilityVerification.aspx | Reports/RetailBanking/LiabilityVerification.aspx | Report
Reports | RetailBanking | LoanAccChargeNotedReport.aspx | Reports/RetailBanking/LoanAccChargeNotedReport.aspx | Report
Reports | RetailBanking | LoanAccountStatement.aspx | Reports/RetailBanking/LoanAccountStatement.aspx | Report
Reports | RetailBanking | LoanBalancingReport.aspx | Reports/RetailBanking/LoanBalancingReport.aspx | Report
Reports | RetailBanking | LoanDepositIntSlab.aspx | Reports/RetailBanking/LoanDepositIntSlab.aspx | Report
Reports | RetailBanking | LoanInsuranceReport.aspx | Reports/RetailBanking/LoanInsuranceReport.aspx | Report
Reports | RetailBanking | LoanInterestCalculationDataChecking.aspx | Reports/RetailBanking/LoanInterestCalculationDataChecking.aspx | Report
Reports | RetailBanking | LoanOstODReport.aspx | Reports/RetailBanking/LoanOstODReport.aspx | Report
Reports | RetailBanking | LoanReport.aspx | Reports/RetailBanking/LoanReport.aspx | Report
Reports | RetailBanking | ecs_MandateAccountStatus.aspx | Reports/RetailBanking/MMS/ecs_MandateAccountStatus.aspx | Report
Reports | RetailBanking | MMSInwOutTranReport.aspx | Reports/RetailBanking/MMSInwOutTranReport.aspx | Report
Reports | RetailBanking | MasterReportSetting.aspx | Reports/RetailBanking/Master/MasterReportSetting.aspx | Report
Reports | RetailBanking | MinorTurnMajorLetter.aspx | Reports/RetailBanking/MinorTurnMajorLetter.aspx | Report
Reports | RetailBanking | MstClsAdv.aspx | Reports/RetailBanking/MstClsAdv.aspx | Report
Reports | RetailBanking | NBFC.aspx | Reports/RetailBanking/NBFC_V1/NBFC.aspx | Report
Reports | RetailBanking | NODCStatement.aspx | Reports/RetailBanking/NODCStatement.aspx | Report
Reports | RetailBanking | ClassificationNPA.aspx | Reports/RetailBanking/NPA/ClassificationNPA.aspx | Report
Reports | RetailBanking | NPAMovement.aspx | Reports/RetailBanking/NPA/NPAMovement.aspx | Report
Reports | RetailBanking | NPAReportSettings.aspx | Reports/RetailBanking/NPA/NPAReportSettings.aspx | Report
Reports | RetailBanking | NPASummarybyCOA.aspx | Reports/RetailBanking/NPA/NPASummarybyCOA.aspx | Report
Reports | RetailBanking | NpaModificationReport.aspx | Reports/RetailBanking/NPA/NpaModificationReport.aspx | Report
Reports | RetailBanking | ODAgainstNPA.aspx | Reports/RetailBanking/NPA/ODAgainstNPA.aspx | Report
Reports | RetailBanking | ProbableNPA.aspx | Reports/RetailBanking/NPA/ProbableNPA.aspx | Report
Reports | RetailBanking | NRLMReports.aspx | Reports/RetailBanking/NRLMReports.aspx | Report
Reports | RetailBanking | NetWorthReport.aspx | Reports/RetailBanking/NetWorthReport.aspx | Report
Reports | RetailBanking | AllInterestCertificate.aspx | Reports/RetailBanking/New RetailBanking Report/AllInterestCertificate.aspx | Report
Reports | RetailBanking | BlackListTerroristSearch.aspx | Reports/RetailBanking/New RetailBanking Report/BlackListTerroristSearch.aspx | Report
Reports | RetailBanking | DepositInsuranceV1.aspx | Reports/RetailBanking/New RetailBanking Report/DepositInsuranceV1.aspx | Report
Reports | RetailBanking | LoanDisbRecReport.aspx | Reports/RetailBanking/New RetailBanking Report/LoanDisbRecReport.aspx | Report
Reports | RetailBanking | LockerReport.aspx | Reports/RetailBanking/New RetailBanking Report/LockerReport.aspx | Report
Reports | RetailBanking | OverdueLetterLogReport.aspx | Reports/RetailBanking/New RetailBanking Report/OverdueLetterLogReport.aspx | Report
Reports | RetailBanking | ReportSettings.aspx | Reports/RetailBanking/New RetailBanking Report/ReportSettings.aspx | Report
Reports | RetailBanking | StockStatementDueDate_New.aspx | Reports/RetailBanking/New RetailBanking Report/StockStatementDueDate_New.aspx | Report
Reports | RetailBanking | UserdefinedClientKYCLetter.aspx | Reports/RetailBanking/New RetailBanking Report/UserdefinedClientKYCLetter.aspx | Report
Reports | RetailBanking | UserdefinedWelcomeLetter.aspx | Reports/RetailBanking/New RetailBanking Report/UserdefinedWelcomeLetter.aspx | Report
Reports | RetailBanking | x_UserdefinedOverdueLetter.aspx | Reports/RetailBanking/New RetailBanking Report/x_UserdefinedOverdueLetter.aspx | Report
Reports | RetailBanking | NonOperationAccPostReport.aspx | Reports/RetailBanking/NonOperationAccPostReport.aspx | Report
Reports | RetailBanking | ODCustRptRtdDate.aspx | Reports/RetailBanking/ODCustRptRtdDate.aspx | Report
Reports | RetailBanking | OSCShowReport.aspx | Reports/RetailBanking/OSCStatements/OSCShowReport.aspx | Report
Reports | RetailBanking | OSCShowReportV1.aspx | Reports/RetailBanking/OSCStatementsV1/OSCShowReportV1.aspx | Report
Reports | RetailBanking | st_ViewReports.aspx | Reports/RetailBanking/OSSStatement/st_ViewReports.aspx | Report
Reports | RetailBanking | PacsAccStatement.aspx | Reports/RetailBanking/PacsAccStatement.aspx | Report
Reports | RetailBanking | PigmyAccReceipt.aspx | Reports/RetailBanking/PigmyAccReceipt.aspx | Report
Reports | RetailBanking | PoliceCaseReports.aspx | Reports/RetailBanking/PoliceCaseReports.aspx | Report
Reports | RetailBanking | PolicyReport.aspx | Reports/RetailBanking/PolicyReport.aspx | Report
Reports | RetailBanking | PreDisbInfoReport.aspx | Reports/RetailBanking/PreDisbInfoReport.aspx | Report
Reports | RetailBanking | PrioritySectorAndWeakerSectionReport.aspx | Reports/RetailBanking/PrioritySectorAndWeakerSectionReport.aspx | Report
Reports | RetailBanking | ProjectionReport.aspx | Reports/RetailBanking/ProjectionReport.aspx | Report
Reports | RetailBanking | AvailableReportDates.aspx | Reports/RetailBanking/RBI Group/AvailableReportDates.aspx | Report
Reports | RetailBanking | RBIFormVIII.aspx | Reports/RetailBanking/RBI Group/RBIFormVIII.aspx | Report
Reports | RetailBanking | RBIAS19Slab.aspx | Reports/RetailBanking/RBI Group/RBIStatement1to10/RBIAuditASReports/RBIAS19Slab.aspx | Report
Reports | RetailBanking | RBIAdditionalStatementReoprts.aspx | Reports/RetailBanking/RBI Group/RBIStatement1to10/RBIAuditASReports/RBIAdditionalStatementReoprts.aspx | Report
Reports | RetailBanking | rp_GroupValuesTreeView.aspx | Reports/RetailBanking/RBI Group/rp_GroupValuesTreeView.aspx | Report
Reports | RetailBanking | RDInstReport.aspx | Reports/RetailBanking/RDInstReport.aspx | Report
Reports | RetailBanking | RTGSBatchReport.aspx | Reports/RetailBanking/RTGS/RTGSBatchReport.aspx | Report
Reports | RetailBanking | RTGSOwUnAuthorized.aspx | Reports/RetailBanking/RTGS/RTGSOwUnAuthorized.aspx | Report
Reports | RetailBanking | RTGSReportoptions.aspx | Reports/RetailBanking/RTGS/RTGSReportoptions.aspx | Report
Reports | RetailBanking | x_RTGSRetMarkReport.aspx | Reports/RetailBanking/RTGS/x_RTGSRetMarkReport.aspx | Report
Reports | RetailBanking | x_RTGSTranSummary.aspx | Reports/RetailBanking/RTGS/x_RTGSTranSummary.aspx | Report
Reports | RetailBanking | ReducingLimitReport.aspx | Reports/RetailBanking/ReducingLimitReport.aspx | Report
Reports | RetailBanking | ReportOptions.aspx | Reports/RetailBanking/ReportOptions.aspx | Report
Reports | RetailBanking | ReportOptionsDailyBook.aspx | Reports/RetailBanking/ReportOptionsDailyBook.aspx | Report
Reports | RetailBanking | ReportSubDetails.aspx | Reports/RetailBanking/ReportSubDetails.aspx | Report
Reports | RetailBanking | Reports.aspx | Reports/RetailBanking/Reports.aspx | Report
Reports | RetailBanking | RiskCategoryReport.aspx | Reports/RetailBanking/RiskCategoryReport.aspx | Report
Reports | RetailBanking | SGFReport.aspx | Reports/RetailBanking/SGFReport.aspx | Report
Reports | RetailBanking | SLBCReports.aspx | Reports/RetailBanking/SLBCReports.aspx | Report
Reports | RetailBanking | SMAMarking.aspx | Reports/RetailBanking/SMAMarking.aspx | Report
Reports | RetailBanking | SMSLogReport.aspx | Reports/RetailBanking/SMSLogReport.aspx | Report
Reports | RetailBanking | STRKYCDetailsPopUp.aspx | Reports/RetailBanking/STR/STRKYCDetailsPopUp.aspx | Report
Reports | RetailBanking | STR.aspx | Reports/RetailBanking/STR/Version2/STR.aspx | Report
Reports | RetailBanking | ScrutinyReport.aspx | Reports/RetailBanking/ScrutinyReport.aspx | Report
Reports | RetailBanking | ShareMemIntRcvReport.aspx | Reports/RetailBanking/ShareMemIntRcvReport.aspx | Report
Reports | RetailBanking | SocSchemeDailyReport.aspx | Reports/RetailBanking/SocSchemeDailyReport.aspx | Report
Reports | RetailBanking | SocietyReports.aspx | Reports/RetailBanking/SocietyReports.aspx | Report
Reports | RetailBanking | StaffLoanList.aspx | Reports/RetailBanking/StaffLoanList.aspx | Report
Reports | RetailBanking | StandingInstReport.aspx | Reports/RetailBanking/StandingInstReport.aspx | Report
Reports | RetailBanking | StatementNo7.aspx | Reports/RetailBanking/StatementNo7.aspx | Report
Reports | RetailBanking | StatementNo9.aspx | Reports/RetailBanking/StatementNo9.aspx | Report
Reports | RetailBanking | SubMemChargesReport.aspx | Reports/RetailBanking/SubMemChargesReport.aspx | Report
Reports | RetailBanking | SweepAccountStatement.aspx | Reports/RetailBanking/SweepAccountStatement.aspx | Report
Reports | RetailBanking | Form15GHReportXML.aspx | Reports/RetailBanking/TDS/Form15GHReportXML.aspx | Report
Reports | RetailBanking | TDSDetailsSummaryReport.aspx | Reports/RetailBanking/TDS/TDSDetailsSummaryReport.aspx | Report
Reports | RetailBanking | TDSReversalReportOption.aspx | Reports/RetailBanking/TDS/TDSReversalReportOption.aspx | Report
Reports | RetailBanking | TakeOverLoanReport.aspx | Reports/RetailBanking/TakeOverLoanReport.aspx | Report
Reports | RetailBanking | TopNReports.aspx | Reports/RetailBanking/TopNReports.aspx | Report
Reports | RetailBanking | TransactionReportSettings.aspx | Reports/RetailBanking/Transaction/TransactionReportSettings.aspx | Report
Reports | RetailBanking | TransactionSourceReport.aspx | Reports/RetailBanking/Transaction/TransactionSourceReport.aspx | Report
Reports | RetailBanking | TreasuryCashPosition.aspx | Reports/RetailBanking/TreasuryCashPosition.aspx | Report
Reports | RetailBanking | SocietyMiscReports.aspx | Reports/RetailBanking/UtilityReports/SocietyMiscReports.aspx | Report
Reports | RetailBanking | UtilityReports.aspx | Reports/RetailBanking/UtilityReports/UtilityReports.aspx | Report
Reports | RetailBanking | WillfulDefaulterReport.aspx | Reports/RetailBanking/WillfulDefaulterReport.aspx | Report
Reports | RetailBanking | XBRL.aspx | Reports/RetailBanking/XBRL/XBRL.aspx | Report
Reports | RetailBanking | XBRLOSS8GeneralProfile.aspx | Reports/RetailBanking/XBRL/XBRLOSS8GeneralProfile.aspx | Report
Reports | RetailBanking | XBRL_SignatoryPopUp.aspx | Reports/RetailBanking/XBRL/XBRL_SignatoryPopUp.aspx | Report
Reports | RetailBanking | rp_XBRL_AccountCategoryMapping.aspx | Reports/RetailBanking/XBRL/rp_XBRL_AccountCategoryMapping.aspx | Report
Reports | RetailBanking | b_AccStatementPrintDialog.aspx | Reports/RetailBanking/b_AccStatementPrintDialog.aspx | Report
Reports | RetailBanking | b_BankVariableDet.aspx | Reports/RetailBanking/b_BankVariableDet.aspx | Report
Reports | RetailBanking | c_LoanAbstractReport.aspx | Reports/RetailBanking/c_LoanAbstractReport.aspx | Report
Reports | RetailBanking | LoanOverdueReportSettings.aspx | Reports/RetailBanking/loan/LoanOverdueReportSettings.aspx | Report
Reports | RetailBanking | LoanRecoveryReport.aspx | Reports/RetailBanking/loan/LoanRecoveryReport.aspx | Report
Reports | RetailBanking | LoanReportSettings.aspx | Reports/RetailBanking/loan/LoanReportSettings.aspx | Report
Reports | RetailBanking | StmtOfDemandCol.aspx | Reports/RetailBanking/loan/StmtOfDemandCol.aspx | Report
Reports | RetailBanking | user_worksheet_report_option.aspx | Reports/RetailBanking/user_worksheet/user_worksheet_report_option.aspx | Report
Reports | RetailBanking | x_LoanSettlementCalc.aspx | Reports/RetailBanking/x_LoanSettlementCalc.aspx | Report
Reports | RetailBanking | x_PurposeLnAccList.aspx | Reports/RetailBanking/x_PurposeLnAccList.aspx | Report
Reports | RetailBanking | x_UserDefinedDormantLetter.aspx | Reports/RetailBanking/x_UserDefinedDormantLetter.aspx | Report
Reports | RetailBanking | x_UserDefinedNoTranLetter.aspx | Reports/RetailBanking/x_UserDefinedNoTranLetter.aspx | Report
Reports | SHGReport | SHGReport.aspx | Reports/SHGReport/SHGReport.aspx | Report
RetailBanking | ATM | AtmCardViewer.aspx | RetailBanking/ATM/AtmCardViewer.aspx | Medium
RetailBanking | ATM | AtmFinacusDataExport.aspx | RetailBanking/ATM/AtmFinacusDataExport.aspx | Medium
RetailBanking | ATM | BbpsTranReport.aspx | RetailBanking/ATM/BbpsTranReport.aspx | Report
RetailBanking | ATM | RrnInfo.aspx | RetailBanking/ATM/RrnInfo.aspx | Medium
RetailBanking | ATM | aeps_recon_reports.aspx | RetailBanking/ATM/aeps_recon_reports.aspx | Report
RetailBanking | ATM | atm_cbr_BranchTerminal_Report.aspx | RetailBanking/ATM/atm_cbr_BranchTerminal_Report.aspx | Report
RetailBanking | ATM | atm_euronet_Offus_reports.aspx | RetailBanking/ATM/atm_euronet_Offus_reports.aspx | Report
RetailBanking | ATM | atm_euronet_Onus_Offus_reports.aspx | RetailBanking/ATM/atm_euronet_Onus_Offus_reports.aspx | Report
RetailBanking | ATM | atm_euronet_reports.aspx | RetailBanking/ATM/atm_euronet_reports.aspx | Report
RetailBanking | ATM | atm_recon_ags_format_report.aspx | RetailBanking/ATM/atm_recon_ags_format_report.aspx | Report
RetailBanking | ATM | atm_reports.aspx | RetailBanking/ATM/atm_reports.aspx | Report
RetailBanking | ATM | b_CardInfo.aspx | RetailBanking/ATM/b_CardInfo.aspx | Medium
RetailBanking | ATM | b_UrbanInstaCardInfo.aspx | RetailBanking/ATM/b_UrbanInstaCardInfo.aspx | Medium
RetailBanking | ATM | en_InstaExport_cif.aspx | RetailBanking/ATM/en_InstaExport_cif.aspx | Medium
RetailBanking | ATM | en_export_cif.aspx | RetailBanking/ATM/en_export_cif.aspx | Medium
RetailBanking | ATM | finaccus_recon_reports.aspx | RetailBanking/ATM/finaccus_recon_reports.aspx | Report
RetailBanking | ATM | upi_recon_reports.aspx | RetailBanking/ATM/upi_recon_reports.aspx | Report
RetailBanking | Account | AgriLTMTLoan.aspx | RetailBanking/Account/AgriLTMTLoan.aspx | Medium
RetailBanking | Account | AlertMessages.aspx | RetailBanking/Account/AlertMessages.aspx | Medium
RetailBanking | Account | AmortChartUpload.aspx | RetailBanking/Account/AmortChartUpload.aspx | Medium
RetailBanking | Account | BOOK_DEBTS.aspx | RetailBanking/Account/BOOK_DEBTS.aspx | Medium
RetailBanking | Account | CCODRenewal.aspx | RetailBanking/Account/CCODRenewal.aspx | Medium
RetailBanking | Account | CCODRenewalMulti.aspx | RetailBanking/Account/CCODRenewalMulti.aspx | Medium
RetailBanking | Account | C_LoanActualPurpose.aspx | RetailBanking/Account/C_LoanActualPurpose.aspx | Medium
RetailBanking | Account | DailyDepositAgentAccount.aspx | RetailBanking/Account/DailyDepositAgentAccount.aspx | Medium
RetailBanking | Account | DisbScheduleUpdate.aspx | RetailBanking/Account/DisbScheduleUpdate.aspx | Medium
RetailBanking | Account | EMIReadyRecknor.aspx | RetailBanking/Account/EMIReadyRecknor.aspx | Medium
RetailBanking | Account | GOVERNMENT_SUPPLY_BILLS.aspx | RetailBanking/Account/GOVERNMENT_SUPPLY_BILLS.aspx | Medium
RetailBanking | Account | GovSecProvisionAccount.aspx | RetailBanking/Account/GovSecProvisionAccount.aspx | Medium
RetailBanking | Account | Machinaryequipment.aspx | RetailBanking/Account/Machinaryequipment.aspx | Medium
RetailBanking | Account | ModificationLog.aspx | RetailBanking/Account/ModificationLog.aspx | Medium
RetailBanking | Account | SHARES_OF_JOINT_STOCK_COMPANY.aspx | RetailBanking/Account/SHARES_OF_JOINT_STOCK_COMPANY.aspx | Medium
RetailBanking | Account | SecurityCommon.aspx | RetailBanking/Account/SecurityCommon.aspx | Medium
RetailBanking | Account | SecurityInvestmentAccount.aspx | RetailBanking/Account/SecurityInvestmentAccount.aspx | Medium
RetailBanking | Account | SecurityLogViewer.aspx | RetailBanking/Account/SecurityLogViewer.aspx | Medium
RetailBanking | Account | SecurityViewer.aspx | RetailBanking/Account/SecurityViewer.aspx | Medium
RetailBanking | Account | ShowYearlyIRSlab.aspx | RetailBanking/Account/ShowYearlyIRSlab.aspx | Medium
RetailBanking | Account | WAREHOUSE_RECEIPTS.aspx | RetailBanking/Account/WAREHOUSE_RECEIPTS.aspx | Medium
RetailBanking | Account | b_AccountEmployer.aspx | RetailBanking/Account/b_AccountEmployer.aspx | Medium
RetailBanking | Account | b_AccountNumberMapping.aspx | RetailBanking/Account/b_AccountNumberMapping.aspx | Medium
RetailBanking | Account | b_AccountTransfer.aspx | RetailBanking/Account/b_AccountTransfer.aspx | Medium
RetailBanking | Account | b_OrnamentImage.aspx | RetailBanking/Account/b_OrnamentImage.aspx | Medium
RetailBanking | Account | b_PigmyClientTransferHistory.aspx | RetailBanking/Account/b_PigmyClientTransferHistory.aspx | Medium
RetailBanking | Account | b_SchemeChange.aspx | RetailBanking/Account/b_SchemeChange.aspx | Medium
RetailBanking | Account | bankCurrentAccount.aspx | RetailBanking/Account/bankCurrentAccount.aspx | Medium
RetailBanking | Account | c_CCAccReview.aspx | RetailBanking/Account/c_CCAccReview.aspx | Medium
RetailBanking | Account | c_CCODEnhancement.aspx | RetailBanking/Account/c_CCODEnhancement.aspx | Medium
RetailBanking | Account | c_FdLineInfo.aspx | RetailBanking/Account/c_FdLineInfo.aspx | Medium
RetailBanking | Account | c_GoldDetails.aspx | RetailBanking/Account/c_GoldDetails.aspx | Medium
RetailBanking | Account | c_Insurance.aspx | RetailBanking/Account/c_Insurance.aspx | Medium
RetailBanking | Account | c_Loan.aspx | RetailBanking/Account/c_Loan.aspx | Medium
RetailBanking | Account | c_LoanSecurity.aspx | RetailBanking/Account/c_LoanSecurity.aspx | Medium
RetailBanking | Account | c_MakeOfVehicleMaster.aspx | RetailBanking/Account/c_MakeOfVehicleMaster.aspx | Medium
RetailBanking | Account | c_MultiIRSlabUpdate.aspx | RetailBanking/Account/c_MultiIRSlabUpdate.aspx | Medium
RetailBanking | Account | c_OtherSecurity.aspx | RetailBanking/Account/c_OtherSecurity.aspx | Medium
RetailBanking | Account | c_ReducingCCRenewal.aspx | RetailBanking/Account/c_ReducingCCRenewal.aspx | Medium
RetailBanking | Account | c_SecInstitutionalGuarantee.aspx | RetailBanking/Account/c_SecInstitutionalGuarantee.aspx | Medium
RetailBanking | Account | c_SecNationalSavCertificate.aspx | RetailBanking/Account/c_SecNationalSavCertificate.aspx | Medium
RetailBanking | Account | c_SecurityGOIBond.aspx | RetailBanking/Account/c_SecurityGOIBond.aspx | Medium
RetailBanking | Account | c_SecurityMutualFunds.aspx | RetailBanking/Account/c_SecurityMutualFunds.aspx | Medium
RetailBanking | Account | c_SecurityOtherCert.aspx | RetailBanking/Account/c_SecurityOtherCert.aspx | Medium
RetailBanking | Account | c_SecurityPersonalGuarantee.aspx | RetailBanking/Account/c_SecurityPersonalGuarantee.aspx | Medium
RetailBanking | Account | c_SecurityProperty.aspx | RetailBanking/Account/c_SecurityProperty.aspx | Medium
RetailBanking | Account | c_SecurityStockDetails.aspx | RetailBanking/Account/c_SecurityStockDetails.aspx | Medium
RetailBanking | Account | c_StockDetails.aspx | RetailBanking/Account/c_StockDetails.aspx | Medium
RetailBanking | Account | c_VehicleDetails.aspx | RetailBanking/Account/c_VehicleDetails.aspx | Medium
RetailBanking | Account | c_VehicleMaster.aspx | RetailBanking/Account/c_VehicleMaster.aspx | Medium
RetailBanking | Account | c_WareHouseEntry.aspx | RetailBanking/Account/c_WareHouseEntry.aspx | Medium
RetailBanking | Account | callDepositAccount.aspx | RetailBanking/Account/callDepositAccount.aspx | Medium
RetailBanking | Account | d_FDIREnhance.aspx | RetailBanking/Account/d_FDIREnhance.aspx | Medium
RetailBanking | Account | depositAccount.aspx | RetailBanking/Account/depositAccount.aspx | Medium
RetailBanking | Account | depositaccountv1.aspx | RetailBanking/Account/depositaccountv1.aspx | Medium
RetailBanking | Account | g_Group.aspx | RetailBanking/Account/g_Group.aspx | Medium
RetailBanking | Account | generalAccount.aspx | RetailBanking/Account/generalAccount.aspx | Medium
RetailBanking | Account | p_LNCCdocument.aspx | RetailBanking/Account/p_LNCCdocument.aspx | Medium
RetailBanking | Account | showMultipleAccountInfo.aspx | RetailBanking/Account/showMultipleAccountInfo.aspx | Medium
RetailBanking |  | AccountClientUpdate.aspx | RetailBanking/AccountClientUpdate.aspx | Medium
RetailBanking |  | AccountOpeningServiceChargesPosting.aspx | RetailBanking/AccountOpeningServiceChargesPosting.aspx | Medium
RetailBanking |  | AccountViewer.aspx | RetailBanking/AccountViewer.aspx | Medium
RetailBanking | AgentDevice | AgentDeviceMapLog.aspx | RetailBanking/AgentDevice/AgentDeviceMapLog.aspx | Medium
RetailBanking | AgentDevice | AgentPassword.aspx | RetailBanking/AgentDevice/AgentPassword.aspx | Medium
RetailBanking | AgentDevice | b_DeviceMaster.aspx | RetailBanking/AgentDevice/b_DeviceMaster.aspx | Medium
RetailBanking | AgriLoan | AgriLoanAccClosing.aspx | RetailBanking/AgriLoan/AgriLoanAccClosing.aspx | Medium
RetailBanking | AgriLoan | C_AgriLoanExt.aspx | RetailBanking/AgriLoan/C_AgriLoanExt.aspx | Medium
RetailBanking | AgriLoan | CropRates.aspx | RetailBanking/AgriLoan/CropRates.aspx | Medium
RetailBanking | AgriLoan | CropRatesImport.aspx | RetailBanking/AgriLoan/CropRatesImport.aspx | Medium
RetailBanking | AgriLoan | CropSeasonalCategoryDuration.aspx | RetailBanking/AgriLoan/CropSeasonalCategoryDuration.aspx | Medium
RetailBanking | AgriLoan | CropSeasonalMapping.aspx | RetailBanking/AgriLoan/CropSeasonalMapping.aspx | Medium
RetailBanking | AgriLoan | Int_subvention_CalcV1.aspx | RetailBanking/AgriLoan/Int_subvention_CalcV1.aspx | Medium
RetailBanking | AgriLoan | LoanRecovery.aspx | RetailBanking/AgriLoan/LoanRecovery.aspx | Medium
RetailBanking | AgriLoan | PACSAccOpeningBULK.aspx | RetailBanking/AgriLoan/PACSAccOpeningBULK.aspx | Medium
RetailBanking | AgriLoan | PACSMember.aspx | RetailBanking/AgriLoan/PACSMember.aspx | Medium
RetailBanking | AgriLoan | ReleasedLandDetails.aspx | RetailBanking/AgriLoan/ReleasedLandDetails.aspx | Medium
RetailBanking | AgriLoan | SocietyCreation.aspx | RetailBanking/AgriLoan/SocietyCreation.aspx | Medium
RetailBanking | AgriLoan | SocietyLoan.aspx | RetailBanking/AgriLoan/SocietyLoan.aspx | Medium
RetailBanking | AgriLoan | SubsidyMaster.aspx | RetailBanking/AgriLoan/SubsidyMaster.aspx | Medium
RetailBanking | AgriLoan | SubsidyTransfer.aspx | RetailBanking/AgriLoan/SubsidyTransfer.aspx | Medium
RetailBanking | AgriLoan | Subv_int_calc_Popup.aspx | RetailBanking/AgriLoan/Subv_int_calc_Popup.aspx | Medium
RetailBanking | AgriLoan | SubventionProductDetail.aspx | RetailBanking/AgriLoan/SubventionProductDetail.aspx | Medium
RetailBanking | AgriLoan | c_AgriInsurance.aspx | RetailBanking/AgriLoan/c_AgriInsurance.aspx | Medium
RetailBanking | AgriLoan | c_CropGroup.aspx | RetailBanking/AgriLoan/c_CropGroup.aspx | Medium
RetailBanking | AgriLoan | c_CropInscRate.aspx | RetailBanking/AgriLoan/c_CropInscRate.aspx | Medium
RetailBanking | AgriLoan | c_CropMaster.aspx | RetailBanking/AgriLoan/c_CropMaster.aspx | Medium
RetailBanking | AgriLoan | c_CropSeason.aspx | RetailBanking/AgriLoan/c_CropSeason.aspx | Medium
RetailBanking | AgriLoan | c_LoandisbursementAgri.aspx | RetailBanking/AgriLoan/c_LoandisbursementAgri.aspx | Medium
RetailBanking | AgriLoan | g_PACSBusinessAct.aspx | RetailBanking/AgriLoan/g_PACSBusinessAct.aspx | Medium
RetailBanking | AgriLoan | g_PACSIRChart.aspx | RetailBanking/AgriLoan/g_PACSIRChart.aspx | Medium
RetailBanking | AgriLoan | g_PACSTransfer.aspx | RetailBanking/AgriLoan/g_PACSTransfer.aspx | Medium
RetailBanking | AgriLoan | p_SchemeDetails.aspx | RetailBanking/AgriLoan/p_SchemeDetails.aspx | Medium
RetailBanking | AgriLoan | x_PACSMemLedOpening.aspx | RetailBanking/AgriLoan/x_PACSMemLedOpening.aspx | Medium
RetailBanking | AgriLoan | x_PACSMemberDetail.aspx | RetailBanking/AgriLoan/x_PACSMemberDetail.aspx | Medium
RetailBanking | AgriLoan | x_PACSRepayMemTrf.aspx | RetailBanking/AgriLoan/x_PACSRepayMemTrf.aspx | Medium
RetailBanking | AgriLoan | x_ShareShorFallEnqpop.aspx | RetailBanking/AgriLoan/x_ShareShorFallEnqpop.aspx | Medium
RetailBanking |  | AlertMessages.aspx | RetailBanking/AlertMessages.aspx | Medium
RetailBanking | Alerts | CCDocReviewPend.aspx | RetailBanking/Alerts/CCDocReviewPend.aspx | Medium
RetailBanking | Alerts | CCODAccExpiryInDays.aspx | RetailBanking/Alerts/CCODAccExpiryInDays.aspx | Medium
RetailBanking | Alerts | EMIAlert.aspx | RetailBanking/Alerts/EMIAlert.aspx | Medium
RetailBanking | Alerts | ExpWareHouseSecAlert.aspx | RetailBanking/Alerts/ExpWareHouseSecAlert.aspx | Medium
RetailBanking | Alerts | GetStockExpiryAcc.aspx | RetailBanking/Alerts/GetStockExpiryAcc.aspx | Medium
RetailBanking | Alerts | GoldLTV.aspx | RetailBanking/Alerts/GoldLTV.aspx | Medium
RetailBanking | Alerts | HighValTrOnAccOp.aspx | RetailBanking/Alerts/HighValTrOnAccOp.aspx | Medium
RetailBanking | Alerts | HighValTrOnHOl.aspx | RetailBanking/Alerts/HighValTrOnHOl.aspx | Medium
RetailBanking | Alerts | Insurancealert.aspx | RetailBanking/Alerts/Insurancealert.aspx | Medium
RetailBanking | Alerts | InvstIntSettleAlert.aspx | RetailBanking/Alerts/InvstIntSettleAlert.aspx | Medium
RetailBanking | Alerts | InvstMatAccAlert.aspx | RetailBanking/Alerts/InvstMatAccAlert.aspx | Medium
RetailBanking | Alerts | LargeValueAdvancesalert.aspx | RetailBanking/Alerts/LargeValueAdvancesalert.aspx | Medium
RetailBanking | Alerts | LienFDMaturedAlert.aspx | RetailBanking/Alerts/LienFDMaturedAlert.aspx | Medium
RetailBanking | Alerts | NpaProjection.aspx | RetailBanking/Alerts/NpaProjection.aspx | Medium
RetailBanking | Alerts | PendingCKYCAlert.aspx | RetailBanking/Alerts/PendingCKYCAlert.aspx | Medium
RetailBanking | Alerts | RiskCatByThreshold.aspx | RetailBanking/Alerts/RiskCatByThreshold.aspx | Medium
RetailBanking | Alerts | SMAMarkingAlert.aspx | RetailBanking/Alerts/SMAMarkingAlert.aspx | Medium
RetailBanking | Alerts | SeniorCitizen.aspx | RetailBanking/Alerts/SeniorCitizen.aspx | Medium
RetailBanking | Alerts | SpecialInstruction.aspx | RetailBanking/Alerts/SpecialInstruction.aspx | Medium
RetailBanking | Alerts | TODExpired.aspx | RetailBanking/Alerts/TODExpired.aspx | Medium
RetailBanking | Alerts | TranInDormantAcc.aspx | RetailBanking/Alerts/TranInDormantAcc.aspx | Medium
RetailBanking | Alerts | UnCrCCAccInDays.aspx | RetailBanking/Alerts/UnCrCCAccInDays.aspx | Medium
RetailBanking | Alerts | al_MinorTurnMajor.aspx | RetailBanking/Alerts/al_MinorTurnMajor.aspx | Medium
RetailBanking | Alerts | al_SuspiciousTranDet.aspx | RetailBanking/Alerts/al_SuspiciousTranDet.aspx | Medium
RetailBanking | Alerts | rp_TargetMonthAlertV1.aspx | RetailBanking/Alerts/rp_TargetMonthAlertV1.aspx | Medium
RetailBanking |  | AutoDayEndViewerPopup.aspx | RetailBanking/AutoDayEndViewerPopup.aspx | Medium
RetailBanking |  | AutoDayendViewer.aspx | RetailBanking/AutoDayendViewer.aspx | Medium
RetailBanking | BG | BG_Client.aspx | RetailBanking/BG/BG_Client.aspx | Medium
RetailBanking | BG | BG_RevokeTran.aspx | RetailBanking/BG/BG_RevokeTran.aspx | Medium
RetailBanking | BG | Bg_ClientRenewal.aspx | RetailBanking/BG/Bg_ClientRenewal.aspx | Medium
RetailBanking | BG | Bg_FdLineInfo.aspx | RetailBanking/BG/Bg_FdLineInfo.aspx | Medium
RetailBanking | BG | Bg_Issue.aspx | RetailBanking/BG/Bg_Issue.aspx | Medium
RetailBanking | BG | Bg_IssueRenewalTran.aspx | RetailBanking/BG/Bg_IssueRenewalTran.aspx | Medium
RetailBanking | BG | Bg_LienNotationRelease.aspx | RetailBanking/BG/Bg_LienNotationRelease.aspx | Medium
RetailBanking | BG | bgClose.aspx | RetailBanking/BG/bgClose.aspx | Medium
RetailBanking |  | B_TerroristGroupNew.aspx | RetailBanking/B_TerroristGroupNew.aspx | Medium
RetailBanking | BillCollection | x_BillPurchase.aspx | RetailBanking/BillCollection/x_BillPurchase.aspx | Medium
RetailBanking | BillCollection | x_billCollection.aspx | RetailBanking/BillCollection/x_billCollection.aspx | Medium
RetailBanking |  | BookBalRunStatuspopup.aspx | RetailBanking/BookBalRunStatuspopup.aspx | Medium
RetailBanking |  | BookBalanceCertificateReportV1.aspx | RetailBanking/BookBalanceCertificateReportV1.aspx | Report
RetailBanking |  | BookBalanceCheckerJS.aspx | RetailBanking/BookBalanceCheckerJS.aspx | Medium
RetailBanking | CBDT | cbdt.aspx | RetailBanking/CBDT/cbdt.aspx | Medium
RetailBanking | Cash | ExchangeDenomination.aspx | RetailBanking/Cash/ExchangeDenomination.aspx | Medium
RetailBanking | Cash | b_CashRemitLimit.aspx | RetailBanking/Cash/b_CashRemitLimit.aspx | Medium
RetailBanking | Cash | b_HeadCashierMap.aspx | RetailBanking/Cash/b_HeadCashierMap.aspx | Medium
RetailBanking | Cash | x_CashierScroll.aspx | RetailBanking/Cash/x_CashierScroll.aspx | Medium
RetailBanking | Cash | x_ChestCashierLedger.aspx | RetailBanking/Cash/x_ChestCashierLedger.aspx | Medium
RetailBanking | Cash | x_ChestCashierToCashierLedger.aspx | RetailBanking/Cash/x_ChestCashierToCashierLedger.aspx | Medium
RetailBanking | Cash | x_ChestOpening.aspx | RetailBanking/Cash/x_ChestOpening.aspx | Medium
RetailBanking | Cash | x_Denomination.aspx | RetailBanking/Cash/x_Denomination.aspx | Medium
RetailBanking | Cash | x_DenominationUnit.aspx | RetailBanking/Cash/x_DenominationUnit.aspx | Medium
RetailBanking | CersaiMortgage | c_CersaiMortgage.aspx | RetailBanking/CersaiMortgage/c_CersaiMortgage.aspx | Medium
RetailBanking |  | ChangeClientType.aspx | RetailBanking/ChangeClientType.aspx | Medium
RetailBanking |  | ChequeBookDetPopUp.aspx | RetailBanking/ChequeBookDetPopUp.aspx | Medium
RetailBanking |  | ChequeBookReturn.aspx | RetailBanking/ChequeBookReturn.aspx | Medium
RetailBanking | Clearing | AccountDialog.aspx | RetailBanking/Clearing/AccountDialog.aspx | Medium
RetailBanking | Clearing | CTSCentralizeLotUpdate.aspx | RetailBanking/Clearing/CTSCentralizeLotUpdate.aspx | Medium
RetailBanking | Clearing | CTSChequeShifting.aspx | RetailBanking/Clearing/CTSChequeShifting.aspx | Medium
RetailBanking | Clearing | CTSClearingLotExport.aspx | RetailBanking/Clearing/CTSClearingLotExport.aspx | Medium
RetailBanking | Clearing | CTSInwardReturn.aspx | RetailBanking/Clearing/CTSInwardReturn.aspx | Medium
RetailBanking | Clearing | CTS_HdfcHubVendor.aspx | RetailBanking/Clearing/CTS_HdfcHubVendor.aspx | Medium
RetailBanking | Clearing | CTS_OWClearingReturnMark.aspx | RetailBanking/Clearing/CTS_OWClearingReturnMark.aspx | Medium
RetailBanking | Clearing | CTS_PositiveFinalRespImport.aspx | RetailBanking/Clearing/CTS_PositiveFinalRespImport.aspx | Medium
RetailBanking | Clearing | CTS_PositivePayEntries.aspx | RetailBanking/Clearing/CTS_PositivePayEntries.aspx | Medium
RetailBanking | Clearing | CTS_PositivePayExport.aspx | RetailBanking/Clearing/CTS_PositivePayExport.aspx | Medium
RetailBanking | Clearing | CTS_PositiveRespRead.aspx | RetailBanking/Clearing/CTS_PositiveRespRead.aspx | Medium
RetailBanking | Clearing | ClearingLotExport.aspx | RetailBanking/Clearing/ClearingLotExport.aspx | Medium
RetailBanking | Clearing | Cts_OWDFileResp.aspx | RetailBanking/Clearing/Cts_OWDFileResp.aspx | Medium
RetailBanking | Clearing | DeCntrLotExport.aspx | RetailBanking/Clearing/DeCntrLotExport.aspx | Medium
RetailBanking | Clearing | InwardStatusRevert.aspx | RetailBanking/Clearing/InwardStatusRevert.aspx | Medium
RetailBanking | Clearing | OWDFileRespStat.aspx | RetailBanking/Clearing/OWDFileRespStat.aspx | Medium
RetailBanking | Clearing | OWDFileRespStatRejectRecord.aspx | RetailBanking/Clearing/OWDFileRespStatRejectRecord.aspx | Medium
RetailBanking | Clearing | OWDFileRespStatRejectRecordDetails.aspx | RetailBanking/Clearing/OWDFileRespStatRejectRecordDetails.aspx | Medium
RetailBanking | Clearing | OWLotHoldMarking.aspx | RetailBanking/Clearing/OWLotHoldMarking.aspx | Medium
RetailBanking | Clearing | OutwardClgTransactionUpdate.aspx | RetailBanking/Clearing/OutwardClgTransactionUpdate.aspx | Complex
RetailBanking | Clearing | OwClgClearRetMarking.aspx | RetailBanking/Clearing/OwClgClearRetMarking.aspx | Medium
RetailBanking | Clearing | PopupReasonCode.aspx | RetailBanking/Clearing/PopupReasonCode.aspx | Medium
RetailBanking | Clearing | ShowChequeDetails.aspx | RetailBanking/Clearing/ShowChequeDetails.aspx | Medium
RetailBanking | Clearing | SubMemChequeShifting.aspx | RetailBanking/Clearing/SubMemChequeShifting.aspx | Medium
RetailBanking | Clearing | addOutwardClearingTransaction.aspx | RetailBanking/Clearing/addOutwardClearingTransaction.aspx | Complex
RetailBanking | Clearing | b_CTSIwClearingContraTrans.aspx | RetailBanking/Clearing/b_CTSIwClearingContraTrans.aspx | Medium
RetailBanking | Clearing | b_CTSIwReturnContraTrans.aspx | RetailBanking/Clearing/b_CTSIwReturnContraTrans.aspx | Medium
RetailBanking | Clearing | b_inwardClgChequeImages.aspx | RetailBanking/Clearing/b_inwardClgChequeImages.aspx | Medium
RetailBanking | Clearing | b_inwardClgFileExtension.aspx | RetailBanking/Clearing/b_inwardClgFileExtension.aspx | Medium
RetailBanking | Clearing | b_inwardClgFileUpdate.aspx | RetailBanking/Clearing/b_inwardClgFileUpdate.aspx | Medium
RetailBanking | Clearing | b_inwardClgFileV2.aspx | RetailBanking/Clearing/b_inwardClgFileV2.aspx | Medium
RetailBanking | Clearing | CTSOutwardTranONUS.aspx | RetailBanking/Clearing/consclearing/CTSOutwardTranONUS.aspx | Medium
RetailBanking | Clearing | CTSOwLotCrDateUpdate.aspx | RetailBanking/Clearing/consclearing/CTSOwLotCrDateUpdate.aspx | Medium
RetailBanking | Clearing | CTSOwTransAccUpdate.aspx | RetailBanking/Clearing/consclearing/CTSOwTransAccUpdate.aspx | Medium
RetailBanking | Clearing | CentralizeClearingOwFileExport.aspx | RetailBanking/Clearing/consclearing/CentralizeClearingOwFileExport.aspx | Medium
RetailBanking | Clearing | CentralizedOutwardClearingTransaction.aspx | RetailBanking/Clearing/consclearing/CentralizedOutwardClearingTransaction.aspx | Complex
RetailBanking | Clearing | CentralizedOutwardLotDisable.aspx | RetailBanking/Clearing/consclearing/CentralizedOutwardLotDisable.aspx | Medium
RetailBanking | Clearing | Cl_OwRecPayDetail.aspx | RetailBanking/Clearing/consclearing/Cl_OwRecPayDetail.aspx | Medium
RetailBanking | Clearing | CtsInwChqNoUpdate.aspx | RetailBanking/Clearing/consclearing/CtsInwChqNoUpdate.aspx | Medium
RetailBanking | Clearing | CtsIwFileImport.aspx | RetailBanking/Clearing/consclearing/CtsIwFileImport.aspx | Medium
RetailBanking | Clearing | CtslOwReturnImport.aspx | RetailBanking/Clearing/consclearing/CtslOwReturnImport.aspx | Medium
RetailBanking | Clearing | OwLateReturn.aspx | RetailBanking/Clearing/consclearing/OwLateReturn.aspx | Medium
RetailBanking | Clearing | SubmemReturnContra.aspx | RetailBanking/Clearing/consclearing/SubmemReturnContra.aspx | Medium
RetailBanking | Clearing | SubmemberOwClrRetEntry.aspx | RetailBanking/Clearing/consclearing/SubmemberOwClrRetEntry.aspx | Medium
RetailBanking | Clearing | outward_clear_v1.aspx | RetailBanking/Clearing/consclearing/outward_clear_v1.aspx | Medium
RetailBanking | Clearing | outward_clearing_pre_val.aspx | RetailBanking/Clearing/consclearing/outward_clearing_pre_val.aspx | Medium
RetailBanking | Clearing | createLot.aspx | RetailBanking/Clearing/createLot.aspx | Medium
RetailBanking | Clearing | ctsDashEnqForm.aspx | RetailBanking/Clearing/ctsDashEnqForm.aspx | Medium
RetailBanking | Clearing | ctsDashEnqFormPopup.aspx | RetailBanking/Clearing/ctsDashEnqFormPopup.aspx | Medium
RetailBanking | Clearing | cts_P2FMarking.aspx | RetailBanking/Clearing/cts_P2FMarking.aspx | Medium
RetailBanking | Clearing | executeOutwardClearingTransaction.aspx | RetailBanking/Clearing/executeOutwardClearingTransaction.aspx | Complex
RetailBanking | Clearing | outward_clear.aspx | RetailBanking/Clearing/outward_clear.aspx | Medium
RetailBanking |  | ClientComplaintRegister.aspx | RetailBanking/ClientComplaintRegister.aspx | Medium
RetailBanking |  | ClientComplaintRegisterDetails.aspx | RetailBanking/ClientComplaintRegisterDetails.aspx | Medium
RetailBanking |  | ClientGroupViewer.aspx | RetailBanking/ClientGroupViewer.aspx | Medium
RetailBanking |  | ClientTdsCashExempt.aspx | RetailBanking/ClientTdsCashExempt.aspx | Medium
RetailBanking |  | ClientTdscashExemptDetPopup.aspx | RetailBanking/ClientTdscashExemptDetPopup.aspx | Medium
RetailBanking |  | ContraTrEntriesUpdate.aspx | RetailBanking/ContraTrEntriesUpdate.aspx | Medium
RetailBanking |  | CounterfeitNotes.aspx | RetailBanking/CounterfeitNotes.aspx | Medium
RetailBanking |  | DDPOParameterSetting.aspx | RetailBanking/DDPOParameterSetting.aspx | Medium
RetailBanking | Dayend | DayendDetails.aspx | RetailBanking/Dayend/DayendDetails.aspx | Medium
RetailBanking | DeathClaim | g_DeathClaim.aspx | RetailBanking/DeathClaim/g_DeathClaim.aspx | Medium
RetailBanking |  | DepLNCCIntegrityChecker.aspx | RetailBanking/DepLNCCIntegrityChecker.aspx | Medium
RetailBanking |  | DepositInterestSlab.aspx | RetailBanking/DepositInterestSlab.aspx | Medium
RetailBanking |  | DuplicateFDPrint.aspx | RetailBanking/DuplicateFDPrint.aspx | Medium
RetailBanking | ECS | ECS_SubMemCrDrShifting.aspx | RetailBanking/ECS/MandateManagement/ECS_SubMemCrDrShifting.aspx | Medium
RetailBanking | ECS | Ecs_MandateNewInwFile.aspx | RetailBanking/ECS/MandateManagement/Ecs_MandateNewInwFile.aspx | Medium
RetailBanking | ECS | Ecs_MandatenewinwAcceptfile.aspx | RetailBanking/ECS/MandateManagement/Ecs_MandatenewinwAcceptfile.aspx | Medium
RetailBanking | ECS | Ecs_MandatenewinwAcceptfileV1.aspx | RetailBanking/ECS/MandateManagement/Ecs_MandatenewinwAcceptfileV1.aspx | Medium
RetailBanking | ECS | NewMandateImage.aspx | RetailBanking/ECS/MandateManagement/NewMandateImage.aspx | Medium
RetailBanking | ECS | ecs_MandateACKFile.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateACKFile.aspx | Medium
RetailBanking | ECS | ecs_MandateACKFilePopup.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateACKFilePopup.aspx | Medium
RetailBanking | ECS | ecs_MandateACKFileV1.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateACKFileV1.aspx | Medium
RetailBanking | ECS | ecs_MandateAcceptResponseFileV1.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateAcceptResponseFileV1.aspx | Medium
RetailBanking | ECS | ecs_MandateBulkExport.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateBulkExport.aspx | Medium
RetailBanking | ECS | ecs_MandateNewBulkInwFile.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateNewBulkInwFile.aspx | Medium
RetailBanking | ECS | ecs_MandateNewFile.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateNewFile.aspx | Medium
RetailBanking | ECS | ecs_MandateNewInwFilePopup.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateNewInwFilePopup.aspx | Medium
RetailBanking | ECS | ecs_MandateReport.aspx | RetailBanking/ECS/MandateManagement/ecs_MandateReport.aspx | Report
RetailBanking | ECS | ecs_MandatenewinwAcceptfilePopupV1.aspx | RetailBanking/ECS/MandateManagement/ecs_MandatenewinwAcceptfilePopupV1.aspx | Medium
RetailBanking | ECS | ecs_ProductTypeTransactionReport.aspx | RetailBanking/ECS/MandateManagement/ecs_ProductTypeTransactionReport.aspx | Report
RetailBanking | ECS | x_AchProcessResponseFileData.aspx | RetailBanking/ECS/MandateManagement/x_AchProcessResponseFileData.aspx | Medium
RetailBanking | ECS | x_GlobalACHInputRtnACKFile.aspx | RetailBanking/ECS/MandateManagement/x_GlobalACHInputRtnACKFile.aspx | Medium
RetailBanking | ECS | x_MICRECSGenerateFileData.aspx | RetailBanking/ECS/MandateManagement/x_MICRECSGenerateFileData.aspx | Medium
RetailBanking | ECS | b_SubMemberBank.aspx | RetailBanking/ECS/b_SubMemberBank.aspx | Medium
RetailBanking | ECS | ecs_OtherPayFileData.aspx | RetailBanking/ECS/ecs_OtherPayFileData.aspx | Medium
RetailBanking |  | EMIChart.aspx | RetailBanking/EMIChart.aspx | Medium
RetailBanking |  | FDLienDetails.aspx | RetailBanking/FDLienDetails.aspx | Medium
RetailBanking |  | FDPrint.aspx | RetailBanking/FDPrint.aspx | Medium
RetailBanking | FI | fi.aspx | RetailBanking/FI/fi.aspx | Medium
RetailBanking | FI | fi_accountHeadMapping.aspx | RetailBanking/FI/fi_accountHeadMapping.aspx | Medium
RetailBanking | FI | fi_agentconfig.aspx | RetailBanking/FI/fi_agentconfig.aspx | Medium
RetailBanking |  | FailedSweepInProcess.aspx | RetailBanking/FailedSweepInProcess.aspx | Medium
RetailBanking |  | GoldLoanReceipt.aspx | RetailBanking/GoldLoanReceipt.aspx | Medium
RetailBanking | IMPS | IMPSChangeStatus.aspx | RetailBanking/IMPS/IMPSChangeStatus.aspx | Medium
RetailBanking | IMPS | IMPSOutwardStatus.aspx | RetailBanking/IMPS/IMPSOutwardStatus.aspx | Medium
RetailBanking | IMPS | IMPSOutwardstatusDetails.aspx | RetailBanking/IMPS/IMPSOutwardstatusDetails.aspx | Medium
RetailBanking | IMPS | IMPS_Outward.aspx | RetailBanking/IMPS/IMPS_Outward.aspx | Medium
RetailBanking | IMPS | imps_mmid_request.aspx | RetailBanking/IMPS/imps_mmid_request.aspx | Medium
RetailBanking | IMPS | mobile_bankingreport.aspx | RetailBanking/IMPS/mobile_bankingreport.aspx | Report
RetailBanking | IMPS | mobile_registeredClient.aspx | RetailBanking/IMPS/mobile_registeredClient.aspx | Medium
RetailBanking | Insurance | c_LoanInsurance.aspx | RetailBanking/Insurance/c_LoanInsurance.aspx | Medium
RetailBanking | InterestActivity | ATMServiceChargePosting_Calc.aspx | RetailBanking/InterestActivity/Charges/ATMServiceChargePosting_Calc.aspx | Medium
RetailBanking | InterestActivity | CC_Unutilized_Limit_calc.aspx | RetailBanking/InterestActivity/Charges/CC_Unutilized_Limit_calc.aspx | Medium
RetailBanking | InterestActivity | CashWithdrawalCharges_Calc.aspx | RetailBanking/InterestActivity/Charges/CashWithdrawalCharges_Calc.aspx | Medium
RetailBanking | InterestActivity | Charges_Calc_Posting_V2.aspx | RetailBanking/InterestActivity/Charges/Charges_Calc_Posting_V2.aspx | Medium
RetailBanking | InterestActivity | NonComplianceCharges_Calc_Posting.aspx | RetailBanking/InterestActivity/Charges/NonComplianceCharges_Calc_Posting.aspx | Medium
RetailBanking | InterestActivity | NonStockStmtCharges_Calc_V2.aspx | RetailBanking/InterestActivity/Charges/NonStockStmtCharges_Calc_V2.aspx | Medium
RetailBanking | InterestActivity | PigmyToLoanTrfCharges.aspx | RetailBanking/InterestActivity/Charges/PigmyToLoanTrfCharges.aspx | Medium
RetailBanking | InterestActivity | QRCharges_Calc_Posting.aspx | RetailBanking/InterestActivity/Charges/QRCharges_Calc_Posting.aspx | Medium
RetailBanking | InterestActivity | SMSChargesCalculation_V2.aspx | RetailBanking/InterestActivity/Charges/SMSChargesCalculation_V2.aspx | Medium
RetailBanking | InterestActivity | StationaryCharges_Calc_PostingV1.aspx | RetailBanking/InterestActivity/Charges/StationaryCharges_Calc_PostingV1.aspx | Medium
RetailBanking | InterestActivity | b_SubMemCharges.aspx | RetailBanking/InterestActivity/Charges/b_SubMemCharges.aspx | Medium
RetailBanking | InterestActivity | c_DormantCharges_V2.aspx | RetailBanking/InterestActivity/Charges/c_DormantCharges_V2.aspx | Medium
RetailBanking | InterestActivity | cc_NonRenewalcharges_calc_V2.aspx | RetailBanking/InterestActivity/Charges/cc_NonRenewalcharges_calc_V2.aspx | Medium
RetailBanking | InterestActivity | x_AllbranchStatusLog.aspx | RetailBanking/InterestActivity/Charges/x_AllbranchStatusLog.aspx | Medium
RetailBanking | InterestActivity | x_Charge_Calc_ForMinimumBalanceProvision_V2.aspx | RetailBanking/InterestActivity/Charges/x_Charge_Calc_ForMinimumBalanceProvision_V2.aspx | Medium
RetailBanking | InterestActivity | x_ChargefreqCalc.aspx | RetailBanking/InterestActivity/Charges/x_ChargefreqCalc.aspx | Medium
RetailBanking | InterestActivity | x_ChargesSelector.aspx | RetailBanking/InterestActivity/Charges/x_ChargesSelector.aspx | Medium
RetailBanking | InterestActivity | x_CreditMonCharges_Calc.aspx | RetailBanking/InterestActivity/Charges/x_CreditMonCharges_Calc.aspx | Medium
RetailBanking | InterestActivity | x_IMPSChargeProvision.aspx | RetailBanking/InterestActivity/Charges/x_IMPSChargeProvision.aspx | Medium
RetailBanking | InterestActivity | x_LoanInsuranceCharges_Calc.aspx | RetailBanking/InterestActivity/Charges/x_LoanInsuranceCharges_Calc.aspx | Medium
RetailBanking | InterestActivity | fd_int_calc_V1.aspx | RetailBanking/InterestActivity/FD/fd_int_calc_V1.aspx | Medium
RetailBanking | InterestActivity | SavingInterestDetails.aspx | RetailBanking/InterestActivity/SavingInterestDetails.aspx | Medium
RetailBanking | InterestActivity | TDS_int_calc.aspx | RetailBanking/InterestActivity/TDS/TDS_int_calc.aspx | Medium
RetailBanking | InterestActivity | TDSallaccountDetails.aspx | RetailBanking/InterestActivity/TDS/TDSallaccountDetails.aspx | Medium
RetailBanking | InterestActivity | TdsBranchwisedetails.aspx | RetailBanking/InterestActivity/TDS/TdsBranchwisedetails.aspx | Medium
RetailBanking | InterestActivity | b_TdsChallanDetails.aspx | RetailBanking/InterestActivity/TDS/b_TdsChallanDetails.aspx | Medium
RetailBanking | InterestActivity | x_TDS_PANABCCA.aspx | RetailBanking/InterestActivity/TDS/x_TDS_PANABCCA.aspx | Medium
RetailBanking | InterestActivity | IntActPreChecker.aspx | RetailBanking/InterestActivity/lnccod/IntActPreChecker.aspx | Medium
RetailBanking | InterestActivity | IntActPreCheckerLog_Popup.aspx | RetailBanking/InterestActivity/lnccod/IntActPreCheckerLog_Popup.aspx | Medium
RetailBanking | InterestActivity | InterestRebate_calc.aspx | RetailBanking/InterestActivity/lnccod/InterestRebate_calc.aspx | Medium
RetailBanking | InterestActivity | LNPenalPost.aspx | RetailBanking/InterestActivity/lnccod/LNPenalPost.aspx | Medium
RetailBanking | InterestActivity | lnccod_int_calc_Popup_V1.aspx | RetailBanking/InterestActivity/lnccod/lnccod_int_calc_Popup_V1.aspx | Medium
RetailBanking | InterestActivity | lnccod_int_calc_V1.aspx | RetailBanking/InterestActivity/lnccod/lnccod_int_calc_V1.aspx | Medium
RetailBanking | InterestActivity | rd_int_calc_V1.aspx | RetailBanking/InterestActivity/rd/rd_int_calc_V1.aspx | Medium
RetailBanking | InterestActivity | sb_int_calc_V2.aspx | RetailBanking/InterestActivity/sb/sb_int_calc_V2.aspx | Medium
RetailBanking | InterestActivity | x_FDMatIntProv.aspx | RetailBanking/InterestActivity/x_FDMatIntProv.aspx | Medium
RetailBanking | InterestActivity | x_FDMatIntProvLog.aspx | RetailBanking/InterestActivity/x_FDMatIntProvLog.aspx | Medium
RetailBanking | InterestActivity | x_InvestmentInterestActivity.aspx | RetailBanking/InterestActivity/x_InvestmentInterestActivity.aspx | Medium
RetailBanking | InterestActivity | x_NonOperativeInterestActivity.aspx | RetailBanking/InterestActivity/x_NonOperativeInterestActivity.aspx | Medium
RetailBanking | InterestActivity | x_NonOperativeInterestActivity_V2.aspx | RetailBanking/InterestActivity/x_NonOperativeInterestActivity_V2.aspx | Medium
RetailBanking | InterestActivity | x_SBInterestOnDemand.aspx | RetailBanking/InterestActivity/x_SBInterestOnDemand.aspx | Medium
RetailBanking | InterestActivity | x_SavingInterestActivity.aspx | RetailBanking/InterestActivity/x_SavingInterestActivity.aspx | Medium
RetailBanking | KYC | ClientsConsent.aspx | RetailBanking/KYC/ClientsConsent.aspx | Medium
RetailBanking | KYC | KYCClientPopup_V1.aspx | RetailBanking/KYC/KYCClientPopup_V1.aspx | Medium
RetailBanking | KYC | KYC_DashboardDetails.aspx | RetailBanking/KYC/KYC_DashboardDetails.aspx | Medium
RetailBanking | KYC | kyc_Batch.aspx | RetailBanking/KYC/kyc_Batch.aspx | Medium
RetailBanking | KYC | kyc_BulkDownloadGenFile.aspx | RetailBanking/KYC/kyc_BulkDownloadGenFile.aspx | Medium
RetailBanking | KYC | kyc_BulkDownloadResponseFile.aspx | RetailBanking/KYC/kyc_BulkDownloadResponseFile.aspx | Medium
RetailBanking | KYC | kyc_BulkFile.aspx | RetailBanking/KYC/kyc_BulkFile.aspx | Medium
RetailBanking | KYC | kyc_BulkSearch.aspx | RetailBanking/KYC/kyc_BulkSearch.aspx | Medium
RetailBanking | KYC | kyc_ClientAdditionalDetails.aspx | RetailBanking/KYC/kyc_ClientAdditionalDetails.aspx | Medium
RetailBanking | KYC | kyc_ClientDetailsPopup.aspx | RetailBanking/KYC/kyc_ClientDetailsPopup.aspx | Medium
RetailBanking | KYC | kyc_ClientValidationStatus.aspx | RetailBanking/KYC/kyc_ClientValidationStatus.aspx | Medium
RetailBanking | KYC | kyc_Dashboard.aspx | RetailBanking/KYC/kyc_Dashboard.aspx | Medium
RetailBanking | KYC | kyc_DocSnapPreview.aspx | RetailBanking/KYC/kyc_DocSnapPreview.aspx | Medium
RetailBanking | KYC | kyc_DownloadBatch.aspx | RetailBanking/KYC/kyc_DownloadBatch.aspx | Medium
RetailBanking | KYC | kyc_GetCustomerDetails.aspx | RetailBanking/KYC/kyc_GetCustomerDetails.aspx | Medium
RetailBanking | KYC | kyc_Inward.aspx | RetailBanking/KYC/kyc_Inward.aspx | Medium
RetailBanking | KYC | kyc_ReconcilePostResponseFile.aspx | RetailBanking/KYC/kyc_ReconcilePostResponseFile.aspx | Medium
RetailBanking | KYC | kyc_ReconcileResponseFile.aspx | RetailBanking/KYC/kyc_ReconcileResponseFile.aspx | Medium
RetailBanking |  | LNCCAutoIntAccrualUpdate.aspx | RetailBanking/LNCCAutoIntAccrualUpdate.aspx | Medium
RetailBanking |  | LedgerNullifyContra.aspx | RetailBanking/LedgerNullifyContra.aspx | Medium
RetailBanking | Legal | lg_Consultant.aspx | RetailBanking/Legal/lg_Consultant.aspx | Medium
RetailBanking | Legal | lg_PoliceCase.aspx | RetailBanking/Legal/lg_PoliceCase.aspx | Medium
RetailBanking | Legal | lg_SuitCase.aspx | RetailBanking/Legal/lg_SuitCase.aspx | Medium
RetailBanking | Legal | lg_SuitCaseClosing.aspx | RetailBanking/Legal/lg_SuitCaseClosing.aspx | Medium
RetailBanking | Legal | lg_SuitCaseHistory.aspx | RetailBanking/Legal/lg_SuitCaseHistory.aspx | Medium
RetailBanking |  | LienNotationRelease.aspx | RetailBanking/LienNotationRelease.aspx | Medium
RetailBanking |  | LoanAndAdvances.aspx | RetailBanking/LoanAndAdvances.aspx | Medium
RetailBanking |  | LoanDisbursmentDebitCharges.aspx | RetailBanking/LoanDisbursmentDebitCharges.aspx | Medium
RetailBanking |  | LoanInterestUpdation.aspx | RetailBanking/LoanInterestUpdation.aspx | Medium
RetailBanking |  | LoanProductDetail.aspx | RetailBanking/LoanProductDetail.aspx | Medium
RetailBanking |  | LosConfiguration.aspx | RetailBanking/LosConfiguration.aspx | Medium
RetailBanking |  | MemberSharedLedger.aspx | RetailBanking/MemberSharedLedger.aspx | Medium
RetailBanking |  | MinorTurnMajorLetterTemplate.aspx | RetailBanking/MinorTurnMajorLetterTemplate.aspx | Medium
RetailBanking | NPA | DepositNPAcalc.aspx | RetailBanking/NPA/DepositNPAcalc.aspx | Medium
RetailBanking | NPA | SubAccountNPAMarking.aspx | RetailBanking/NPA/SubAccountNPAMarking.aspx | Medium
RetailBanking | NPA | b_NPAClassMaster.aspx | RetailBanking/NPA/b_NPAClassMaster.aspx | Medium
RetailBanking | NPA | b_NPAMaster.aspx | RetailBanking/NPA/b_NPAMaster.aspx | Medium
RetailBanking | NPA | b_NPAParameters.aspx | RetailBanking/NPA/b_NPAParameters.aspx | Medium
RetailBanking | NPA | b_NPAReceivableRecAppr.aspx | RetailBanking/NPA/b_NPAReceivableRecAppr.aspx | Medium
RetailBanking | NPA | c_ManualNPAStatUpdate.aspx | RetailBanking/NPA/c_ManualNPAStatUpdate.aspx | Medium
RetailBanking | NPA | c_NPAAccountSetting.aspx | RetailBanking/NPA/c_NPAAccountSetting.aspx | Medium
RetailBanking | NPA | c_NPAMethodMapping.aspx | RetailBanking/NPA/c_NPAMethodMapping.aspx | Medium
RetailBanking | NPA | x_InvNPASetting.aspx | RetailBanking/NPA/x_InvNPASetting.aspx | Medium
RetailBanking | NPA | x_NPACalculation.aspx | RetailBanking/NPA/x_NPACalculation.aspx | Medium
RetailBanking | NPA | x_NPACalculationMulti_V2.aspx | RetailBanking/NPA/x_NPACalculationMulti_V2.aspx | Medium
RetailBanking | NPA | x_NpaIntRevert.aspx | RetailBanking/NPA/x_NpaIntRevert.aspx | Medium
RetailBanking | NPCI | npci_All_DisputeTransactionPosting.aspx | RetailBanking/NPCI/npci_All_DisputeTransactionPosting.aspx | Complex
RetailBanking | NPCI | npci_All_DisputesImport.aspx | RetailBanking/NPCI/npci_All_DisputesImport.aspx | Medium
RetailBanking |  | OfflineLedPost.aspx | RetailBanking/OfflineLedPost.aspx | Medium
RetailBanking | PACS | x_PACSCropInsurance.aspx | RetailBanking/PACS/x_PACSCropInsurance.aspx | Medium
RetailBanking | PACS | x_PACSMemberLedgerView.aspx | RetailBanking/PACS/x_PACSMemberLedgerView.aspx | Medium
RetailBanking |  | PassBookParameterSetting.aspx | RetailBanking/PassBookParameterSetting.aspx | Medium
RetailBanking |  | PassBookPrinting.aspx | RetailBanking/PassBookPrinting.aspx | Medium
RetailBanking |  | PassbookPrint.aspx | RetailBanking/PassbookPrint.aspx | Medium
RetailBanking |  | PresentPosition.aspx | RetailBanking/PresentPosition.aspx | Medium
RetailBanking |  | PrintDDPO.aspx | RetailBanking/PrintDDPO.aspx | Medium
RetailBanking | Printing | DepositSlipPrinting.aspx | RetailBanking/Printing/DepositSlipPrinting.aspx | Medium
RetailBanking | Printing | LoanRepaymentReceipt.aspx | RetailBanking/Printing/LoanRepaymentReceipt.aspx | Medium
RetailBanking | Printing | RecPrinting.aspx | RetailBanking/Printing/RecPrinting.aspx | Medium
RetailBanking | RTGS | FundTransferMsgLog.aspx | RetailBanking/RTGS/FundTransferMsgLog.aspx | Medium
RetailBanking | RTGS | Iftas24By7Neft.aspx | RetailBanking/RTGS/Iftas24By7Neft.aspx | Medium
RetailBanking | RTGS | OutwardPayRetMark.aspx | RetailBanking/RTGS/OutwardPayRetMark.aspx | Medium
RetailBanking | RTGS | RTGSEnquiry.aspx | RetailBanking/RTGS/RTGSEnquiry.aspx | Medium
RetailBanking | RTGS | RTGSExport.aspx | RetailBanking/RTGS/RTGSExport.aspx | Medium
RetailBanking | RTGS | RTGSExportNew.aspx | RetailBanking/RTGS/RTGSExportNew.aspx | Medium
RetailBanking | RTGS | RTGSExportUtrDet.aspx | RetailBanking/RTGS/RTGSExportUtrDet.aspx | Medium
RetailBanking | RTGS | RTGSImport.aspx | RetailBanking/RTGS/RTGSImport.aspx | Medium
RetailBanking | RTGS | RTGSImportFileStatus.aspx | RetailBanking/RTGS/RTGSImportFileStatus.aspx | Medium
RetailBanking | RTGS | RTGSImportReturn.aspx | RetailBanking/RTGS/RTGSImportReturn.aspx | Medium
RetailBanking | RTGS | RTGSPayment.aspx | RetailBanking/RTGS/RTGSPayment.aspx | Medium
RetailBanking | RTGS | RTGSPaymentReversalV1.aspx | RetailBanking/RTGS/RTGSPaymentReversalV1.aspx | Medium
RetailBanking | RTGS | RTGSPaymentV2.aspx | RetailBanking/RTGS/RTGSPaymentV2.aspx | Medium
RetailBanking | RTGS | RTGSPaymentV3.aspx | RetailBanking/RTGS/RTGSPaymentV3.aspx | Medium
RetailBanking | RTGS | RTGSPaymentv1.aspx | RetailBanking/RTGS/RTGSPaymentv1.aspx | Medium
RetailBanking | RTGS | RTGSResponseImport.aspx | RetailBanking/RTGS/RTGSResponseImport.aspx | Medium
RetailBanking | RTGS | RTGSRetMark.aspx | RetailBanking/RTGS/RTGSRetMark.aspx | Medium
RetailBanking | RTGS | RtgsIftsDashEnqForm.aspx | RetailBanking/RTGS/RtgsIftsDashEnqForm.aspx | Medium
RetailBanking | RTGS | RtgsIftsDashEnqFormPopUp.aspx | RetailBanking/RTGS/RtgsIftsDashEnqFormPopUp.aspx | Medium
RetailBanking | RTGS | rtgspaymentbatch.aspx | RetailBanking/RTGS/rtgspaymentbatch.aspx | Medium
RetailBanking | RTGS | rtgspaymentbatch_popup.aspx | RetailBanking/RTGS/rtgspaymentbatch_popup.aspx | Medium
RetailBanking | RTGS | rtgspaymentbatch_upload.aspx | RetailBanking/RTGS/rtgspaymentbatch_upload.aspx | Medium
RetailBanking | RTGS | x_RTGSRstrctDate.aspx | RetailBanking/RTGS/x_RTGSRstrctDate.aspx | Medium
RetailBanking |  | SBIntCalcLogDetail.aspx | RetailBanking/SBIntCalcLogDetail.aspx | Medium
RetailBanking | SI | standingInstructionProcessing.aspx | RetailBanking/SI/standingInstructionProcessing.aspx | Medium
RetailBanking | SI | x_StandingInstruction.aspx | RetailBanking/SI/x_StandingInstruction.aspx | Medium
RetailBanking | SMS | sms_registeredAccount.aspx | RetailBanking/SMS/sms_registeredAccount.aspx | Medium
RetailBanking | SMS | sms_registeredAccountDetails.aspx | RetailBanking/SMS/sms_registeredAccountDetails.aspx | Medium
RetailBanking |  | SearchUtility.aspx | RetailBanking/SearchUtility.aspx | Medium
RetailBanking | ServiceTaxCalculation | serviceTaxCalculation.aspx | RetailBanking/ServiceTaxCalculation/serviceTaxCalculation.aspx | Medium
RetailBanking | ServiceTaxCalculation | x_ServiceTaxAccountHeadMapping.aspx | RetailBanking/ServiceTaxCalculation/x_ServiceTaxAccountHeadMapping.aspx | Medium
RetailBanking |  | SignaturePreview.aspx | RetailBanking/SignaturePreview.aspx | Medium
RetailBanking |  | StatusModification.aspx | RetailBanking/StatusModification.aspx | Medium
RetailBanking | TDS | d_TDSCalculation.aspx | RetailBanking/TDS/d_TDSCalculation.aspx | Medium
RetailBanking | TDS | x_ManualTDSDeduction.aspx | RetailBanking/TDS/x_ManualTDSDeduction.aspx | Medium
RetailBanking | TDS | x_ManualTDSReverse.aspx | RetailBanking/TDS/x_ManualTDSReverse.aspx | Medium
RetailBanking | TDS | x_TDSLedger.aspx | RetailBanking/TDS/x_TDSLedger.aspx | Medium
RetailBanking | Transaction | AccountDetailsView.aspx | RetailBanking/Transaction/AccountDetailsView.aspx | Complex
RetailBanking | Transaction | AccountSearchByClient.aspx | RetailBanking/Transaction/AccountSearchByClient.aspx | Complex
RetailBanking | Transaction | CCODAddLimitPopup.aspx | RetailBanking/Transaction/CCODAddLimitPopup.aspx | Complex
RetailBanking | Transaction | ChargesRecView.aspx | RetailBanking/Transaction/ChargesRecView.aspx | Complex
RetailBanking | Transaction | CheaueBookDetailsPopup.aspx | RetailBanking/Transaction/CheaueBookDetailsPopup.aspx | Complex
RetailBanking | Transaction | DailyDepositBalanceTransferNew.aspx | RetailBanking/Transaction/DailyDepositBalanceTransferNew.aspx | Complex
RetailBanking | Transaction | DebitMandateImagePreview.aspx | RetailBanking/Transaction/DebitMandateImagePreview.aspx | Complex
RetailBanking | Transaction | DepAccountHistory.aspx | RetailBanking/Transaction/DepAccountHistory.aspx | Complex
RetailBanking | Transaction | DepositLienIntSlab.aspx | RetailBanking/Transaction/DepositLienIntSlab.aspx | Complex
RetailBanking | Transaction | ECSCrDrBatchDet.aspx | RetailBanking/Transaction/ECSCrDrBatchDet.aspx | Complex
RetailBanking | Transaction | ExceptionalLogViewer.aspx | RetailBanking/Transaction/ExceptionalLogViewer.aspx | Complex
RetailBanking | Transaction | IntPayWithdrawalPopup.aspx | RetailBanking/Transaction/IntPayWithdrawalPopup.aspx | Complex
RetailBanking | Transaction | LienDetails.aspx | RetailBanking/Transaction/LienDetails.aspx | Complex
RetailBanking | Transaction | LockerDetails.aspx | RetailBanking/Transaction/LockerDetails.aspx | Complex
RetailBanking | Transaction | RelatedAccountSearchByClient.aspx | RetailBanking/Transaction/RelatedAccountSearchByClient.aspx | Complex
RetailBanking | Transaction | SBCASecurityViewer.aspx | RetailBanking/Transaction/SBCASecurityViewer.aspx | Complex
RetailBanking | Transaction | ShowFDInterestDetails.aspx | RetailBanking/Transaction/ShowFDInterestDetails.aspx | Complex
RetailBanking | Transaction | ShowPigmyInterestDetails.aspx | RetailBanking/Transaction/ShowPigmyInterestDetails.aspx | Complex
RetailBanking | Transaction | ShowRDInterestDetails.aspx | RetailBanking/Transaction/ShowRDInterestDetails.aspx | Complex
RetailBanking | Transaction | SignaturePopup.aspx | RetailBanking/Transaction/SignaturePopup.aspx | Complex
RetailBanking | Transaction | b_AccountClosingTransactionNew.aspx | RetailBanking/Transaction/b_AccountClosingTransactionNew.aspx | Complex
RetailBanking | Transaction | b_AccountPartialClosingTransaction.aspx | RetailBanking/Transaction/b_AccountPartialClosingTransaction.aspx | Complex
RetailBanking | Transaction | b_DailyDepositInterestCalculationNew.aspx | RetailBanking/Transaction/b_DailyDepositInterestCalculationNew.aspx | Complex
RetailBanking | Transaction | b_InoperativeIR.aspx | RetailBanking/Transaction/b_InoperativeIR.aspx | Complex
RetailBanking | Transaction | b_dailyClientAccountRenewal.aspx | RetailBanking/Transaction/b_dailyClientAccountRenewal.aspx | Complex
RetailBanking | Transaction | d_MatDepClsTrf.aspx | RetailBanking/Transaction/d_MatDepClsTrf.aspx | Complex
RetailBanking | Transaction | ecs_MandateReport.aspx | RetailBanking/Transaction/ecs_MandateReport.aspx | Report
RetailBanking | Transaction | ibt_headmap.aspx | RetailBanking/Transaction/ibt_headmap.aspx | Complex
RetailBanking | Transaction | sh_signature.aspx | RetailBanking/Transaction/sh_signature.aspx | Complex
RetailBanking | Transaction | AccountSelector.aspx | RetailBanking/Transaction/userControls/AccountSelector.aspx | Complex
RetailBanking | Transaction | x_AchSponsorTransactionPosting.aspx | RetailBanking/Transaction/x_AchSponsorTransactionPosting.aspx | Complex
RetailBanking | Transaction | x_BatchTransactionTemplate.aspx | RetailBanking/Transaction/x_BatchTransactionTemplate.aspx | Complex
RetailBanking | Transaction | x_CashBatchTransaction.aspx | RetailBanking/Transaction/x_CashBatchTransaction.aspx | Complex
RetailBanking | Transaction | x_DailyDepositTransactionFromToDateAllnew.aspx | RetailBanking/Transaction/x_DailyDepositTransactionFromToDateAllnew.aspx | Complex
RetailBanking | Transaction | x_DeafClaim.aspx | RetailBanking/Transaction/x_DeafClaim.aspx | Complex
RetailBanking | Transaction | x_DemandGeneration.aspx | RetailBanking/Transaction/x_DemandGeneration.aspx | Complex
RetailBanking | Transaction | x_DividendTransaction.aspx | RetailBanking/Transaction/x_DividendTransaction.aspx | Complex
RetailBanking | Transaction | x_FDRAutoTransferTransaction.aspx | RetailBanking/Transaction/x_FDRAutoTransferTransaction.aspx | Complex
RetailBanking | Transaction | x_FDRenewalTransaction.aspx | RetailBanking/Transaction/x_FDRenewalTransaction.aspx | Complex
RetailBanking | Transaction | x_FdPayableCashPayment.aspx | RetailBanking/Transaction/x_FdPayableCashPayment.aspx | Complex
RetailBanking | Transaction | x_GovSecInvestmentCategoryTransfer.aspx | RetailBanking/Transaction/x_GovSecInvestmentCategoryTransfer.aspx | Complex
RetailBanking | Transaction | x_GovSecInvestmentEarmark.aspx | RetailBanking/Transaction/x_GovSecInvestmentEarmark.aspx | Complex
RetailBanking | Transaction | x_GovSecInvestmentReleaseEarmark.aspx | RetailBanking/Transaction/x_GovSecInvestmentReleaseEarmark.aspx | Complex
RetailBanking | Transaction | x_GovSecInvestmentTransfer.aspx | RetailBanking/Transaction/x_GovSecInvestmentTransfer.aspx | Complex
RetailBanking | Transaction | x_GovtSecInvestmentImport.aspx | RetailBanking/Transaction/x_GovtSecInvestmentImport.aspx | Complex
RetailBanking | Transaction | x_GovtSecInvestmentImportConfig.aspx | RetailBanking/Transaction/x_GovtSecInvestmentImportConfig.aspx | Complex
RetailBanking | Transaction | x_GovtSecInvestmentImportTransaction.aspx | RetailBanking/Transaction/x_GovtSecInvestmentImportTransaction.aspx | Complex
RetailBanking | Transaction | x_GovtSecMarketValueImport.aspx | RetailBanking/Transaction/x_GovtSecMarketValueImport.aspx | Complex
RetailBanking | Transaction | x_IncomeSTtrasaction.aspx | RetailBanking/Transaction/x_IncomeSTtrasaction.aspx | Complex
RetailBanking | Transaction | x_InvestmentClosingTransaction.aspx | RetailBanking/Transaction/x_InvestmentClosingTransaction.aspx | Complex
RetailBanking | Transaction | x_InvestmentInterestSettlementTransaction.aspx | RetailBanking/Transaction/x_InvestmentInterestSettlementTransaction.aspx | Complex
RetailBanking | Transaction | x_InvestmentMoneyTrade.aspx | RetailBanking/Transaction/x_InvestmentMoneyTrade.aspx | Complex
RetailBanking | Transaction | x_InvestmentMultipleSaleTransaction.aspx | RetailBanking/Transaction/x_InvestmentMultipleSaleTransaction.aspx | Complex
RetailBanking | Transaction | x_InvestmentPurchaseRepo.aspx | RetailBanking/Transaction/x_InvestmentPurchaseRepo.aspx | Complex
RetailBanking | Transaction | x_InvestmentRenewalTransaction.aspx | RetailBanking/Transaction/x_InvestmentRenewalTransaction.aspx | Complex
RetailBanking | Transaction | x_InvestmentTransaction.aspx | RetailBanking/Transaction/x_InvestmentTransaction.aspx | Complex
RetailBanking | Transaction | x_LedgerClientTdsCashRev.aspx | RetailBanking/Transaction/x_LedgerClientTdsCashRev.aspx | Complex
RetailBanking | Transaction | x_LoanFDSettlement.aspx | RetailBanking/Transaction/x_LoanFDSettlement.aspx | Complex
RetailBanking | Transaction | x_LoanInsuranceChargesPosting.aspx | RetailBanking/Transaction/x_LoanInsuranceChargesPosting.aspx | Complex
RetailBanking | Transaction | x_LockRelease.aspx | RetailBanking/Transaction/x_LockRelease.aspx | Complex
RetailBanking | Transaction | x_MICRECSAccountDetailsPopup.aspx | RetailBanking/Transaction/x_MICRECSAccountDetailsPopup.aspx | Complex
RetailBanking | Transaction | x_MICRECSCreditManualStatus.aspx | RetailBanking/Transaction/x_MICRECSCreditManualStatus.aspx | Complex
RetailBanking | Transaction | x_MICRECSGenerateReturnFile.aspx | RetailBanking/Transaction/x_MICRECSGenerateReturnFile.aspx | Complex
RetailBanking | Transaction | x_MICRECSManualStatus.aspx | RetailBanking/Transaction/x_MICRECSManualStatus.aspx | Complex
RetailBanking | Transaction | x_MICRECSOACGenerateFile.aspx | RetailBanking/Transaction/x_MICRECSOACGenerateFile.aspx | Complex
RetailBanking | Transaction | x_MICRECSOACGenerateFilePopup.aspx | RetailBanking/Transaction/x_MICRECSOACGenerateFilePopup.aspx | Complex
RetailBanking | Transaction | x_MICRECSPaymentGenerateReturnFile.aspx | RetailBanking/Transaction/x_MICRECSPaymentGenerateReturnFile.aspx | Complex
RetailBanking | Transaction | x_MICRECSPaymentManualStatus.aspx | RetailBanking/Transaction/x_MICRECSPaymentManualStatus.aspx | Complex
RetailBanking | Transaction | x_MICRECSPaymentProcessFile.aspx | RetailBanking/Transaction/x_MICRECSPaymentProcessFile.aspx | Complex
RetailBanking | Transaction | x_MICRECSPaymentProcessFilePopup.aspx | RetailBanking/Transaction/x_MICRECSPaymentProcessFilePopup.aspx | Complex
RetailBanking | Transaction | x_MICRECSPaymentProcessFileReport.aspx | RetailBanking/Transaction/x_MICRECSPaymentProcessFileReport.aspx | Report
RetailBanking | Transaction | x_MICRECSPaymentTransactionPosting_v1.aspx | RetailBanking/Transaction/x_MICRECSPaymentTransactionPosting_v1.aspx | Complex
RetailBanking | Transaction | x_MICRECSPaymentUploadFile.aspx | RetailBanking/Transaction/x_MICRECSPaymentUploadFile.aspx | Complex
RetailBanking | Transaction | x_MICRECSProcessFileData_v2.aspx | RetailBanking/Transaction/x_MICRECSProcessFileData_v2.aspx | Complex
RetailBanking | Transaction | x_MICRECSProcessFilePopup.aspx | RetailBanking/Transaction/x_MICRECSProcessFilePopup.aspx | Complex
RetailBanking | Transaction | x_MICRECSTransactionPosting.aspx | RetailBanking/Transaction/x_MICRECSTransactionPosting.aspx | Complex
RetailBanking | Transaction | x_MICRECSUploadFile.aspx | RetailBanking/Transaction/x_MICRECSUploadFile.aspx | Complex
RetailBanking | Transaction | x_ManyToManyTranPopUp.aspx | RetailBanking/Transaction/x_ManyToManyTranPopUp.aspx | Complex
RetailBanking | Transaction | x_ManyToManyTransactionIBT_V1.aspx | RetailBanking/Transaction/x_ManyToManyTransactionIBT_V1.aspx | Complex
RetailBanking | Transaction | x_NonOprClaim.aspx | RetailBanking/Transaction/x_NonOprClaim.aspx | Complex
RetailBanking | Transaction | x_NonOprClaimReceived.aspx | RetailBanking/Transaction/x_NonOprClaimReceived.aspx | Complex
RetailBanking | Transaction | x_NonOprDepositPost.aspx | RetailBanking/Transaction/x_NonOprDepositPost.aspx | Complex
RetailBanking | Transaction | x_NonOprDepositPostPopup.aspx | RetailBanking/Transaction/x_NonOprDepositPostPopup.aspx | Complex
RetailBanking | Transaction | x_NonOprDepositTrf.aspx | RetailBanking/Transaction/x_NonOprDepositTrf.aspx | Complex
RetailBanking | Transaction | x_NonOprDepositTrfPopup.aspx | RetailBanking/Transaction/x_NonOprDepositTrfPopup.aspx | Complex
RetailBanking | Transaction | x_P2BDemandGeneration.aspx | RetailBanking/Transaction/x_P2BDemandGeneration.aspx | Complex
RetailBanking | Transaction | x_PigmyCommCalculateNewV1.aspx | RetailBanking/Transaction/x_PigmyCommCalculateNewV1.aspx | Complex
RetailBanking | Transaction | x_PigmyExportSetting.aspx | RetailBanking/Transaction/x_PigmyExportSetting.aspx | Complex
RetailBanking | Transaction | x_PigmyProductTransactionDetails.aspx | RetailBanking/Transaction/x_PigmyProductTransactionDetails.aspx | Complex
RetailBanking | Transaction | x_ProfitLossSummation.aspx | RetailBanking/Transaction/x_ProfitLossSummation.aspx | Complex
RetailBanking | Transaction | x_ProfitLossSummationPopup.aspx | RetailBanking/Transaction/x_ProfitLossSummationPopup.aspx | Complex
RetailBanking | Transaction | x_ProfitLossSummationV1.aspx | RetailBanking/Transaction/x_ProfitLossSummationV1.aspx | Complex
RetailBanking | Transaction | x_PurchaseDealNumber.aspx | RetailBanking/Transaction/x_PurchaseDealNumber.aspx | Complex
RetailBanking | Transaction | x_RDAccountClosing.aspx | RetailBanking/Transaction/x_RDAccountClosing.aspx | Complex
RetailBanking | Transaction | x_RDProduct.aspx | RetailBanking/Transaction/x_RDProduct.aspx | Complex
RetailBanking | Transaction | x_SbCaRdAccountClosing.aspx | RetailBanking/Transaction/x_SbCaRdAccountClosing.aspx | Complex
RetailBanking | Transaction | x_SignatureImage.aspx | RetailBanking/Transaction/x_SignatureImage.aspx | Complex
RetailBanking | Transaction | x_TransClientAccODDet.aspx | RetailBanking/Transaction/x_TransClientAccODDet.aspx | Complex
RetailBanking | Transaction | x_TransactionOtherDetails.aspx | RetailBanking/Transaction/x_TransactionOtherDetails.aspx | Complex
RetailBanking | Transaction | x_TransactionOtherDetailsOld.aspx | RetailBanking/Transaction/x_TransactionOtherDetailsOld.aspx | Complex
RetailBanking | Transaction | x_investmentAmortisationCalc.aspx | RetailBanking/Transaction/x_investmentAmortisationCalc.aspx | Complex
RetailBanking | Transaction | x_pigmyTrfAmtToLinkAcc.aspx | RetailBanking/Transaction/x_pigmyTrfAmtToLinkAcc.aspx | Complex
RetailBanking | Transaction | x_transaction_js_cash_handler.aspx | RetailBanking/Transaction/x_transaction_js_cash_handler.aspx | Complex
RetailBanking | Transaction | x_transaction_js_ibt_cash_handler.aspx | RetailBanking/Transaction/x_transaction_js_ibt_cash_handler.aspx | Complex
RetailBanking | Transaction | x_transaction_js_ibt_trf_handler.aspx | RetailBanking/Transaction/x_transaction_js_ibt_trf_handler.aspx | Complex
RetailBanking | Transaction | x_transaction_js_transfer_handler.aspx | RetailBanking/Transaction/x_transaction_js_transfer_handler.aspx | Complex
RetailBanking | Transaction | x_transactionv1.aspx | RetailBanking/Transaction/x_transactionv1.aspx | Complex
RetailBanking |  | UserDefLetterTemplateCons.aspx | RetailBanking/UserDefLetterTemplateCons.aspx | Medium
RetailBanking | Utilities | CentralizedDayBegin.aspx | RetailBanking/Utilities/CentralizedDayBegin.aspx | Medium
RetailBanking | Utilities | DayendCentral.aspx | RetailBanking/Utilities/DayendCentral.aspx | Medium
RetailBanking | Utilities | DayendLog.aspx | RetailBanking/Utilities/DayendLog.aspx | Medium
RetailBanking | Utilities | DayendParamConfig.aspx | RetailBanking/Utilities/DayendParamConfig.aspx | Medium
RetailBanking | Utilities | LedgerUpdateReq.aspx | RetailBanking/Utilities/LedgerUpdateReq.aspx | Medium
RetailBanking | Utilities | LogDetails.aspx | RetailBanking/Utilities/LogDetails.aspx | Medium
RetailBanking | Utilities | SMSOtherChLog.aspx | RetailBanking/Utilities/SMSOtherChLog.aspx | Medium
RetailBanking | Utilities | c_RepaymentSchedule.aspx | RetailBanking/Utilities/c_RepaymentSchedule.aspx | Medium
RetailBanking |  | ValidateBenName.aspx | RetailBanking/ValidateBenName.aspx | Medium
RetailBanking |  | VerifyMobNo.aspx | RetailBanking/VerifyMobNo.aspx | Medium
RetailBanking |  | VoucherPrintPopup.aspx | RetailBanking/VoucherPrintPopup.aspx | Medium
RetailBanking |  | VoucherPrinting.aspx | RetailBanking/VoucherPrinting.aspx | Medium
RetailBanking |  | VoucherViewer.aspx | RetailBanking/VoucherViewer.aspx | Medium
RetailBanking |  | VoucherViewerPopup.aspx | RetailBanking/VoucherViewerPopup.aspx | Medium
RetailBanking |  | WriteOffAccount.aspx | RetailBanking/WriteOffAccount.aspx | Medium
RetailBanking |  | WriteOffRecovery.aspx | RetailBanking/WriteOffRecovery.aspx | Medium
RetailBanking | YearEndActivities | BalanceTransfer.aspx | RetailBanking/YearEndActivities/BalanceTransfer.aspx | Medium
RetailBanking | YearEndActivities | YearEnd.aspx | RetailBanking/YearEndActivities/YearEnd.aspx | Medium
RetailBanking |  | a_UserPassTranLimit.aspx | RetailBanking/a_UserPassTranLimit.aspx | Medium
RetailBanking | aadhar | PfmsTranReport.aspx | RetailBanking/aadhar/PfmsTranReport.aspx | Report
RetailBanking | aadhar | aadhar_mapping_request.aspx | RetailBanking/aadhar/aadhar_mapping_request.aspx | Medium
RetailBanking | aadhar | ach_inward.aspx | RetailBanking/aadhar/ach_inward.aspx | Medium
RetailBanking | aadhar | apbs_inward.aspx | RetailBanking/aadhar/apbs_inward.aspx | Medium
RetailBanking | aadhar | apbs_inwardprocess_details.aspx | RetailBanking/aadhar/apbs_inwardprocess_details.aspx | Medium
RetailBanking | aadhar | dbtl.aspx | RetailBanking/aadhar/dbtl.aspx | Medium
RetailBanking |  | accchargewaiveoff.aspx | RetailBanking/accchargewaiveoff.aspx | Medium
RetailBanking |  | b_AccHoldingAmount.aspx | RetailBanking/b_AccHoldingAmount.aspx | Medium
RetailBanking |  | b_AccountHeadConfig.aspx | RetailBanking/b_AccountHeadConfig.aspx | Medium
RetailBanking |  | b_AgentAreaTrf.aspx | RetailBanking/b_AgentAreaTrf.aspx | Medium
RetailBanking |  | b_AgentDataTransferNew.aspx | RetailBanking/b_AgentDataTransferNew.aspx | Medium
RetailBanking |  | b_AgentFSATrf.aspx | RetailBanking/b_AgentFSATrf.aspx | Medium
RetailBanking |  | b_BranchDetails.aspx | RetailBanking/b_BranchDetails.aspx | Medium
RetailBanking |  | b_ClientTDSCashLimit.aspx | RetailBanking/b_ClientTDSCashLimit.aspx | Medium
RetailBanking |  | b_ContraActivityMapping.aspx | RetailBanking/b_ContraActivityMapping.aspx | Medium
RetailBanking |  | b_CounterParty.aspx | RetailBanking/b_CounterParty.aspx | Medium
RetailBanking |  | b_DailyClientAccountStatus.aspx | RetailBanking/b_DailyClientAccountStatus.aspx | Medium
RetailBanking |  | b_DayEndParamLogs.aspx | RetailBanking/b_DayEndParamLogs.aspx | Medium
RetailBanking |  | b_DayEndParamLogsCons.aspx | RetailBanking/b_DayEndParamLogsCons.aspx | Medium
RetailBanking |  | b_DayendCheckConfig.aspx | RetailBanking/b_DayendCheckConfig.aspx | Medium
RetailBanking |  | b_DividendFinYearCOAMap.aspx | RetailBanking/b_DividendFinYearCOAMap.aspx | Medium
RetailBanking |  | b_Document.aspx | RetailBanking/b_Document.aspx | Medium
RetailBanking |  | b_DocumentType.aspx | RetailBanking/b_DocumentType.aspx | Medium
RetailBanking |  | b_DormantLetterTemplate.aspx | RetailBanking/b_DormantLetterTemplate.aspx | Medium
RetailBanking |  | b_EmployeeSignature.aspx | RetailBanking/b_EmployeeSignature.aspx | Medium
RetailBanking |  | b_GlContraHeadMapping.aspx | RetailBanking/b_GlContraHeadMapping.aspx | Medium
RetailBanking |  | b_GovtSecEarmarkParticulars.aspx | RetailBanking/b_GovtSecEarmarkParticulars.aspx | Medium
RetailBanking |  | b_InvestmentAccountSetting.aspx | RetailBanking/b_InvestmentAccountSetting.aspx | Medium
RetailBanking |  | b_LoanInterestRule.aspx | RetailBanking/b_LoanInterestRule.aspx | Medium
RetailBanking |  | b_MFArea.aspx | RetailBanking/b_MFArea.aspx | Medium
RetailBanking |  | b_MFCreditOfficer.aspx | RetailBanking/b_MFCreditOfficer.aspx | Medium
RetailBanking |  | b_PigmyCommisionMapping.aspx | RetailBanking/b_PigmyCommisionMapping.aspx | Medium
RetailBanking |  | b_PreDisbQstEntry.aspx | RetailBanking/b_PreDisbQstEntry.aspx | Medium
RetailBanking |  | b_ProvisionShareCapital.aspx | RetailBanking/b_ProvisionShareCapital.aspx | Medium
RetailBanking |  | b_RdFdReadyRecknor.aspx | RetailBanking/b_RdFdReadyRecknor.aspx | Medium
RetailBanking |  | b_SMAMarking.aspx | RetailBanking/b_SMAMarking.aspx | Medium
RetailBanking |  | b_SchoolEmployer.aspx | RetailBanking/b_SchoolEmployer.aspx | Medium
RetailBanking |  | b_Signature.aspx | RetailBanking/b_Signature.aspx | Medium
RetailBanking |  | b_SmsAutoMarkCOAMap.aspx | RetailBanking/b_SmsAutoMarkCOAMap.aspx | Medium
RetailBanking |  | b_SocietiesMaster.aspx | RetailBanking/b_SocietiesMaster.aspx | Medium
RetailBanking |  | b_SpecialInstruction.aspx | RetailBanking/b_SpecialInstruction.aspx | Medium
RetailBanking |  | b_StaffRelieve.aspx | RetailBanking/b_StaffRelieve.aspx | Medium
RetailBanking |  | b_ThriftGuarSchemeMap.aspx | RetailBanking/b_ThriftGuarSchemeMap.aspx | Medium
RetailBanking |  | b_accwaiveoff.aspx | RetailBanking/b_accwaiveoff.aspx | Medium
RetailBanking |  | c_CCAddLimit.aspx | RetailBanking/c_CCAddLimit.aspx | Medium
RetailBanking |  | c_CCAddPeriod.aspx | RetailBanking/c_CCAddPeriod.aspx | Medium
RetailBanking |  | c_CaratMaster.aspx | RetailBanking/c_CaratMaster.aspx | Medium
RetailBanking |  | c_Community.aspx | RetailBanking/c_Community.aspx | Medium
RetailBanking |  | c_DepLoanCatAddlIR.aspx | RetailBanking/c_DepLoanCatAddlIR.aspx | Medium
RetailBanking |  | c_DepositAccDrLimit.aspx | RetailBanking/c_DepositAccDrLimit.aspx | Medium
RetailBanking |  | c_LNEnhancement.aspx | RetailBanking/c_LNEnhancement.aspx | Medium
RetailBanking |  | c_LNSchemeChange.aspx | RetailBanking/c_LNSchemeChange.aspx | Medium
RetailBanking |  | c_LNSchemeChangeDet.aspx | RetailBanking/c_LNSchemeChangeDet.aspx | Medium
RetailBanking |  | c_LoanDisbursement.aspx | RetailBanking/c_LoanDisbursement.aspx | Medium
RetailBanking |  | c_LoanScheme.aspx | RetailBanking/c_LoanScheme.aspx | Medium
RetailBanking |  | c_ODLimitDeduction.aspx | RetailBanking/c_ODLimitDeduction.aspx | Medium
RetailBanking |  | c_OrnamentMaster.aspx | RetailBanking/c_OrnamentMaster.aspx | Medium
RetailBanking |  | c_OtherReceivable.aspx | RetailBanking/c_OtherReceivable.aspx | Medium
RetailBanking |  | c_PACSHeadMapping.aspx | RetailBanking/c_PACSHeadMapping.aspx | Medium
RetailBanking |  | c_Priority.aspx | RetailBanking/c_Priority.aspx | Medium
RetailBanking |  | c_ReducingCCLimit.aspx | RetailBanking/c_ReducingCCLimit.aspx | Medium
RetailBanking |  | c_StockApplCOA.aspx | RetailBanking/c_StockApplCOA.aspx | Medium
RetailBanking |  | c_ValuatorMaster.aspx | RetailBanking/c_ValuatorMaster.aspx | Medium
RetailBanking |  | c_WeakerSection.aspx | RetailBanking/c_WeakerSection.aspx | Medium
RetailBanking |  | c_WriteOffStlHeadMap.aspx | RetailBanking/c_WriteOffStlHeadMap.aspx | Medium
RetailBanking |  | d_fdRtgsProcess.aspx | RetailBanking/d_fdRtgsProcess.aspx | Medium
RetailBanking | dd | DDListExport.aspx | RetailBanking/dd/DDListExport.aspx | Medium
RetailBanking | dd | DDPO_Mapping.aspx | RetailBanking/dd/DDPO_Mapping.aspx | Medium
RetailBanking | dd | DemandDraftPayOrderSeries.aspx | RetailBanking/dd/DemandDraftPayOrderSeries.aspx | Medium
RetailBanking | dd | PODDStaleDateUpdate.aspx | RetailBanking/dd/PODDStaleDateUpdate.aspx | Medium
RetailBanking | dd | b_FDCertificateSeries.aspx | RetailBanking/dd/b_FDCertificateSeries.aspx | Medium
RetailBanking | dd | dd.aspx | RetailBanking/dd/dd.aspx | Medium
RetailBanking | dd | x_DDCancel.aspx | RetailBanking/dd/x_DDCancel.aspx | Medium
RetailBanking | dormant | DormantReActivation.aspx | RetailBanking/dormant/DormantReActivation.aspx | Medium
RetailBanking | dormant | b_DormantHistory.aspx | RetailBanking/dormant/b_DormantHistory.aspx | Medium
RetailBanking |  | fi.aspx | RetailBanking/fi.aspx | Medium
RetailBanking |  | g_AllowDebitTransactionAccountHeads.aspx | RetailBanking/g_AllowDebitTransactionAccountHeads.aspx | Complex
RetailBanking |  | g_ClientDocRcvdStatus.aspx | RetailBanking/g_ClientDocRcvdStatus.aspx | Medium
RetailBanking |  | g_CustomerDetailView.aspx | RetailBanking/g_CustomerDetailView.aspx | Medium
RetailBanking |  | g_CustomerDetailView_v1.aspx | RetailBanking/g_CustomerDetailView_v1.aspx | Medium
RetailBanking |  | g_FundDistributionAverage.aspx | RetailBanking/g_FundDistributionAverage.aspx | Medium
RetailBanking |  | g_IfscDetailView.aspx | RetailBanking/g_IfscDetailView.aspx | Medium
RetailBanking |  | k_LockerExpiryLetterTemplate.aspx | RetailBanking/k_LockerExpiryLetterTemplate.aspx | Medium
RetailBanking |  | loanRepayment.aspx | RetailBanking/loanRepayment.aspx | Medium
RetailBanking |  | mBankUPIColQRPrint.aspx | RetailBanking/mBankUPIColQRPrint.aspx | Medium
RetailBanking |  | mBank_LimitConfig.aspx | RetailBanking/mBank_LimitConfig.aspx | Medium
RetailBanking |  | maturedButNotPaid.aspx | RetailBanking/maturedButNotPaid.aspx | Medium
RetailBanking |  | mbankUPICollManual.aspx | RetailBanking/mbankUPICollManual.aspx | Medium
RetailBanking |  | mbank_upicoll_qr_sound_Terminal.aspx | RetailBanking/mbank_upicoll_qr_sound_Terminal.aspx | Medium
RetailBanking |  | openingBalance.aspx | RetailBanking/openingBalance.aspx | Medium
RetailBanking | pmby | APY_DeathClaim.aspx | RetailBanking/pmby/APY_DeathClaim.aspx | Medium
RetailBanking | pmby | PMBYMemsettlementView.aspx | RetailBanking/pmby/PMBYMemsettlementView.aspx | Medium
RetailBanking | pmby | Pmby_PolicyMaster.aspx | RetailBanking/pmby/Pmby_PolicyMaster.aspx | Medium
RetailBanking | pmby | SocialSchemeDetails.aspx | RetailBanking/pmby/SocialSchemeDetails.aspx | Medium
RetailBanking | pmby | apy.aspx | RetailBanking/pmby/apy.aspx | Medium
RetailBanking | pmby | pmby.aspx | RetailBanking/pmby/pmby.aspx | Medium
RetailBanking |  | rescheduleLoanRepayment.aspx | RetailBanking/rescheduleLoanRepayment.aspx | Medium
RetailBanking |  | unPassedTransaction.aspx | RetailBanking/unPassedTransaction.aspx | Complex
RetailBanking | user_worksheet | User_target_achivement.aspx | RetailBanking/user_worksheet/User_target_achivement.aspx | Medium
RetailBanking | user_worksheet | user_monthly_target.aspx | RetailBanking/user_worksheet/user_monthly_target.aspx | Medium
RetailBanking |  | x_BatchTransactionLog.aspx | RetailBanking/x_BatchTransactionLog.aspx | Complex
RetailBanking |  | x_ChargesReversal.aspx | RetailBanking/x_ChargesReversal.aspx | Medium
RetailBanking |  | x_ChequeBook.aspx | RetailBanking/x_ChequeBook.aspx | Medium
RetailBanking |  | x_ChequeBookAutoImport.aspx | RetailBanking/x_ChequeBookAutoImport.aspx | Medium
RetailBanking |  | x_ChequeReturnReason.aspx | RetailBanking/x_ChequeReturnReason.aspx | Medium
RetailBanking |  | x_ChequeStatusRevert.aspx | RetailBanking/x_ChequeStatusRevert.aspx | Medium
RetailBanking |  | x_ChequeStopPaymentDetails.aspx | RetailBanking/x_ChequeStopPaymentDetails.aspx | Medium
RetailBanking |  | x_ClientKYCLetterTemplate.aspx | RetailBanking/x_ClientKYCLetterTemplate.aspx | Medium
RetailBanking |  | x_CutOffLnCcOdRecovery.aspx | RetailBanking/x_CutOffLnCcOdRecovery.aspx | Medium
RetailBanking |  | x_IROIRSettlement.aspx | RetailBanking/x_IROIRSettlement.aspx | Medium
RetailBanking |  | x_LNCCAccumInt.aspx | RetailBanking/x_LNCCAccumInt.aspx | Medium
RetailBanking |  | x_LNCCCRecCharge.aspx | RetailBanking/x_LNCCCRecCharge.aspx | Medium
RetailBanking |  | x_LooseChequeDetail.aspx | RetailBanking/x_LooseChequeDetail.aspx | Medium
RetailBanking |  | x_MarkingForm6061.aspx | RetailBanking/x_MarkingForm6061.aspx | Medium
RetailBanking |  | x_NoTranTemplate.aspx | RetailBanking/x_NoTranTemplate.aspx | Medium
RetailBanking |  | x_NonOprPAN.aspx | RetailBanking/x_NonOprPAN.aspx | Medium
RetailBanking |  | x_NoticeCharges.aspx | RetailBanking/x_NoticeCharges.aspx | Medium
RetailBanking |  | x_OverdueLetterTemplate.aspx | RetailBanking/x_OverdueLetterTemplate.aspx | Medium
RetailBanking |  | x_PACSLoanDisbursement.aspx | RetailBanking/x_PACSLoanDisbursement.aspx | Medium
RetailBanking |  | x_PACSRecovery.aspx | RetailBanking/x_PACSRecovery.aspx | Medium
RetailBanking |  | x_ReconciliationHead.aspx | RetailBanking/x_ReconciliationHead.aspx | Medium
RetailBanking |  | x_SalSchemeRegisExport.aspx | RetailBanking/x_SalSchemeRegisExport.aspx | Medium
RetailBanking |  | x_SalSchemeRegistration.aspx | RetailBanking/x_SalSchemeRegistration.aspx | Medium
RetailBanking |  | x_SalSchemeRegistrationReports.aspx | RetailBanking/x_SalSchemeRegistrationReports.aspx | Report
RetailBanking |  | x_SalSchemeRegistrationSearchReport.aspx | RetailBanking/x_SalSchemeRegistrationSearchReport.aspx | Report
RetailBanking |  | x_TranAccHeadRestrict.aspx | RetailBanking/x_TranAccHeadRestrict.aspx | Medium
RetailBanking |  | x_UnAppliedLedgerView.aspx | RetailBanking/x_UnAppliedLedgerView.aspx | Medium
RetailBanking |  | x_WelcomeLetterTemplate.aspx | RetailBanking/x_WelcomeLetterTemplate.aspx | Medium
RetailBanking |  | x_chequeBookPrintData.aspx | RetailBanking/x_chequeBookPrintData.aspx | Medium
RetailBanking |  | x_chequeBookPrintDataExport.aspx | RetailBanking/x_chequeBookPrintDataExport.aspx | Medium
RetailBanking |  | x_loansettlement.aspx | RetailBanking/x_loansettlement.aspx | Medium
ServiceBranch |  | b_BranchAdjInt.aspx | ServiceBranch/b_BranchAdjInt.aspx | Simple
StatutoryReports |  | StatutoryExcelReportSave.aspx | StatutoryReports/StatutoryExcelReportSave.aspx | Report
StatutoryReports |  | StatutoryReportData.aspx | StatutoryReports/StatutoryReportData.aspx | Report
StatutoryReports |  | StautoryReportDetails.aspx | StatutoryReports/StautoryReportDetails.aspx | Report
UserControls |  | MessageBox.aspx | UserControls/MessageBox.aspx | Medium
UserControls |  | RecordSelector.aspx | UserControls/RecordSelector.aspx | Medium
UserControls |  | RecordSelectorV2.aspx | UserControls/RecordSelectorV2.aspx | Medium
UserControls |  | SearchAdvanced.aspx | UserControls/SearchAdvanced.aspx | Medium
(root) |  | ad_ajax_dac.aspx | ad_ajax_dac.aspx | Simple
ajax |  | commonV2.aspx | ajax/commonV2.aspx | Medium
ajax |  | commonv1.aspx | ajax/commonv1.aspx | Medium
(root) |  | apperror.aspx | apperror.aspx | Simple
(root) |  | customised_reports.aspx | customised_reports.aspx | Report
(root) |  | dosprint.aspx | dosprint.aspx | Simple
(root) |  | download.aspx | download.aspx | Simple
external_api | DL | drivinglicense_verify_handler.aspx | external_api/DL/drivinglicense_verify_handler.aspx | Medium
external_api | aadhaar | aadhaar_verify_handler.aspx | external_api/aadhaar/aadhaar_verify_handler.aspx | Medium
external_api | cust_onboard | customer_onboarding_handler.aspx | external_api/cust_onboard/customer_onboarding_handler.aspx | Medium
external_api | pan | pan_verify_handler.aspx | external_api/pan/pan_verify_handler.aspx | Medium
external_api | votercard | votercard_verify_handler.aspx | external_api/votercard/votercard_verify_handler.aspx | Medium
fp |  | a_logintype.aspx | fp/a_logintype.aspx | Medium
fp |  | fp_auth_handler.aspx | fp/fp_auth_handler.aspx | Medium
fp |  | fp_authorize.aspx | fp/fp_authorize.aspx | Medium
fp |  | login_handler.aspx | fp/login_handler.aspx | Medium
fp | mfs100 | fpui.aspx | fp/mfs100/fpui.aspx | Medium
(root) |  | login_otp_verify.aspx | login_otp_verify.aspx | Simple
(root) |  | login_otp_verify_handler.aspx | login_otp_verify_handler.aspx | Simple
(root) |  | logout.aspx | logout.aspx | Simple